## Risk_Knowledge_Base
Risk_ID | Risk_Category | Risk_Keyword | Sector | Project_Type | Contract_Type | Typical_Probability | Typical_Impact | Quantification_Method | Key_Reference | Reference_Year
1 | Political & Regulatory | Political instability | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
2 | Political & Regulatory | Policy change | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
3 | Political & Regulatory | Permit delay | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
4 | Political & Regulatory | Regulatory uncertainty | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
5 | Political & Regulatory | Change in law | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
6 | Political & Regulatory | Nationalization risk | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
7 | Political & Regulatory | Local opposition | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
8 | Political & Regulatory | Tariff reform | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
9 | Political & Regulatory | Political instability | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
10 | Political & Regulatory | Policy change | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
11 | Political & Regulatory | Permit delay | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
12 | Political & Regulatory | Regulatory uncertainty | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
13 | Political & Regulatory | Change in law | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
14 | Political & Regulatory | Nationalization risk | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
15 | Political & Regulatory | Local opposition | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
16 | Political & Regulatory | Tariff reform | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
17 | Political & Regulatory | Political instability | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
18 | Political & Regulatory | Policy change | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
19 | Political & Regulatory | Permit delay | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
20 | Political & Regulatory | Regulatory uncertainty | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
21 | Political & Regulatory | Change in law | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
22 | Political & Regulatory | Nationalization risk | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
23 | Political & Regulatory | Local opposition | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
24 | Political & Regulatory | Tariff reform | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
25 | Political & Regulatory | Political instability | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
26 | Political & Regulatory | Policy change | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
27 | Political & Regulatory | Permit delay | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
28 | Political & Regulatory | Regulatory uncertainty | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
29 | Political & Regulatory | Change in law | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
30 | Political & Regulatory | Nationalization risk | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
31 | Political & Regulatory | Local opposition | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
32 | Political & Regulatory | Tariff reform | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
33 | Contractual & Legal | Ambiguous clauses | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
34 | Contractual & Legal | Unbalanced risk allocation | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
35 | Contractual & Legal | Force majeure | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
36 | Contractual & Legal | Claims escalation | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
37 | Contractual & Legal | Dispute resolution delay | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
38 | Contractual & Legal | Liquidated damages | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
39 | Contractual & Legal | Change order disputes | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
40 | Contractual & Legal | Contract interpretation risk | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
41 | Contractual & Legal | Ambiguous clauses | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
42 | Contractual & Legal | Unbalanced risk allocation | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
43 | Contractual & Legal | Force majeure | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
44 | Contractual & Legal | Claims escalation | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
45 | Contractual & Legal | Dispute resolution delay | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
46 | Contractual & Legal | Liquidated damages | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
47 | Contractual & Legal | Change order disputes | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
48 | Contractual & Legal | Contract interpretation risk | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
49 | Contractual & Legal | Ambiguous clauses | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
50 | Contractual & Legal | Unbalanced risk allocation | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
51 | Contractual & Legal | Force majeure | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
52 | Contractual & Legal | Claims escalation | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
53 | Contractual & Legal | Dispute resolution delay | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
54 | Contractual & Legal | Liquidated damages | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
55 | Contractual & Legal | Change order disputes | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
56 | Contractual & Legal | Contract interpretation risk | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
57 | Contractual & Legal | Ambiguous clauses | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
58 | Contractual & Legal | Unbalanced risk allocation | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
59 | Contractual & Legal | Force majeure | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
60 | Contractual & Legal | Claims escalation | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
61 | Contractual & Legal | Dispute resolution delay | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
62 | Contractual & Legal | Liquidated damages | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
63 | Contractual & Legal | Change order disputes | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
64 | Contractual & Legal | Contract interpretation risk | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
65 | Financial & Commercial | Cost overrun | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
66 | Financial & Commercial | Inflation escalation | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
67 | Financial & Commercial | Currency fluctuation | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
68 | Financial & Commercial | Payment delay | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
69 | Financial & Commercial | Financing risk | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
70 | Financial & Commercial | Revenue shortfall | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
71 | Financial & Commercial | Interest rate volatility | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
72 | Financial & Commercial | Cost overrun | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
73 | Financial & Commercial | Inflation escalation | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
74 | Financial & Commercial | Currency fluctuation | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
75 | Financial & Commercial | Payment delay | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
76 | Financial & Commercial | Financing risk | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
77 | Financial & Commercial | Revenue shortfall | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
78 | Financial & Commercial | Interest rate volatility | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
79 | Financial & Commercial | Cost overrun | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
80 | Financial & Commercial | Inflation escalation | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
81 | Financial & Commercial | Currency fluctuation | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
82 | Financial & Commercial | Payment delay | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
83 | Financial & Commercial | Financing risk | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
84 | Financial & Commercial | Revenue shortfall | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
85 | Financial & Commercial | Interest rate volatility | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
86 | Financial & Commercial | Cost overrun | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
87 | Financial & Commercial | Inflation escalation | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
88 | Financial & Commercial | Currency fluctuation | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
89 | Financial & Commercial | Payment delay | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
90 | Financial & Commercial | Financing risk | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
91 | Financial & Commercial | Revenue shortfall | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
92 | Financial & Commercial | Interest rate volatility | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
93 | Technical & Design | Design errors | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
94 | Technical & Design | Technology immaturity | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
95 | Technical & Design | Interface risk | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
96 | Technical & Design | Performance shortfall | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
97 | Technical & Design | Equipment failure | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
98 | Technical & Design | Grid integration failure | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
99 | Technical & Design | Design errors | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
100 | Technical & Design | Technology immaturity | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
101 | Technical & Design | Interface risk | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
102 | Technical & Design | Performance shortfall | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
103 | Technical & Design | Equipment failure | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
104 | Technical & Design | Grid integration failure | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
105 | Technical & Design | Design errors | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
106 | Technical & Design | Technology immaturity | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
107 | Technical & Design | Interface risk | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
108 | Technical & Design | Performance shortfall | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
109 | Technical & Design | Equipment failure | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
110 | Technical & Design | Grid integration failure | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
111 | Technical & Design | Design errors | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
112 | Technical & Design | Technology immaturity | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
113 | Technical & Design | Interface risk | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
114 | Technical & Design | Performance shortfall | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
115 | Technical & Design | Equipment failure | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
116 | Technical & Design | Grid integration failure | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
117 | Construction & Execution | Schedule delay | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
118 | Construction & Execution | Productivity loss | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
119 | Construction & Execution | Labor shortage | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
120 | Construction & Execution | Supply chain disruption | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
121 | Construction & Execution | Subcontractor default | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
122 | Construction & Execution | Logistics failure | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
123 | Construction & Execution | Schedule delay | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
124 | Construction & Execution | Productivity loss | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
125 | Construction & Execution | Labor shortage | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
126 | Construction & Execution | Supply chain disruption | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
127 | Construction & Execution | Subcontractor default | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
128 | Construction & Execution | Logistics failure | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
129 | Construction & Execution | Schedule delay | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
130 | Construction & Execution | Productivity loss | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
131 | Construction & Execution | Labor shortage | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
132 | Construction & Execution | Supply chain disruption | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
133 | Construction & Execution | Subcontractor default | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
134 | Construction & Execution | Logistics failure | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
135 | Construction & Execution | Schedule delay | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
136 | Construction & Execution | Productivity loss | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
137 | Construction & Execution | Labor shortage | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
138 | Construction & Execution | Supply chain disruption | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
139 | Construction & Execution | Subcontractor default | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
140 | Construction & Execution | Logistics failure | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
141 | Environmental & Social | Environmental compliance | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
142 | Environmental & Social | Land acquisition dispute | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
143 | Environmental & Social | Community resistance | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
144 | Environmental & Social | Biodiversity impact | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
145 | Environmental & Social | Carbon regulation risk | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
146 | Environmental & Social | ESG non-compliance | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
147 | Environmental & Social | Environmental compliance | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
148 | Environmental & Social | Land acquisition dispute | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
149 | Environmental & Social | Community resistance | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
150 | Environmental & Social | Biodiversity impact | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
151 | Environmental & Social | Carbon regulation risk | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
152 | Environmental & Social | ESG non-compliance | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
153 | Environmental & Social | Environmental compliance | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
154 | Environmental & Social | Land acquisition dispute | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
155 | Environmental & Social | Community resistance | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
156 | Environmental & Social | Biodiversity impact | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
157 | Environmental & Social | Carbon regulation risk | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
158 | Environmental & Social | ESG non-compliance | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
159 | Environmental & Social | Environmental compliance | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
160 | Environmental & Social | Land acquisition dispute | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
161 | Environmental & Social | Community resistance | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
162 | Environmental & Social | Biodiversity impact | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
163 | Environmental & Social | Carbon regulation risk | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
164 | Environmental & Social | ESG non-compliance | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
165 | Energy-Specific | Resource variability | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
166 | Energy-Specific | Curtailment risk | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
167 | Energy-Specific | Fuel supply risk | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
168 | Energy-Specific | Storage system failure | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
169 | Energy-Specific | Decommissioning liability | Energy | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
170 | Energy-Specific | Resource variability | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
171 | Energy-Specific | Curtailment risk | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
172 | Energy-Specific | Fuel supply risk | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
173 | Energy-Specific | Storage system failure | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
174 | Energy-Specific | Decommissioning liability | EPC | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
175 | Energy-Specific | Resource variability | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
176 | Energy-Specific | Curtailment risk | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
177 | Energy-Specific | Fuel supply risk | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
178 | Energy-Specific | Storage system failure | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
179 | Energy-Specific | Decommissioning liability | Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014
180 | Energy-Specific | Resource variability | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Akintoye & MacLeod, Int. J. Project Management | 1997
181 | Energy-Specific | Curtailment risk | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Dikmen et al., Computers in Industry | 2025
182 | Energy-Specific | Fuel supply risk | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Zavadskas et al., Energy Policy | 2014
183 | Energy-Specific | Storage system failure | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | PMBOK Risk Management Guide | 2017
184 | Energy-Specific | Decommissioning liability | Non-Renewable | Infrastructure Project | EPC / EPCM / BOT | Medium–High | High | Probability–Impact / Monte Carlo / Fuzzy | Flyvbjerg, Oxford Handbook of Megaprojects | 2014