## Financial Inputs
Risk Quantification Inputs
Total Contract Value (EUR) | 100000000 | Editable project input
Low probability factor | 15% | Screening assumption
Medium probability factor | 40% | Screening assumption
High probability factor | 70% | Screening assumption
Default mitigation effectiveness | 35% | Editable expected reduction in EMV

## Financial Summary
Portfolio Risk Exposure Summary
Total Contract Value | 100000000
Sum of gross exposures | 5790000000
Sum of expected monetary values | 2916000000
Sum of residual expected exposures | 1895400000
Residual exposure / TCV | 1895%
Important aggregation warning | The simple sum assumes independent risks and can overstate portfolio exposure where risks overlap or are mutually exclusive. Use Monte Carlo or dependency modelling for contingency setting.

## Risk Library
Risk ID | Risk Statement | Risk Category | Project Type | Energy Segment | Geographic Context | Lifecycle Phase | Employer / Contractor / Shared allocation | Probability (L/M/H) | Impact (Cost / Time / Quality / HSE) | Mitigation Actions | Early Warning Indicators | Risk Owner | Gross Exposure (% TCV) | Gross Exposure (EUR) | Probability Factor | Expected Monetary Value (EUR) | Mitigation Effectiveness | Residual Exposure (EUR) | Residual Exposure (% TCV) | Quantification Basis | Source Basis
GER-0001 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that ambiguity or conflicting requirements, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Contractual | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0002 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that ambiguity or conflicting requirements, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Contractual | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0003 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that ambiguity or conflicting requirements, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Contractual | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0004 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that ambiguity or conflicting requirements, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Contractual | Grid Interconnection | Offshore Wind | North America | Procurement | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0005 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that ambiguity or conflicting requirements, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Contractual | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0006 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that ambiguity or conflicting requirements, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Contractual | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0007 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that ambiguity or conflicting requirements, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Contractual | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0008 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that ambiguity or conflicting requirements, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Contractual | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0009 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that ambiguity or conflicting requirements, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Contractual | EPC / Turnkey | Hydropower | Latin America | Construction | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0010 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that ambiguity or conflicting requirements, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Contractual | Installation | Nuclear Power | Global / Multi-country | Installation | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0011 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that ambiguity or conflicting requirements, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Contractual | R&D / Technology Development | Geothermal | Africa | Manufacturing | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0012 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that ambiguity or conflicting requirements, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Contractual | Brownfield Modification | LNG | East Asia | Construction | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0013 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that ambiguity or conflicting requirements, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Contractual | Owner’s Engineering | Onshore Wind | North America | Installation | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0014 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that ambiguity or conflicting requirements, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Contractual | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0015 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that ambiguity or conflicting requirements, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Contractual | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0016 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that ambiguity or conflicting requirements, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Contractual | Installation | Battery Energy Storage | South Asia | Installation | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0017 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that ambiguity or conflicting requirements, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Contractual | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0018 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that ambiguity or conflicting requirements, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Contractual | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0019 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that ambiguity or conflicting requirements, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Contractual | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0020 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that ambiguity or conflicting requirements, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Contractual | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0021 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that ambiguity or conflicting requirements, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Contractual | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0022 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that ambiguity or conflicting requirements, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Contractual | Decommissioning | Marine Energy | North America | Operations / Handover | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0023 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that ambiguity or conflicting requirements, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Contractual | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0024 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that ambiguity or conflicting requirements, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Contractual | Installation | LNG | Europe | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0025 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that ambiguity or conflicting requirements, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Contractual | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0026 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that ambiguity or conflicting requirements, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Contractual | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0027 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that ambiguity or conflicting requirements, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Contractual | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0028 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that ambiguity or conflicting requirements, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Contractual | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0029 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that ambiguity or conflicting requirements, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Contractual | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0030 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that ambiguity or conflicting requirements, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Contractual | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0031 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that ambiguity or conflicting requirements, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Contractual | Operations & Maintenance | District Energy | North America | Detailed Engineering | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0032 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that ambiguity or conflicting requirements, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Contractual | Grid Interconnection | Pumped Storage | Oceania | Procurement | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0033 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that ambiguity or conflicting requirements, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Contractual | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0034 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that ambiguity or conflicting requirements, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Contractual | Brownfield Modification | Marine Energy | Africa | Construction | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0035 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that ambiguity or conflicting requirements, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Contractual | Owner’s Engineering | Geothermal | East Asia | Installation | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0036 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that ambiguity or conflicting requirements, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Contractual | Decommissioning | Offshore Wind | Latin America | Manufacturing | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0037 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that ambiguity or conflicting requirements, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Contractual | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0038 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that ambiguity or conflicting requirements, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Contractual | Installation | Refining & Petrochemicals | Middle East | Installation | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0039 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that ambiguity or conflicting requirements, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Contractual | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0040 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that ambiguity or conflicting requirements, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Contractual | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0041 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that ambiguity or conflicting requirements, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Contractual | Owner’s Engineering | Hydropower | Oceania | Installation | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0042 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that ambiguity or conflicting requirements, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Contractual | EPCM | Nuclear Power | Europe | Pre-commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0043 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that ambiguity or conflicting requirements, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Contractual | Commissioning & Start-up | District Energy | Africa | Commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0044 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that ambiguity or conflicting requirements, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Contractual | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0045 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that ambiguity or conflicting requirements, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Contractual | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0046 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that ambiguity or conflicting requirements, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Contractual | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0047 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that ambiguity or conflicting requirements, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Contractual | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0048 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that ambiguity or conflicting requirements, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Contractual | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0049 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that ambiguity or conflicting requirements, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Contractual | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0050 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that ambiguity or conflicting requirements, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Contractual | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0051 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that ambiguity or conflicting requirements, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Contractual | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0052 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that ambiguity or conflicting requirements, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Contractual | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0053 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that ambiguity or conflicting requirements, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Contractual | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0054 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that ambiguity or conflicting requirements, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Contractual | Grid Interconnection | Nuclear Power | North America | Procurement | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0055 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that ambiguity or conflicting requirements, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Contractual | R&D / Technology Development | District Energy | Oceania | Manufacturing | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0056 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that ambiguity or conflicting requirements, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Contractual | EPCM | LNG | Middle East | Detailed Engineering | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0057 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that ambiguity or conflicting requirements, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Contractual | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0058 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that ambiguity or conflicting requirements, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Contractual | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0059 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that ambiguity or conflicting requirements, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Contractual | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0060 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that ambiguity or conflicting requirements, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Contractual | Installation | Offshore Wind | Global / Multi-country | Installation | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0061 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that ambiguity or conflicting requirements, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Contractual | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0062 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that ambiguity or conflicting requirements, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Contractual | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0063 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that ambiguity or conflicting requirements, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Contractual | Owner’s Engineering | Transmission & Substations | North America | Installation | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0064 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that ambiguity or conflicting requirements, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Contractual | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0065 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that ambiguity or conflicting requirements, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Contractual | Commissioning & Start-up | Hydropower | Europe | Commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0066 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that ambiguity or conflicting requirements, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Contractual | Installation | Marine Energy | South Asia | Installation | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0067 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that ambiguity or conflicting requirements, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Contractual | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0068 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that ambiguity or conflicting requirements, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Contractual | Grid Interconnection | LNG | Latin America | Commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0069 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that ambiguity or conflicting requirements, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Contractual | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0070 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that ambiguity or conflicting requirements, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Contractual | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0071 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that ambiguity or conflicting requirements, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Contractual | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0072 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that ambiguity or conflicting requirements, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Contractual | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0073 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that ambiguity or conflicting requirements, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Contractual | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0074 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that ambiguity or conflicting requirements, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Contractual | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0075 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that ambiguity or conflicting requirements, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Contractual | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0076 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that ambiguity or conflicting requirements, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Contractual | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0077 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that ambiguity or conflicting requirements, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Contractual | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0078 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that ambiguity or conflicting requirements, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Contractual | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0079 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that ambiguity or conflicting requirements, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Contractual | Commissioning & Start-up | Geothermal | Middle East | Procurement | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0080 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that ambiguity or conflicting requirements, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Contractual | Decommissioning | LNG | South Asia | Manufacturing | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0081 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that ambiguity or conflicting requirements, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Contractual | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0082 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that ambiguity or conflicting requirements, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Contractual | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0083 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that ambiguity or conflicting requirements, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Contractual | R&D / Technology Development | Solar PV | Europe | Manufacturing | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0084 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that ambiguity or conflicting requirements, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Contractual | Brownfield Modification | Battery Energy Storage | Africa | Construction | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0085 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that ambiguity or conflicting requirements, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Contractual | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0086 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that ambiguity or conflicting requirements, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Contractual | Decommissioning | Nuclear Power | Latin America | Manufacturing | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0087 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that ambiguity or conflicting requirements, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Contractual | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0088 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that ambiguity or conflicting requirements, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Contractual | Installation | Pumped Storage | Middle East | Installation | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0089 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that ambiguity or conflicting requirements, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Contractual | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0090 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that ambiguity or conflicting requirements, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Contractual | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0091 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that ambiguity or conflicting requirements, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Contractual | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0092 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that ambiguity or conflicting requirements, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Contractual | EPCM | Offshore Wind | Europe | Pre-commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0093 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that ambiguity or conflicting requirements, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Contractual | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0094 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that ambiguity or conflicting requirements, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Contractual | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0095 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that ambiguity or conflicting requirements, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Contractual | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0096 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that ambiguity or conflicting requirements, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Contractual | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Contract Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0097 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that ambiguity or conflicting requirements, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Contractual | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Contract Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0098 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that ambiguity or conflicting requirements, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Contractual | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Contract Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0099 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that ambiguity or conflicting requirements, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Contractual | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Contract Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0100 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that ambiguity or conflicting requirements, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Contractual | EPCM | Pumped Storage | Latin America | Detailed Engineering | Shared | M | Cost / Time | Establish controls for ambiguity or conflicting requirements; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Contract Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0101 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that critical-path slippage or late approvals, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Schedule | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0102 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that critical-path slippage or late approvals, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Schedule | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0103 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that critical-path slippage or late approvals, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Schedule | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0104 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that critical-path slippage or late approvals, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Schedule | Grid Interconnection | Offshore Wind | North America | Procurement | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0105 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that critical-path slippage or late approvals, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Schedule | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0106 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that critical-path slippage or late approvals, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Schedule | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0107 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that critical-path slippage or late approvals, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Schedule | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0108 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that critical-path slippage or late approvals, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Schedule | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0109 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that critical-path slippage or late approvals, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Schedule | EPC / Turnkey | Hydropower | Latin America | Construction | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0110 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that critical-path slippage or late approvals, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Schedule | Installation | Nuclear Power | Global / Multi-country | Installation | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0111 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that critical-path slippage or late approvals, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Schedule | R&D / Technology Development | Geothermal | Africa | Manufacturing | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0112 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that critical-path slippage or late approvals, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Schedule | Brownfield Modification | LNG | East Asia | Construction | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0113 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that critical-path slippage or late approvals, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Schedule | Owner’s Engineering | Onshore Wind | North America | Installation | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0114 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that critical-path slippage or late approvals, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Schedule | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0115 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that critical-path slippage or late approvals, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Schedule | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0116 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that critical-path slippage or late approvals, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Schedule | Installation | Battery Energy Storage | South Asia | Installation | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0117 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that critical-path slippage or late approvals, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Schedule | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0118 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that critical-path slippage or late approvals, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Schedule | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0119 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that critical-path slippage or late approvals, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Schedule | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0120 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that critical-path slippage or late approvals, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Schedule | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0121 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that critical-path slippage or late approvals, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Schedule | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0122 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that critical-path slippage or late approvals, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Schedule | Decommissioning | Marine Energy | North America | Operations / Handover | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0123 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that critical-path slippage or late approvals, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Schedule | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0124 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that critical-path slippage or late approvals, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Schedule | Installation | LNG | Europe | FEED / Basic Design | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0125 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that critical-path slippage or late approvals, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Schedule | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0126 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that critical-path slippage or late approvals, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Schedule | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0127 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that critical-path slippage or late approvals, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Schedule | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0128 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that critical-path slippage or late approvals, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Schedule | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0129 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that critical-path slippage or late approvals, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Schedule | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0130 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that critical-path slippage or late approvals, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Schedule | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0131 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that critical-path slippage or late approvals, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Schedule | Operations & Maintenance | District Energy | North America | Detailed Engineering | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0132 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that critical-path slippage or late approvals, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Schedule | Grid Interconnection | Pumped Storage | Oceania | Procurement | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0133 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that critical-path slippage or late approvals, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Schedule | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0134 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that critical-path slippage or late approvals, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Schedule | Brownfield Modification | Marine Energy | Africa | Construction | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0135 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that critical-path slippage or late approvals, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Schedule | Owner’s Engineering | Geothermal | East Asia | Installation | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0136 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that critical-path slippage or late approvals, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Schedule | Decommissioning | Offshore Wind | Latin America | Manufacturing | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0137 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that critical-path slippage or late approvals, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Schedule | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0138 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that critical-path slippage or late approvals, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Schedule | Installation | Refining & Petrochemicals | Middle East | Installation | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0139 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that critical-path slippage or late approvals, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Schedule | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0140 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that critical-path slippage or late approvals, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Schedule | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0141 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that critical-path slippage or late approvals, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Schedule | Owner’s Engineering | Hydropower | Oceania | Installation | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0142 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that critical-path slippage or late approvals, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Schedule | EPCM | Nuclear Power | Europe | Pre-commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0143 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that critical-path slippage or late approvals, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Schedule | Commissioning & Start-up | District Energy | Africa | Commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0144 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that critical-path slippage or late approvals, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Schedule | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0145 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that critical-path slippage or late approvals, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Schedule | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0146 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that critical-path slippage or late approvals, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Schedule | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0147 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that critical-path slippage or late approvals, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Schedule | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0148 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that critical-path slippage or late approvals, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Schedule | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0149 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that critical-path slippage or late approvals, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Schedule | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0150 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that critical-path slippage or late approvals, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Schedule | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0151 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that critical-path slippage or late approvals, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Schedule | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0152 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that critical-path slippage or late approvals, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Schedule | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0153 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that critical-path slippage or late approvals, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Schedule | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0154 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that critical-path slippage or late approvals, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Schedule | Grid Interconnection | Nuclear Power | North America | Procurement | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0155 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that critical-path slippage or late approvals, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Schedule | R&D / Technology Development | District Energy | Oceania | Manufacturing | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0156 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that critical-path slippage or late approvals, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Schedule | EPCM | LNG | Middle East | Detailed Engineering | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0157 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that critical-path slippage or late approvals, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Schedule | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0158 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that critical-path slippage or late approvals, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Schedule | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0159 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that critical-path slippage or late approvals, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Schedule | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0160 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that critical-path slippage or late approvals, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Schedule | Installation | Offshore Wind | Global / Multi-country | Installation | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0161 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that critical-path slippage or late approvals, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Schedule | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0162 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that critical-path slippage or late approvals, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Schedule | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0163 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that critical-path slippage or late approvals, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Schedule | Owner’s Engineering | Transmission & Substations | North America | Installation | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0164 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that critical-path slippage or late approvals, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Schedule | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0165 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that critical-path slippage or late approvals, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Schedule | Commissioning & Start-up | Hydropower | Europe | Commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0166 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that critical-path slippage or late approvals, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Schedule | Installation | Marine Energy | South Asia | Installation | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0167 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that critical-path slippage or late approvals, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Schedule | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0168 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that critical-path slippage or late approvals, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Schedule | Grid Interconnection | LNG | Latin America | Commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0169 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that critical-path slippage or late approvals, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Schedule | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0170 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that critical-path slippage or late approvals, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Schedule | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0171 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that critical-path slippage or late approvals, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Schedule | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0172 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that critical-path slippage or late approvals, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Schedule | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0173 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that critical-path slippage or late approvals, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Schedule | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0174 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that critical-path slippage or late approvals, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Schedule | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0175 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that critical-path slippage or late approvals, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Schedule | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0176 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that critical-path slippage or late approvals, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Schedule | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0177 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that critical-path slippage or late approvals, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Schedule | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0178 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that critical-path slippage or late approvals, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Schedule | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0179 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that critical-path slippage or late approvals, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Schedule | Commissioning & Start-up | Geothermal | Middle East | Procurement | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0180 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that critical-path slippage or late approvals, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Schedule | Decommissioning | LNG | South Asia | Manufacturing | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0181 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that critical-path slippage or late approvals, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Schedule | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0182 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that critical-path slippage or late approvals, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Schedule | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0183 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that critical-path slippage or late approvals, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Schedule | R&D / Technology Development | Solar PV | Europe | Manufacturing | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0184 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that critical-path slippage or late approvals, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Schedule | Brownfield Modification | Battery Energy Storage | Africa | Construction | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0185 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that critical-path slippage or late approvals, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Schedule | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0186 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that critical-path slippage or late approvals, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Schedule | Decommissioning | Nuclear Power | Latin America | Manufacturing | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0187 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that critical-path slippage or late approvals, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Schedule | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0188 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that critical-path slippage or late approvals, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Schedule | Installation | Pumped Storage | Middle East | Installation | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0189 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that critical-path slippage or late approvals, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Schedule | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0190 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that critical-path slippage or late approvals, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Schedule | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0191 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that critical-path slippage or late approvals, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Schedule | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0192 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that critical-path slippage or late approvals, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Schedule | EPCM | Offshore Wind | Europe | Pre-commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0193 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that critical-path slippage or late approvals, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Schedule | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0194 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that critical-path slippage or late approvals, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Schedule | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0195 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that critical-path slippage or late approvals, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Schedule | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0196 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that critical-path slippage or late approvals, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Schedule | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Controls Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0197 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that critical-path slippage or late approvals, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Schedule | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Controls Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0198 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that critical-path slippage or late approvals, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Schedule | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Controls Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0199 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that critical-path slippage or late approvals, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Schedule | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Controls Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0200 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that critical-path slippage or late approvals, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Schedule | EPCM | Pumped Storage | Latin America | Detailed Engineering | Contractor | H | Time / Cost | Establish controls for critical-path slippage or late approvals; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Controls Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0201 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that estimate omissions, escalation or quantity growth, combined with insufficient planning, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0202 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that estimate omissions, escalation or quantity growth, combined with insufficient planning, may adversely affect project objectives through cost consequences. | Cost & Estimating | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0203 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that estimate omissions, escalation or quantity growth, combined with insufficient planning, may adversely affect project objectives through cost consequences. | Cost & Estimating | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0204 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that estimate omissions, escalation or quantity growth, combined with insufficient planning, may adversely affect project objectives through cost consequences. | Cost & Estimating | Grid Interconnection | Offshore Wind | North America | Procurement | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0205 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that estimate omissions, escalation or quantity growth, combined with insufficient planning, may adversely affect project objectives through cost consequences. | Cost & Estimating | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0206 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that estimate omissions, escalation or quantity growth, combined with incomplete information, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0207 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that estimate omissions, escalation or quantity growth, combined with incomplete information, may adversely affect project objectives through cost consequences. | Cost & Estimating | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0208 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that estimate omissions, escalation or quantity growth, combined with incomplete information, may adversely affect project objectives through cost consequences. | Cost & Estimating | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0209 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that estimate omissions, escalation or quantity growth, combined with incomplete information, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPC / Turnkey | Hydropower | Latin America | Construction | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0210 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that estimate omissions, escalation or quantity growth, combined with incomplete information, may adversely affect project objectives through cost consequences. | Cost & Estimating | Installation | Nuclear Power | Global / Multi-country | Installation | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0211 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that estimate omissions, escalation or quantity growth, combined with late decision-making, may adversely affect project objectives through cost consequences. | Cost & Estimating | R&D / Technology Development | Geothermal | Africa | Manufacturing | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0212 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that estimate omissions, escalation or quantity growth, combined with late decision-making, may adversely affect project objectives through cost consequences. | Cost & Estimating | Brownfield Modification | LNG | East Asia | Construction | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0213 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that estimate omissions, escalation or quantity growth, combined with late decision-making, may adversely affect project objectives through cost consequences. | Cost & Estimating | Owner’s Engineering | Onshore Wind | North America | Installation | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0214 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that estimate omissions, escalation or quantity growth, combined with late decision-making, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0215 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that estimate omissions, escalation or quantity growth, combined with late decision-making, may adversely affect project objectives through cost consequences. | Cost & Estimating | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0216 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that estimate omissions, escalation or quantity growth, combined with weak controls, may adversely affect project objectives through cost consequences. | Cost & Estimating | Installation | Battery Energy Storage | South Asia | Installation | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0217 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that estimate omissions, escalation or quantity growth, combined with weak controls, may adversely affect project objectives through cost consequences. | Cost & Estimating | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0218 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that estimate omissions, escalation or quantity growth, combined with weak controls, may adversely affect project objectives through cost consequences. | Cost & Estimating | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0219 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that estimate omissions, escalation or quantity growth, combined with weak controls, may adversely affect project objectives through cost consequences. | Cost & Estimating | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0220 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that estimate omissions, escalation or quantity growth, combined with weak controls, may adversely affect project objectives through cost consequences. | Cost & Estimating | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0221 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that estimate omissions, escalation or quantity growth, combined with resource constraints, may adversely affect project objectives through cost consequences. | Cost & Estimating | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0222 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that estimate omissions, escalation or quantity growth, combined with resource constraints, may adversely affect project objectives through cost consequences. | Cost & Estimating | Decommissioning | Marine Energy | North America | Operations / Handover | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0223 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that estimate omissions, escalation or quantity growth, combined with resource constraints, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0224 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that estimate omissions, escalation or quantity growth, combined with resource constraints, may adversely affect project objectives through cost consequences. | Cost & Estimating | Installation | LNG | Europe | FEED / Basic Design | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0225 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that estimate omissions, escalation or quantity growth, combined with resource constraints, may adversely affect project objectives through cost consequences. | Cost & Estimating | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0226 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that estimate omissions, escalation or quantity growth, combined with supplier dependency, may adversely affect project objectives through cost consequences. | Cost & Estimating | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0227 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that estimate omissions, escalation or quantity growth, combined with supplier dependency, may adversely affect project objectives through cost consequences. | Cost & Estimating | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0228 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that estimate omissions, escalation or quantity growth, combined with supplier dependency, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0229 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that estimate omissions, escalation or quantity growth, combined with supplier dependency, may adversely affect project objectives through cost consequences. | Cost & Estimating | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0230 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that estimate omissions, escalation or quantity growth, combined with supplier dependency, may adversely affect project objectives through cost consequences. | Cost & Estimating | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0231 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that estimate omissions, escalation or quantity growth, combined with interface complexity, may adversely affect project objectives through cost consequences. | Cost & Estimating | Operations & Maintenance | District Energy | North America | Detailed Engineering | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0232 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that estimate omissions, escalation or quantity growth, combined with interface complexity, may adversely affect project objectives through cost consequences. | Cost & Estimating | Grid Interconnection | Pumped Storage | Oceania | Procurement | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0233 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that estimate omissions, escalation or quantity growth, combined with interface complexity, may adversely affect project objectives through cost consequences. | Cost & Estimating | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0234 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that estimate omissions, escalation or quantity growth, combined with interface complexity, may adversely affect project objectives through cost consequences. | Cost & Estimating | Brownfield Modification | Marine Energy | Africa | Construction | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0235 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that estimate omissions, escalation or quantity growth, combined with interface complexity, may adversely affect project objectives through cost consequences. | Cost & Estimating | Owner’s Engineering | Geothermal | East Asia | Installation | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0236 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that estimate omissions, escalation or quantity growth, combined with requirements volatility, may adversely affect project objectives through cost consequences. | Cost & Estimating | Decommissioning | Offshore Wind | Latin America | Manufacturing | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0237 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that estimate omissions, escalation or quantity growth, combined with requirements volatility, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0238 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that estimate omissions, escalation or quantity growth, combined with requirements volatility, may adversely affect project objectives through cost consequences. | Cost & Estimating | Installation | Refining & Petrochemicals | Middle East | Installation | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0239 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that estimate omissions, escalation or quantity growth, combined with requirements volatility, may adversely affect project objectives through cost consequences. | Cost & Estimating | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0240 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that estimate omissions, escalation or quantity growth, combined with requirements volatility, may adversely affect project objectives through cost consequences. | Cost & Estimating | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0241 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that estimate omissions, escalation or quantity growth, combined with regulatory uncertainty, may adversely affect project objectives through cost consequences. | Cost & Estimating | Owner’s Engineering | Hydropower | Oceania | Installation | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0242 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that estimate omissions, escalation or quantity growth, combined with regulatory uncertainty, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPCM | Nuclear Power | Europe | Pre-commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0243 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that estimate omissions, escalation or quantity growth, combined with regulatory uncertainty, may adversely affect project objectives through cost consequences. | Cost & Estimating | Commissioning & Start-up | District Energy | Africa | Commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0244 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that estimate omissions, escalation or quantity growth, combined with regulatory uncertainty, may adversely affect project objectives through cost consequences. | Cost & Estimating | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0245 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that estimate omissions, escalation or quantity growth, combined with regulatory uncertainty, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0246 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that estimate omissions, escalation or quantity growth, combined with inadequate verification, may adversely affect project objectives through cost consequences. | Cost & Estimating | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0247 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that estimate omissions, escalation or quantity growth, combined with inadequate verification, may adversely affect project objectives through cost consequences. | Cost & Estimating | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0248 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that estimate omissions, escalation or quantity growth, combined with inadequate verification, may adversely affect project objectives through cost consequences. | Cost & Estimating | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0249 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that estimate omissions, escalation or quantity growth, combined with inadequate verification, may adversely affect project objectives through cost consequences. | Cost & Estimating | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0250 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that estimate omissions, escalation or quantity growth, combined with inadequate verification, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0251 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that estimate omissions, escalation or quantity growth, combined with poor communication, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0252 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that estimate omissions, escalation or quantity growth, combined with poor communication, may adversely affect project objectives through cost consequences. | Cost & Estimating | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0253 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that estimate omissions, escalation or quantity growth, combined with poor communication, may adversely affect project objectives through cost consequences. | Cost & Estimating | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0254 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that estimate omissions, escalation or quantity growth, combined with poor communication, may adversely affect project objectives through cost consequences. | Cost & Estimating | Grid Interconnection | Nuclear Power | North America | Procurement | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0255 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that estimate omissions, escalation or quantity growth, combined with poor communication, may adversely affect project objectives through cost consequences. | Cost & Estimating | R&D / Technology Development | District Energy | Oceania | Manufacturing | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0256 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that estimate omissions, escalation or quantity growth, combined with incorrect assumptions, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPCM | LNG | Middle East | Detailed Engineering | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0257 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that estimate omissions, escalation or quantity growth, combined with incorrect assumptions, may adversely affect project objectives through cost consequences. | Cost & Estimating | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0258 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that estimate omissions, escalation or quantity growth, combined with incorrect assumptions, may adversely affect project objectives through cost consequences. | Cost & Estimating | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0259 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that estimate omissions, escalation or quantity growth, combined with incorrect assumptions, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0260 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that estimate omissions, escalation or quantity growth, combined with incorrect assumptions, may adversely affect project objectives through cost consequences. | Cost & Estimating | Installation | Offshore Wind | Global / Multi-country | Installation | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0261 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that estimate omissions, escalation or quantity growth, combined with low technical maturity, may adversely affect project objectives through cost consequences. | Cost & Estimating | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0262 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that estimate omissions, escalation or quantity growth, combined with low technical maturity, may adversely affect project objectives through cost consequences. | Cost & Estimating | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0263 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that estimate omissions, escalation or quantity growth, combined with low technical maturity, may adversely affect project objectives through cost consequences. | Cost & Estimating | Owner’s Engineering | Transmission & Substations | North America | Installation | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0264 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that estimate omissions, escalation or quantity growth, combined with low technical maturity, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0265 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that estimate omissions, escalation or quantity growth, combined with low technical maturity, may adversely affect project objectives through cost consequences. | Cost & Estimating | Commissioning & Start-up | Hydropower | Europe | Commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0266 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that estimate omissions, escalation or quantity growth, combined with documentation gaps, may adversely affect project objectives through cost consequences. | Cost & Estimating | Installation | Marine Energy | South Asia | Installation | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0267 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that estimate omissions, escalation or quantity growth, combined with documentation gaps, may adversely affect project objectives through cost consequences. | Cost & Estimating | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0268 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that estimate omissions, escalation or quantity growth, combined with documentation gaps, may adversely affect project objectives through cost consequences. | Cost & Estimating | Grid Interconnection | LNG | Latin America | Commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0269 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that estimate omissions, escalation or quantity growth, combined with documentation gaps, may adversely affect project objectives through cost consequences. | Cost & Estimating | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0270 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that estimate omissions, escalation or quantity growth, combined with documentation gaps, may adversely affect project objectives through cost consequences. | Cost & Estimating | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0271 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that estimate omissions, escalation or quantity growth, combined with external disruption, may adversely affect project objectives through cost consequences. | Cost & Estimating | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0272 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that estimate omissions, escalation or quantity growth, combined with external disruption, may adversely affect project objectives through cost consequences. | Cost & Estimating | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0273 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that estimate omissions, escalation or quantity growth, combined with external disruption, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0274 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that estimate omissions, escalation or quantity growth, combined with external disruption, may adversely affect project objectives through cost consequences. | Cost & Estimating | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0275 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that estimate omissions, escalation or quantity growth, combined with external disruption, may adversely affect project objectives through cost consequences. | Cost & Estimating | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0276 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that estimate omissions, escalation or quantity growth, combined with governance delay, may adversely affect project objectives through cost consequences. | Cost & Estimating | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0277 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that estimate omissions, escalation or quantity growth, combined with governance delay, may adversely affect project objectives through cost consequences. | Cost & Estimating | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0278 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that estimate omissions, escalation or quantity growth, combined with governance delay, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0279 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that estimate omissions, escalation or quantity growth, combined with governance delay, may adversely affect project objectives through cost consequences. | Cost & Estimating | Commissioning & Start-up | Geothermal | Middle East | Procurement | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0280 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that estimate omissions, escalation or quantity growth, combined with governance delay, may adversely affect project objectives through cost consequences. | Cost & Estimating | Decommissioning | LNG | South Asia | Manufacturing | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0281 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that estimate omissions, escalation or quantity growth, combined with commercial misalignment, may adversely affect project objectives through cost consequences. | Cost & Estimating | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0282 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that estimate omissions, escalation or quantity growth, combined with commercial misalignment, may adversely affect project objectives through cost consequences. | Cost & Estimating | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0283 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that estimate omissions, escalation or quantity growth, combined with commercial misalignment, may adversely affect project objectives through cost consequences. | Cost & Estimating | R&D / Technology Development | Solar PV | Europe | Manufacturing | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0284 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that estimate omissions, escalation or quantity growth, combined with commercial misalignment, may adversely affect project objectives through cost consequences. | Cost & Estimating | Brownfield Modification | Battery Energy Storage | Africa | Construction | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0285 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that estimate omissions, escalation or quantity growth, combined with commercial misalignment, may adversely affect project objectives through cost consequences. | Cost & Estimating | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0286 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that estimate omissions, escalation or quantity growth, combined with quality escape, may adversely affect project objectives through cost consequences. | Cost & Estimating | Decommissioning | Nuclear Power | Latin America | Manufacturing | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0287 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that estimate omissions, escalation or quantity growth, combined with quality escape, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0288 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that estimate omissions, escalation or quantity growth, combined with quality escape, may adversely affect project objectives through cost consequences. | Cost & Estimating | Installation | Pumped Storage | Middle East | Installation | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0289 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that estimate omissions, escalation or quantity growth, combined with quality escape, may adversely affect project objectives through cost consequences. | Cost & Estimating | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0290 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that estimate omissions, escalation or quantity growth, combined with quality escape, may adversely affect project objectives through cost consequences. | Cost & Estimating | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0291 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that estimate omissions, escalation or quantity growth, combined with access constraint, may adversely affect project objectives through cost consequences. | Cost & Estimating | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0292 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that estimate omissions, escalation or quantity growth, combined with access constraint, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPCM | Offshore Wind | Europe | Pre-commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0293 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that estimate omissions, escalation or quantity growth, combined with access constraint, may adversely affect project objectives through cost consequences. | Cost & Estimating | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0294 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that estimate omissions, escalation or quantity growth, combined with access constraint, may adversely affect project objectives through cost consequences. | Cost & Estimating | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0295 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that estimate omissions, escalation or quantity growth, combined with access constraint, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0296 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that estimate omissions, escalation or quantity growth, combined with performance variability, may adversely affect project objectives through cost consequences. | Cost & Estimating | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0297 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that estimate omissions, escalation or quantity growth, combined with performance variability, may adversely affect project objectives through cost consequences. | Cost & Estimating | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0298 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that estimate omissions, escalation or quantity growth, combined with performance variability, may adversely affect project objectives through cost consequences. | Cost & Estimating | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0299 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that estimate omissions, escalation or quantity growth, combined with performance variability, may adversely affect project objectives through cost consequences. | Cost & Estimating | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0300 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that estimate omissions, escalation or quantity growth, combined with performance variability, may adversely affect project objectives through cost consequences. | Cost & Estimating | EPCM | Pumped Storage | Latin America | Detailed Engineering | Contractor | H | Cost | Establish controls for estimate omissions, escalation or quantity growth; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0301 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that design error, immaturity or interface mismatch, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0302 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that design error, immaturity or interface mismatch, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0303 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that design error, immaturity or interface mismatch, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0304 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that design error, immaturity or interface mismatch, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Grid Interconnection | Offshore Wind | North America | Procurement | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0305 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that design error, immaturity or interface mismatch, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0306 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that design error, immaturity or interface mismatch, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0307 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that design error, immaturity or interface mismatch, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0308 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that design error, immaturity or interface mismatch, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0309 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that design error, immaturity or interface mismatch, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPC / Turnkey | Hydropower | Latin America | Construction | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0310 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that design error, immaturity or interface mismatch, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Installation | Nuclear Power | Global / Multi-country | Installation | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0311 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that design error, immaturity or interface mismatch, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | R&D / Technology Development | Geothermal | Africa | Manufacturing | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0312 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that design error, immaturity or interface mismatch, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Brownfield Modification | LNG | East Asia | Construction | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0313 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that design error, immaturity or interface mismatch, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Owner’s Engineering | Onshore Wind | North America | Installation | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0314 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that design error, immaturity or interface mismatch, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0315 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that design error, immaturity or interface mismatch, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0316 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that design error, immaturity or interface mismatch, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Installation | Battery Energy Storage | South Asia | Installation | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0317 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that design error, immaturity or interface mismatch, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0318 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that design error, immaturity or interface mismatch, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0319 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that design error, immaturity or interface mismatch, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0320 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that design error, immaturity or interface mismatch, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0321 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that design error, immaturity or interface mismatch, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0322 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that design error, immaturity or interface mismatch, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Decommissioning | Marine Energy | North America | Operations / Handover | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0323 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that design error, immaturity or interface mismatch, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0324 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that design error, immaturity or interface mismatch, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Installation | LNG | Europe | FEED / Basic Design | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0325 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that design error, immaturity or interface mismatch, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0326 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that design error, immaturity or interface mismatch, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0327 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that design error, immaturity or interface mismatch, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0328 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that design error, immaturity or interface mismatch, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0329 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that design error, immaturity or interface mismatch, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0330 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that design error, immaturity or interface mismatch, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0331 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that design error, immaturity or interface mismatch, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Operations & Maintenance | District Energy | North America | Detailed Engineering | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0332 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that design error, immaturity or interface mismatch, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Grid Interconnection | Pumped Storage | Oceania | Procurement | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0333 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that design error, immaturity or interface mismatch, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0334 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that design error, immaturity or interface mismatch, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Brownfield Modification | Marine Energy | Africa | Construction | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0335 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that design error, immaturity or interface mismatch, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Owner’s Engineering | Geothermal | East Asia | Installation | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0336 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that design error, immaturity or interface mismatch, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Decommissioning | Offshore Wind | Latin America | Manufacturing | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0337 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that design error, immaturity or interface mismatch, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0338 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that design error, immaturity or interface mismatch, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Installation | Refining & Petrochemicals | Middle East | Installation | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0339 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that design error, immaturity or interface mismatch, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0340 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that design error, immaturity or interface mismatch, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0341 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that design error, immaturity or interface mismatch, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Owner’s Engineering | Hydropower | Oceania | Installation | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0342 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that design error, immaturity or interface mismatch, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPCM | Nuclear Power | Europe | Pre-commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0343 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that design error, immaturity or interface mismatch, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Commissioning & Start-up | District Energy | Africa | Commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0344 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that design error, immaturity or interface mismatch, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0345 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that design error, immaturity or interface mismatch, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0346 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that design error, immaturity or interface mismatch, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0347 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that design error, immaturity or interface mismatch, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0348 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that design error, immaturity or interface mismatch, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0349 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that design error, immaturity or interface mismatch, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0350 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that design error, immaturity or interface mismatch, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0351 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that design error, immaturity or interface mismatch, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0352 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that design error, immaturity or interface mismatch, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0353 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that design error, immaturity or interface mismatch, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0354 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that design error, immaturity or interface mismatch, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Grid Interconnection | Nuclear Power | North America | Procurement | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0355 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that design error, immaturity or interface mismatch, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | R&D / Technology Development | District Energy | Oceania | Manufacturing | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0356 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that design error, immaturity or interface mismatch, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPCM | LNG | Middle East | Detailed Engineering | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0357 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that design error, immaturity or interface mismatch, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0358 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that design error, immaturity or interface mismatch, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0359 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that design error, immaturity or interface mismatch, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0360 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that design error, immaturity or interface mismatch, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Installation | Offshore Wind | Global / Multi-country | Installation | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0361 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that design error, immaturity or interface mismatch, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0362 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that design error, immaturity or interface mismatch, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0363 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that design error, immaturity or interface mismatch, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Owner’s Engineering | Transmission & Substations | North America | Installation | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0364 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that design error, immaturity or interface mismatch, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0365 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that design error, immaturity or interface mismatch, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Commissioning & Start-up | Hydropower | Europe | Commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0366 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that design error, immaturity or interface mismatch, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Installation | Marine Energy | South Asia | Installation | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0367 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that design error, immaturity or interface mismatch, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0368 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that design error, immaturity or interface mismatch, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Grid Interconnection | LNG | Latin America | Commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0369 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that design error, immaturity or interface mismatch, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0370 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that design error, immaturity or interface mismatch, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0371 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that design error, immaturity or interface mismatch, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0372 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that design error, immaturity or interface mismatch, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0373 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that design error, immaturity or interface mismatch, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0374 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that design error, immaturity or interface mismatch, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0375 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that design error, immaturity or interface mismatch, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0376 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that design error, immaturity or interface mismatch, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0377 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that design error, immaturity or interface mismatch, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0378 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that design error, immaturity or interface mismatch, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0379 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that design error, immaturity or interface mismatch, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Commissioning & Start-up | Geothermal | Middle East | Procurement | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0380 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that design error, immaturity or interface mismatch, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Decommissioning | LNG | South Asia | Manufacturing | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0381 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that design error, immaturity or interface mismatch, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0382 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that design error, immaturity or interface mismatch, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0383 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that design error, immaturity or interface mismatch, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | R&D / Technology Development | Solar PV | Europe | Manufacturing | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0384 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that design error, immaturity or interface mismatch, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Brownfield Modification | Battery Energy Storage | Africa | Construction | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0385 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that design error, immaturity or interface mismatch, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0386 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that design error, immaturity or interface mismatch, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Decommissioning | Nuclear Power | Latin America | Manufacturing | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0387 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that design error, immaturity or interface mismatch, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0388 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that design error, immaturity or interface mismatch, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Installation | Pumped Storage | Middle East | Installation | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0389 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that design error, immaturity or interface mismatch, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0390 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that design error, immaturity or interface mismatch, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0391 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that design error, immaturity or interface mismatch, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0392 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that design error, immaturity or interface mismatch, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPCM | Offshore Wind | Europe | Pre-commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0393 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that design error, immaturity or interface mismatch, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0394 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that design error, immaturity or interface mismatch, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0395 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that design error, immaturity or interface mismatch, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0396 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that design error, immaturity or interface mismatch, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Engineering Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0397 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that design error, immaturity or interface mismatch, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Engineering Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0398 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that design error, immaturity or interface mismatch, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Engineering Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0399 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that design error, immaturity or interface mismatch, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Engineering Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0400 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that design error, immaturity or interface mismatch, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Design & Engineering | EPCM | Pumped Storage | Latin America | Detailed Engineering | Contractor | H | Quality / Time / Cost | Establish controls for design error, immaturity or interface mismatch; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Engineering Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0401 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that nonconformance, defective material or weak traceability, combined with insufficient planning, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0402 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that nonconformance, defective material or weak traceability, combined with insufficient planning, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0403 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that nonconformance, defective material or weak traceability, combined with insufficient planning, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0404 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that nonconformance, defective material or weak traceability, combined with insufficient planning, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Grid Interconnection | Offshore Wind | North America | Procurement | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0405 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that nonconformance, defective material or weak traceability, combined with insufficient planning, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0406 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that nonconformance, defective material or weak traceability, combined with incomplete information, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0407 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that nonconformance, defective material or weak traceability, combined with incomplete information, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0408 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that nonconformance, defective material or weak traceability, combined with incomplete information, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0409 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that nonconformance, defective material or weak traceability, combined with incomplete information, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPC / Turnkey | Hydropower | Latin America | Construction | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0410 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that nonconformance, defective material or weak traceability, combined with incomplete information, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Installation | Nuclear Power | Global / Multi-country | Installation | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0411 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that nonconformance, defective material or weak traceability, combined with late decision-making, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | R&D / Technology Development | Geothermal | Africa | Manufacturing | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0412 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that nonconformance, defective material or weak traceability, combined with late decision-making, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Brownfield Modification | LNG | East Asia | Construction | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0413 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that nonconformance, defective material or weak traceability, combined with late decision-making, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Owner’s Engineering | Onshore Wind | North America | Installation | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0414 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that nonconformance, defective material or weak traceability, combined with late decision-making, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0415 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that nonconformance, defective material or weak traceability, combined with late decision-making, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0416 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that nonconformance, defective material or weak traceability, combined with weak controls, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Installation | Battery Energy Storage | South Asia | Installation | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0417 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that nonconformance, defective material or weak traceability, combined with weak controls, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0418 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that nonconformance, defective material or weak traceability, combined with weak controls, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0419 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that nonconformance, defective material or weak traceability, combined with weak controls, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0420 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that nonconformance, defective material or weak traceability, combined with weak controls, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0421 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that nonconformance, defective material or weak traceability, combined with resource constraints, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0422 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that nonconformance, defective material or weak traceability, combined with resource constraints, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Decommissioning | Marine Energy | North America | Operations / Handover | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0423 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that nonconformance, defective material or weak traceability, combined with resource constraints, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0424 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that nonconformance, defective material or weak traceability, combined with resource constraints, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Installation | LNG | Europe | FEED / Basic Design | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0425 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that nonconformance, defective material or weak traceability, combined with resource constraints, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0426 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that nonconformance, defective material or weak traceability, combined with supplier dependency, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0427 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that nonconformance, defective material or weak traceability, combined with supplier dependency, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0428 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that nonconformance, defective material or weak traceability, combined with supplier dependency, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0429 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that nonconformance, defective material or weak traceability, combined with supplier dependency, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0430 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that nonconformance, defective material or weak traceability, combined with supplier dependency, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0431 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that nonconformance, defective material or weak traceability, combined with interface complexity, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Operations & Maintenance | District Energy | North America | Detailed Engineering | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0432 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that nonconformance, defective material or weak traceability, combined with interface complexity, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Grid Interconnection | Pumped Storage | Oceania | Procurement | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0433 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that nonconformance, defective material or weak traceability, combined with interface complexity, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0434 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that nonconformance, defective material or weak traceability, combined with interface complexity, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Brownfield Modification | Marine Energy | Africa | Construction | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0435 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that nonconformance, defective material or weak traceability, combined with interface complexity, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Owner’s Engineering | Geothermal | East Asia | Installation | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0436 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that nonconformance, defective material or weak traceability, combined with requirements volatility, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Decommissioning | Offshore Wind | Latin America | Manufacturing | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0437 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that nonconformance, defective material or weak traceability, combined with requirements volatility, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0438 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that nonconformance, defective material or weak traceability, combined with requirements volatility, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Installation | Refining & Petrochemicals | Middle East | Installation | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0439 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that nonconformance, defective material or weak traceability, combined with requirements volatility, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0440 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that nonconformance, defective material or weak traceability, combined with requirements volatility, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0441 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that nonconformance, defective material or weak traceability, combined with regulatory uncertainty, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Owner’s Engineering | Hydropower | Oceania | Installation | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0442 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that nonconformance, defective material or weak traceability, combined with regulatory uncertainty, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPCM | Nuclear Power | Europe | Pre-commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0443 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that nonconformance, defective material or weak traceability, combined with regulatory uncertainty, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Commissioning & Start-up | District Energy | Africa | Commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0444 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that nonconformance, defective material or weak traceability, combined with regulatory uncertainty, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0445 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that nonconformance, defective material or weak traceability, combined with regulatory uncertainty, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0446 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that nonconformance, defective material or weak traceability, combined with inadequate verification, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0447 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that nonconformance, defective material or weak traceability, combined with inadequate verification, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0448 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that nonconformance, defective material or weak traceability, combined with inadequate verification, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0449 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that nonconformance, defective material or weak traceability, combined with inadequate verification, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0450 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that nonconformance, defective material or weak traceability, combined with inadequate verification, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0451 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that nonconformance, defective material or weak traceability, combined with poor communication, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0452 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that nonconformance, defective material or weak traceability, combined with poor communication, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0453 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that nonconformance, defective material or weak traceability, combined with poor communication, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0454 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that nonconformance, defective material or weak traceability, combined with poor communication, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Grid Interconnection | Nuclear Power | North America | Procurement | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0455 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that nonconformance, defective material or weak traceability, combined with poor communication, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | R&D / Technology Development | District Energy | Oceania | Manufacturing | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0456 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that nonconformance, defective material or weak traceability, combined with incorrect assumptions, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPCM | LNG | Middle East | Detailed Engineering | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0457 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that nonconformance, defective material or weak traceability, combined with incorrect assumptions, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0458 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that nonconformance, defective material or weak traceability, combined with incorrect assumptions, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0459 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that nonconformance, defective material or weak traceability, combined with incorrect assumptions, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0460 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that nonconformance, defective material or weak traceability, combined with incorrect assumptions, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Installation | Offshore Wind | Global / Multi-country | Installation | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0461 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that nonconformance, defective material or weak traceability, combined with low technical maturity, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0462 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that nonconformance, defective material or weak traceability, combined with low technical maturity, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0463 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that nonconformance, defective material or weak traceability, combined with low technical maturity, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Owner’s Engineering | Transmission & Substations | North America | Installation | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0464 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that nonconformance, defective material or weak traceability, combined with low technical maturity, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0465 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that nonconformance, defective material or weak traceability, combined with low technical maturity, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Commissioning & Start-up | Hydropower | Europe | Commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0466 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that nonconformance, defective material or weak traceability, combined with documentation gaps, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Installation | Marine Energy | South Asia | Installation | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0467 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that nonconformance, defective material or weak traceability, combined with documentation gaps, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0468 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that nonconformance, defective material or weak traceability, combined with documentation gaps, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Grid Interconnection | LNG | Latin America | Commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0469 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that nonconformance, defective material or weak traceability, combined with documentation gaps, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0470 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that nonconformance, defective material or weak traceability, combined with documentation gaps, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0471 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that nonconformance, defective material or weak traceability, combined with external disruption, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0472 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that nonconformance, defective material or weak traceability, combined with external disruption, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0473 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that nonconformance, defective material or weak traceability, combined with external disruption, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0474 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that nonconformance, defective material or weak traceability, combined with external disruption, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0475 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that nonconformance, defective material or weak traceability, combined with external disruption, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0476 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that nonconformance, defective material or weak traceability, combined with governance delay, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0477 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that nonconformance, defective material or weak traceability, combined with governance delay, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0478 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that nonconformance, defective material or weak traceability, combined with governance delay, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0479 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that nonconformance, defective material or weak traceability, combined with governance delay, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Commissioning & Start-up | Geothermal | Middle East | Procurement | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0480 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that nonconformance, defective material or weak traceability, combined with governance delay, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Decommissioning | LNG | South Asia | Manufacturing | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0481 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that nonconformance, defective material or weak traceability, combined with commercial misalignment, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0482 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that nonconformance, defective material or weak traceability, combined with commercial misalignment, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0483 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that nonconformance, defective material or weak traceability, combined with commercial misalignment, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | R&D / Technology Development | Solar PV | Europe | Manufacturing | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0484 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that nonconformance, defective material or weak traceability, combined with commercial misalignment, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Brownfield Modification | Battery Energy Storage | Africa | Construction | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0485 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that nonconformance, defective material or weak traceability, combined with commercial misalignment, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0486 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that nonconformance, defective material or weak traceability, combined with quality escape, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Decommissioning | Nuclear Power | Latin America | Manufacturing | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0487 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that nonconformance, defective material or weak traceability, combined with quality escape, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0488 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that nonconformance, defective material or weak traceability, combined with quality escape, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Installation | Pumped Storage | Middle East | Installation | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0489 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that nonconformance, defective material or weak traceability, combined with quality escape, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0490 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that nonconformance, defective material or weak traceability, combined with quality escape, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0491 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that nonconformance, defective material or weak traceability, combined with access constraint, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0492 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that nonconformance, defective material or weak traceability, combined with access constraint, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPCM | Offshore Wind | Europe | Pre-commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0493 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that nonconformance, defective material or weak traceability, combined with access constraint, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0494 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that nonconformance, defective material or weak traceability, combined with access constraint, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0495 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that nonconformance, defective material or weak traceability, combined with access constraint, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0496 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that nonconformance, defective material or weak traceability, combined with performance variability, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Quality Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0497 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that nonconformance, defective material or weak traceability, combined with performance variability, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Quality Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0498 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that nonconformance, defective material or weak traceability, combined with performance variability, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Quality Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0499 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that nonconformance, defective material or weak traceability, combined with performance variability, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Quality Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0500 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that nonconformance, defective material or weak traceability, combined with performance variability, may adversely affect project objectives through quality / cost / time consequences. | Quality & Defects | EPCM | Pumped Storage | Latin America | Detailed Engineering | Contractor | M | Quality / Cost / Time | Establish controls for nonconformance, defective material or weak traceability; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Quality Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0501 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that unsafe work, weak supervision or permit failure, combined with insufficient planning, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0502 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that unsafe work, weak supervision or permit failure, combined with insufficient planning, may adversely affect project objectives through hse / time / cost consequences. | HSE | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0503 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that unsafe work, weak supervision or permit failure, combined with insufficient planning, may adversely affect project objectives through hse / time / cost consequences. | HSE | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0504 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that unsafe work, weak supervision or permit failure, combined with insufficient planning, may adversely affect project objectives through hse / time / cost consequences. | HSE | Grid Interconnection | Offshore Wind | North America | Procurement | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0505 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that unsafe work, weak supervision or permit failure, combined with insufficient planning, may adversely affect project objectives through hse / time / cost consequences. | HSE | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0506 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that unsafe work, weak supervision or permit failure, combined with incomplete information, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0507 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that unsafe work, weak supervision or permit failure, combined with incomplete information, may adversely affect project objectives through hse / time / cost consequences. | HSE | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0508 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that unsafe work, weak supervision or permit failure, combined with incomplete information, may adversely affect project objectives through hse / time / cost consequences. | HSE | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0509 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that unsafe work, weak supervision or permit failure, combined with incomplete information, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPC / Turnkey | Hydropower | Latin America | Construction | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0510 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that unsafe work, weak supervision or permit failure, combined with incomplete information, may adversely affect project objectives through hse / time / cost consequences. | HSE | Installation | Nuclear Power | Global / Multi-country | Installation | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0511 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that unsafe work, weak supervision or permit failure, combined with late decision-making, may adversely affect project objectives through hse / time / cost consequences. | HSE | R&D / Technology Development | Geothermal | Africa | Manufacturing | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0512 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that unsafe work, weak supervision or permit failure, combined with late decision-making, may adversely affect project objectives through hse / time / cost consequences. | HSE | Brownfield Modification | LNG | East Asia | Construction | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0513 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that unsafe work, weak supervision or permit failure, combined with late decision-making, may adversely affect project objectives through hse / time / cost consequences. | HSE | Owner’s Engineering | Onshore Wind | North America | Installation | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0514 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that unsafe work, weak supervision or permit failure, combined with late decision-making, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0515 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that unsafe work, weak supervision or permit failure, combined with late decision-making, may adversely affect project objectives through hse / time / cost consequences. | HSE | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0516 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that unsafe work, weak supervision or permit failure, combined with weak controls, may adversely affect project objectives through hse / time / cost consequences. | HSE | Installation | Battery Energy Storage | South Asia | Installation | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0517 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that unsafe work, weak supervision or permit failure, combined with weak controls, may adversely affect project objectives through hse / time / cost consequences. | HSE | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0518 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that unsafe work, weak supervision or permit failure, combined with weak controls, may adversely affect project objectives through hse / time / cost consequences. | HSE | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0519 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that unsafe work, weak supervision or permit failure, combined with weak controls, may adversely affect project objectives through hse / time / cost consequences. | HSE | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0520 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that unsafe work, weak supervision or permit failure, combined with weak controls, may adversely affect project objectives through hse / time / cost consequences. | HSE | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0521 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that unsafe work, weak supervision or permit failure, combined with resource constraints, may adversely affect project objectives through hse / time / cost consequences. | HSE | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0522 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that unsafe work, weak supervision or permit failure, combined with resource constraints, may adversely affect project objectives through hse / time / cost consequences. | HSE | Decommissioning | Marine Energy | North America | Operations / Handover | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0523 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that unsafe work, weak supervision or permit failure, combined with resource constraints, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0524 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that unsafe work, weak supervision or permit failure, combined with resource constraints, may adversely affect project objectives through hse / time / cost consequences. | HSE | Installation | LNG | Europe | FEED / Basic Design | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0525 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that unsafe work, weak supervision or permit failure, combined with resource constraints, may adversely affect project objectives through hse / time / cost consequences. | HSE | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0526 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that unsafe work, weak supervision or permit failure, combined with supplier dependency, may adversely affect project objectives through hse / time / cost consequences. | HSE | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0527 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that unsafe work, weak supervision or permit failure, combined with supplier dependency, may adversely affect project objectives through hse / time / cost consequences. | HSE | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0528 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that unsafe work, weak supervision or permit failure, combined with supplier dependency, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0529 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that unsafe work, weak supervision or permit failure, combined with supplier dependency, may adversely affect project objectives through hse / time / cost consequences. | HSE | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0530 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that unsafe work, weak supervision or permit failure, combined with supplier dependency, may adversely affect project objectives through hse / time / cost consequences. | HSE | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0531 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that unsafe work, weak supervision or permit failure, combined with interface complexity, may adversely affect project objectives through hse / time / cost consequences. | HSE | Operations & Maintenance | District Energy | North America | Detailed Engineering | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0532 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that unsafe work, weak supervision or permit failure, combined with interface complexity, may adversely affect project objectives through hse / time / cost consequences. | HSE | Grid Interconnection | Pumped Storage | Oceania | Procurement | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0533 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that unsafe work, weak supervision or permit failure, combined with interface complexity, may adversely affect project objectives through hse / time / cost consequences. | HSE | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0534 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that unsafe work, weak supervision or permit failure, combined with interface complexity, may adversely affect project objectives through hse / time / cost consequences. | HSE | Brownfield Modification | Marine Energy | Africa | Construction | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0535 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that unsafe work, weak supervision or permit failure, combined with interface complexity, may adversely affect project objectives through hse / time / cost consequences. | HSE | Owner’s Engineering | Geothermal | East Asia | Installation | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0536 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that unsafe work, weak supervision or permit failure, combined with requirements volatility, may adversely affect project objectives through hse / time / cost consequences. | HSE | Decommissioning | Offshore Wind | Latin America | Manufacturing | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0537 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that unsafe work, weak supervision or permit failure, combined with requirements volatility, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0538 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that unsafe work, weak supervision or permit failure, combined with requirements volatility, may adversely affect project objectives through hse / time / cost consequences. | HSE | Installation | Refining & Petrochemicals | Middle East | Installation | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0539 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that unsafe work, weak supervision or permit failure, combined with requirements volatility, may adversely affect project objectives through hse / time / cost consequences. | HSE | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0540 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that unsafe work, weak supervision or permit failure, combined with requirements volatility, may adversely affect project objectives through hse / time / cost consequences. | HSE | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0541 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that unsafe work, weak supervision or permit failure, combined with regulatory uncertainty, may adversely affect project objectives through hse / time / cost consequences. | HSE | Owner’s Engineering | Hydropower | Oceania | Installation | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0542 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that unsafe work, weak supervision or permit failure, combined with regulatory uncertainty, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPCM | Nuclear Power | Europe | Pre-commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0543 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that unsafe work, weak supervision or permit failure, combined with regulatory uncertainty, may adversely affect project objectives through hse / time / cost consequences. | HSE | Commissioning & Start-up | District Energy | Africa | Commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0544 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that unsafe work, weak supervision or permit failure, combined with regulatory uncertainty, may adversely affect project objectives through hse / time / cost consequences. | HSE | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0545 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that unsafe work, weak supervision or permit failure, combined with regulatory uncertainty, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0546 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that unsafe work, weak supervision or permit failure, combined with inadequate verification, may adversely affect project objectives through hse / time / cost consequences. | HSE | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0547 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that unsafe work, weak supervision or permit failure, combined with inadequate verification, may adversely affect project objectives through hse / time / cost consequences. | HSE | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0548 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that unsafe work, weak supervision or permit failure, combined with inadequate verification, may adversely affect project objectives through hse / time / cost consequences. | HSE | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0549 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that unsafe work, weak supervision or permit failure, combined with inadequate verification, may adversely affect project objectives through hse / time / cost consequences. | HSE | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0550 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that unsafe work, weak supervision or permit failure, combined with inadequate verification, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0551 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that unsafe work, weak supervision or permit failure, combined with poor communication, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0552 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that unsafe work, weak supervision or permit failure, combined with poor communication, may adversely affect project objectives through hse / time / cost consequences. | HSE | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0553 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that unsafe work, weak supervision or permit failure, combined with poor communication, may adversely affect project objectives through hse / time / cost consequences. | HSE | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0554 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that unsafe work, weak supervision or permit failure, combined with poor communication, may adversely affect project objectives through hse / time / cost consequences. | HSE | Grid Interconnection | Nuclear Power | North America | Procurement | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0555 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that unsafe work, weak supervision or permit failure, combined with poor communication, may adversely affect project objectives through hse / time / cost consequences. | HSE | R&D / Technology Development | District Energy | Oceania | Manufacturing | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0556 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that unsafe work, weak supervision or permit failure, combined with incorrect assumptions, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPCM | LNG | Middle East | Detailed Engineering | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0557 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that unsafe work, weak supervision or permit failure, combined with incorrect assumptions, may adversely affect project objectives through hse / time / cost consequences. | HSE | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0558 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that unsafe work, weak supervision or permit failure, combined with incorrect assumptions, may adversely affect project objectives through hse / time / cost consequences. | HSE | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0559 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that unsafe work, weak supervision or permit failure, combined with incorrect assumptions, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0560 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that unsafe work, weak supervision or permit failure, combined with incorrect assumptions, may adversely affect project objectives through hse / time / cost consequences. | HSE | Installation | Offshore Wind | Global / Multi-country | Installation | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0561 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that unsafe work, weak supervision or permit failure, combined with low technical maturity, may adversely affect project objectives through hse / time / cost consequences. | HSE | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0562 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that unsafe work, weak supervision or permit failure, combined with low technical maturity, may adversely affect project objectives through hse / time / cost consequences. | HSE | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0563 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that unsafe work, weak supervision or permit failure, combined with low technical maturity, may adversely affect project objectives through hse / time / cost consequences. | HSE | Owner’s Engineering | Transmission & Substations | North America | Installation | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0564 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that unsafe work, weak supervision or permit failure, combined with low technical maturity, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0565 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that unsafe work, weak supervision or permit failure, combined with low technical maturity, may adversely affect project objectives through hse / time / cost consequences. | HSE | Commissioning & Start-up | Hydropower | Europe | Commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0566 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that unsafe work, weak supervision or permit failure, combined with documentation gaps, may adversely affect project objectives through hse / time / cost consequences. | HSE | Installation | Marine Energy | South Asia | Installation | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0567 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that unsafe work, weak supervision or permit failure, combined with documentation gaps, may adversely affect project objectives through hse / time / cost consequences. | HSE | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0568 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that unsafe work, weak supervision or permit failure, combined with documentation gaps, may adversely affect project objectives through hse / time / cost consequences. | HSE | Grid Interconnection | LNG | Latin America | Commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0569 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that unsafe work, weak supervision or permit failure, combined with documentation gaps, may adversely affect project objectives through hse / time / cost consequences. | HSE | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0570 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that unsafe work, weak supervision or permit failure, combined with documentation gaps, may adversely affect project objectives through hse / time / cost consequences. | HSE | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0571 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that unsafe work, weak supervision or permit failure, combined with external disruption, may adversely affect project objectives through hse / time / cost consequences. | HSE | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0572 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that unsafe work, weak supervision or permit failure, combined with external disruption, may adversely affect project objectives through hse / time / cost consequences. | HSE | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0573 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that unsafe work, weak supervision or permit failure, combined with external disruption, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0574 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that unsafe work, weak supervision or permit failure, combined with external disruption, may adversely affect project objectives through hse / time / cost consequences. | HSE | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0575 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that unsafe work, weak supervision or permit failure, combined with external disruption, may adversely affect project objectives through hse / time / cost consequences. | HSE | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0576 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that unsafe work, weak supervision or permit failure, combined with governance delay, may adversely affect project objectives through hse / time / cost consequences. | HSE | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0577 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that unsafe work, weak supervision or permit failure, combined with governance delay, may adversely affect project objectives through hse / time / cost consequences. | HSE | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0578 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that unsafe work, weak supervision or permit failure, combined with governance delay, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0579 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that unsafe work, weak supervision or permit failure, combined with governance delay, may adversely affect project objectives through hse / time / cost consequences. | HSE | Commissioning & Start-up | Geothermal | Middle East | Procurement | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0580 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that unsafe work, weak supervision or permit failure, combined with governance delay, may adversely affect project objectives through hse / time / cost consequences. | HSE | Decommissioning | LNG | South Asia | Manufacturing | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0581 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that unsafe work, weak supervision or permit failure, combined with commercial misalignment, may adversely affect project objectives through hse / time / cost consequences. | HSE | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0582 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that unsafe work, weak supervision or permit failure, combined with commercial misalignment, may adversely affect project objectives through hse / time / cost consequences. | HSE | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0583 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that unsafe work, weak supervision or permit failure, combined with commercial misalignment, may adversely affect project objectives through hse / time / cost consequences. | HSE | R&D / Technology Development | Solar PV | Europe | Manufacturing | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0584 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that unsafe work, weak supervision or permit failure, combined with commercial misalignment, may adversely affect project objectives through hse / time / cost consequences. | HSE | Brownfield Modification | Battery Energy Storage | Africa | Construction | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0585 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that unsafe work, weak supervision or permit failure, combined with commercial misalignment, may adversely affect project objectives through hse / time / cost consequences. | HSE | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0586 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that unsafe work, weak supervision or permit failure, combined with quality escape, may adversely affect project objectives through hse / time / cost consequences. | HSE | Decommissioning | Nuclear Power | Latin America | Manufacturing | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0587 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that unsafe work, weak supervision or permit failure, combined with quality escape, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0588 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that unsafe work, weak supervision or permit failure, combined with quality escape, may adversely affect project objectives through hse / time / cost consequences. | HSE | Installation | Pumped Storage | Middle East | Installation | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0589 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that unsafe work, weak supervision or permit failure, combined with quality escape, may adversely affect project objectives through hse / time / cost consequences. | HSE | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0590 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that unsafe work, weak supervision or permit failure, combined with quality escape, may adversely affect project objectives through hse / time / cost consequences. | HSE | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0591 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that unsafe work, weak supervision or permit failure, combined with access constraint, may adversely affect project objectives through hse / time / cost consequences. | HSE | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0592 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that unsafe work, weak supervision or permit failure, combined with access constraint, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPCM | Offshore Wind | Europe | Pre-commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0593 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that unsafe work, weak supervision or permit failure, combined with access constraint, may adversely affect project objectives through hse / time / cost consequences. | HSE | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0594 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that unsafe work, weak supervision or permit failure, combined with access constraint, may adversely affect project objectives through hse / time / cost consequences. | HSE | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0595 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that unsafe work, weak supervision or permit failure, combined with access constraint, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0596 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that unsafe work, weak supervision or permit failure, combined with performance variability, may adversely affect project objectives through hse / time / cost consequences. | HSE | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | HSE Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0597 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that unsafe work, weak supervision or permit failure, combined with performance variability, may adversely affect project objectives through hse / time / cost consequences. | HSE | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | HSE Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0598 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that unsafe work, weak supervision or permit failure, combined with performance variability, may adversely affect project objectives through hse / time / cost consequences. | HSE | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | HSE Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0599 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that unsafe work, weak supervision or permit failure, combined with performance variability, may adversely affect project objectives through hse / time / cost consequences. | HSE | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | HSE Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0600 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that unsafe work, weak supervision or permit failure, combined with performance variability, may adversely affect project objectives through hse / time / cost consequences. | HSE | EPCM | Pumped Storage | Latin America | Detailed Engineering | Contractor | M | HSE / Time / Cost | Establish controls for unsafe work, weak supervision or permit failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | HSE Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0601 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that pollution, waste failure or permit breach, combined with insufficient planning, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0602 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that pollution, waste failure or permit breach, combined with insufficient planning, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0603 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that pollution, waste failure or permit breach, combined with insufficient planning, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0604 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that pollution, waste failure or permit breach, combined with insufficient planning, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Grid Interconnection | Offshore Wind | North America | Procurement | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0605 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that pollution, waste failure or permit breach, combined with insufficient planning, may adversely affect project objectives through hse / cost / time consequences. | Environmental | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0606 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that pollution, waste failure or permit breach, combined with incomplete information, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0607 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that pollution, waste failure or permit breach, combined with incomplete information, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0608 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that pollution, waste failure or permit breach, combined with incomplete information, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0609 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that pollution, waste failure or permit breach, combined with incomplete information, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPC / Turnkey | Hydropower | Latin America | Construction | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0610 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that pollution, waste failure or permit breach, combined with incomplete information, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Installation | Nuclear Power | Global / Multi-country | Installation | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0611 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that pollution, waste failure or permit breach, combined with late decision-making, may adversely affect project objectives through hse / cost / time consequences. | Environmental | R&D / Technology Development | Geothermal | Africa | Manufacturing | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0612 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that pollution, waste failure or permit breach, combined with late decision-making, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Brownfield Modification | LNG | East Asia | Construction | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0613 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that pollution, waste failure or permit breach, combined with late decision-making, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Owner’s Engineering | Onshore Wind | North America | Installation | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0614 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that pollution, waste failure or permit breach, combined with late decision-making, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0615 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that pollution, waste failure or permit breach, combined with late decision-making, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0616 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that pollution, waste failure or permit breach, combined with weak controls, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Installation | Battery Energy Storage | South Asia | Installation | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0617 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that pollution, waste failure or permit breach, combined with weak controls, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0618 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that pollution, waste failure or permit breach, combined with weak controls, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0619 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that pollution, waste failure or permit breach, combined with weak controls, may adversely affect project objectives through hse / cost / time consequences. | Environmental | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0620 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that pollution, waste failure or permit breach, combined with weak controls, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0621 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that pollution, waste failure or permit breach, combined with resource constraints, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0622 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that pollution, waste failure or permit breach, combined with resource constraints, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Decommissioning | Marine Energy | North America | Operations / Handover | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0623 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that pollution, waste failure or permit breach, combined with resource constraints, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0624 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that pollution, waste failure or permit breach, combined with resource constraints, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Installation | LNG | Europe | FEED / Basic Design | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0625 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that pollution, waste failure or permit breach, combined with resource constraints, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0626 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that pollution, waste failure or permit breach, combined with supplier dependency, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0627 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that pollution, waste failure or permit breach, combined with supplier dependency, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0628 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that pollution, waste failure or permit breach, combined with supplier dependency, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0629 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that pollution, waste failure or permit breach, combined with supplier dependency, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0630 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that pollution, waste failure or permit breach, combined with supplier dependency, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0631 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that pollution, waste failure or permit breach, combined with interface complexity, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Operations & Maintenance | District Energy | North America | Detailed Engineering | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0632 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that pollution, waste failure or permit breach, combined with interface complexity, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Grid Interconnection | Pumped Storage | Oceania | Procurement | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0633 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that pollution, waste failure or permit breach, combined with interface complexity, may adversely affect project objectives through hse / cost / time consequences. | Environmental | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0634 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that pollution, waste failure or permit breach, combined with interface complexity, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Brownfield Modification | Marine Energy | Africa | Construction | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0635 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that pollution, waste failure or permit breach, combined with interface complexity, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Owner’s Engineering | Geothermal | East Asia | Installation | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0636 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that pollution, waste failure or permit breach, combined with requirements volatility, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Decommissioning | Offshore Wind | Latin America | Manufacturing | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0637 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that pollution, waste failure or permit breach, combined with requirements volatility, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0638 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that pollution, waste failure or permit breach, combined with requirements volatility, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Installation | Refining & Petrochemicals | Middle East | Installation | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0639 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that pollution, waste failure or permit breach, combined with requirements volatility, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0640 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that pollution, waste failure or permit breach, combined with requirements volatility, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0641 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that pollution, waste failure or permit breach, combined with regulatory uncertainty, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Owner’s Engineering | Hydropower | Oceania | Installation | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0642 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that pollution, waste failure or permit breach, combined with regulatory uncertainty, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPCM | Nuclear Power | Europe | Pre-commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0643 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that pollution, waste failure or permit breach, combined with regulatory uncertainty, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Commissioning & Start-up | District Energy | Africa | Commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0644 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that pollution, waste failure or permit breach, combined with regulatory uncertainty, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0645 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that pollution, waste failure or permit breach, combined with regulatory uncertainty, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0646 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that pollution, waste failure or permit breach, combined with inadequate verification, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0647 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that pollution, waste failure or permit breach, combined with inadequate verification, may adversely affect project objectives through hse / cost / time consequences. | Environmental | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0648 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that pollution, waste failure or permit breach, combined with inadequate verification, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0649 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that pollution, waste failure or permit breach, combined with inadequate verification, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0650 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that pollution, waste failure or permit breach, combined with inadequate verification, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0651 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that pollution, waste failure or permit breach, combined with poor communication, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0652 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that pollution, waste failure or permit breach, combined with poor communication, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0653 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that pollution, waste failure or permit breach, combined with poor communication, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0654 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that pollution, waste failure or permit breach, combined with poor communication, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Grid Interconnection | Nuclear Power | North America | Procurement | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0655 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that pollution, waste failure or permit breach, combined with poor communication, may adversely affect project objectives through hse / cost / time consequences. | Environmental | R&D / Technology Development | District Energy | Oceania | Manufacturing | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0656 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that pollution, waste failure or permit breach, combined with incorrect assumptions, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPCM | LNG | Middle East | Detailed Engineering | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0657 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that pollution, waste failure or permit breach, combined with incorrect assumptions, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0658 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that pollution, waste failure or permit breach, combined with incorrect assumptions, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0659 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that pollution, waste failure or permit breach, combined with incorrect assumptions, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0660 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that pollution, waste failure or permit breach, combined with incorrect assumptions, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Installation | Offshore Wind | Global / Multi-country | Installation | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0661 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that pollution, waste failure or permit breach, combined with low technical maturity, may adversely affect project objectives through hse / cost / time consequences. | Environmental | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0662 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that pollution, waste failure or permit breach, combined with low technical maturity, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0663 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that pollution, waste failure or permit breach, combined with low technical maturity, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Owner’s Engineering | Transmission & Substations | North America | Installation | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0664 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that pollution, waste failure or permit breach, combined with low technical maturity, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0665 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that pollution, waste failure or permit breach, combined with low technical maturity, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Commissioning & Start-up | Hydropower | Europe | Commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0666 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that pollution, waste failure or permit breach, combined with documentation gaps, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Installation | Marine Energy | South Asia | Installation | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0667 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that pollution, waste failure or permit breach, combined with documentation gaps, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0668 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that pollution, waste failure or permit breach, combined with documentation gaps, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Grid Interconnection | LNG | Latin America | Commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0669 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that pollution, waste failure or permit breach, combined with documentation gaps, may adversely affect project objectives through hse / cost / time consequences. | Environmental | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0670 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that pollution, waste failure or permit breach, combined with documentation gaps, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0671 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that pollution, waste failure or permit breach, combined with external disruption, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0672 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that pollution, waste failure or permit breach, combined with external disruption, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0673 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that pollution, waste failure or permit breach, combined with external disruption, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0674 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that pollution, waste failure or permit breach, combined with external disruption, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0675 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that pollution, waste failure or permit breach, combined with external disruption, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0676 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that pollution, waste failure or permit breach, combined with governance delay, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0677 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that pollution, waste failure or permit breach, combined with governance delay, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0678 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that pollution, waste failure or permit breach, combined with governance delay, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0679 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that pollution, waste failure or permit breach, combined with governance delay, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Commissioning & Start-up | Geothermal | Middle East | Procurement | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0680 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that pollution, waste failure or permit breach, combined with governance delay, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Decommissioning | LNG | South Asia | Manufacturing | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0681 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that pollution, waste failure or permit breach, combined with commercial misalignment, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0682 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that pollution, waste failure or permit breach, combined with commercial misalignment, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0683 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that pollution, waste failure or permit breach, combined with commercial misalignment, may adversely affect project objectives through hse / cost / time consequences. | Environmental | R&D / Technology Development | Solar PV | Europe | Manufacturing | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0684 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that pollution, waste failure or permit breach, combined with commercial misalignment, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Brownfield Modification | Battery Energy Storage | Africa | Construction | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0685 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that pollution, waste failure or permit breach, combined with commercial misalignment, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0686 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that pollution, waste failure or permit breach, combined with quality escape, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Decommissioning | Nuclear Power | Latin America | Manufacturing | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0687 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that pollution, waste failure or permit breach, combined with quality escape, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0688 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that pollution, waste failure or permit breach, combined with quality escape, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Installation | Pumped Storage | Middle East | Installation | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0689 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that pollution, waste failure or permit breach, combined with quality escape, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0690 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that pollution, waste failure or permit breach, combined with quality escape, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0691 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that pollution, waste failure or permit breach, combined with access constraint, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0692 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that pollution, waste failure or permit breach, combined with access constraint, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPCM | Offshore Wind | Europe | Pre-commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0693 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that pollution, waste failure or permit breach, combined with access constraint, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0694 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that pollution, waste failure or permit breach, combined with access constraint, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0695 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that pollution, waste failure or permit breach, combined with access constraint, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0696 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that pollution, waste failure or permit breach, combined with performance variability, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Environmental Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0697 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that pollution, waste failure or permit breach, combined with performance variability, may adversely affect project objectives through hse / cost / time consequences. | Environmental | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Environmental Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0698 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that pollution, waste failure or permit breach, combined with performance variability, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Environmental Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0699 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that pollution, waste failure or permit breach, combined with performance variability, may adversely affect project objectives through hse / cost / time consequences. | Environmental | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Environmental Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0700 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that pollution, waste failure or permit breach, combined with performance variability, may adversely affect project objectives through hse / cost / time consequences. | Environmental | EPCM | Pumped Storage | Latin America | Detailed Engineering | Shared | M | HSE / Cost / Time | Establish controls for pollution, waste failure or permit breach; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Environmental Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0701 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that political instability, trade restriction or civil disturbance, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Political & Country | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0702 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that political instability, trade restriction or civil disturbance, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Political & Country | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0703 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that political instability, trade restriction or civil disturbance, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Political & Country | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0704 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that political instability, trade restriction or civil disturbance, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Political & Country | Grid Interconnection | Offshore Wind | North America | Procurement | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0705 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that political instability, trade restriction or civil disturbance, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Political & Country | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0706 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that political instability, trade restriction or civil disturbance, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Political & Country | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0707 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that political instability, trade restriction or civil disturbance, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Political & Country | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0708 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that political instability, trade restriction or civil disturbance, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Political & Country | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0709 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that political instability, trade restriction or civil disturbance, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Political & Country | EPC / Turnkey | Hydropower | Latin America | Construction | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0710 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that political instability, trade restriction or civil disturbance, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Political & Country | Installation | Nuclear Power | Global / Multi-country | Installation | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0711 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that political instability, trade restriction or civil disturbance, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Political & Country | R&D / Technology Development | Geothermal | Africa | Manufacturing | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0712 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that political instability, trade restriction or civil disturbance, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Political & Country | Brownfield Modification | LNG | East Asia | Construction | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0713 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that political instability, trade restriction or civil disturbance, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Political & Country | Owner’s Engineering | Onshore Wind | North America | Installation | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0714 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that political instability, trade restriction or civil disturbance, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Political & Country | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0715 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that political instability, trade restriction or civil disturbance, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Political & Country | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0716 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that political instability, trade restriction or civil disturbance, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Political & Country | Installation | Battery Energy Storage | South Asia | Installation | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0717 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that political instability, trade restriction or civil disturbance, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Political & Country | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0718 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that political instability, trade restriction or civil disturbance, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Political & Country | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0719 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that political instability, trade restriction or civil disturbance, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Political & Country | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0720 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that political instability, trade restriction or civil disturbance, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Political & Country | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0721 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that political instability, trade restriction or civil disturbance, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Political & Country | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0722 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that political instability, trade restriction or civil disturbance, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Political & Country | Decommissioning | Marine Energy | North America | Operations / Handover | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0723 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that political instability, trade restriction or civil disturbance, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Political & Country | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0724 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that political instability, trade restriction or civil disturbance, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Political & Country | Installation | LNG | Europe | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0725 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that political instability, trade restriction or civil disturbance, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Political & Country | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0726 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that political instability, trade restriction or civil disturbance, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Political & Country | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0727 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that political instability, trade restriction or civil disturbance, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Political & Country | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0728 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that political instability, trade restriction or civil disturbance, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Political & Country | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0729 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that political instability, trade restriction or civil disturbance, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Political & Country | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0730 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that political instability, trade restriction or civil disturbance, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Political & Country | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0731 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that political instability, trade restriction or civil disturbance, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Political & Country | Operations & Maintenance | District Energy | North America | Detailed Engineering | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0732 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that political instability, trade restriction or civil disturbance, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Political & Country | Grid Interconnection | Pumped Storage | Oceania | Procurement | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0733 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that political instability, trade restriction or civil disturbance, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Political & Country | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0734 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that political instability, trade restriction or civil disturbance, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Political & Country | Brownfield Modification | Marine Energy | Africa | Construction | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0735 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that political instability, trade restriction or civil disturbance, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Political & Country | Owner’s Engineering | Geothermal | East Asia | Installation | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0736 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that political instability, trade restriction or civil disturbance, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Political & Country | Decommissioning | Offshore Wind | Latin America | Manufacturing | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0737 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that political instability, trade restriction or civil disturbance, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Political & Country | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0738 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that political instability, trade restriction or civil disturbance, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Political & Country | Installation | Refining & Petrochemicals | Middle East | Installation | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0739 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that political instability, trade restriction or civil disturbance, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Political & Country | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0740 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that political instability, trade restriction or civil disturbance, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Political & Country | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0741 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that political instability, trade restriction or civil disturbance, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Political & Country | Owner’s Engineering | Hydropower | Oceania | Installation | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0742 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that political instability, trade restriction or civil disturbance, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Political & Country | EPCM | Nuclear Power | Europe | Pre-commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0743 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that political instability, trade restriction or civil disturbance, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Political & Country | Commissioning & Start-up | District Energy | Africa | Commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0744 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that political instability, trade restriction or civil disturbance, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Political & Country | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0745 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that political instability, trade restriction or civil disturbance, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Political & Country | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0746 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that political instability, trade restriction or civil disturbance, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Political & Country | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0747 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that political instability, trade restriction or civil disturbance, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Political & Country | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0748 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that political instability, trade restriction or civil disturbance, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Political & Country | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0749 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that political instability, trade restriction or civil disturbance, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Political & Country | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0750 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that political instability, trade restriction or civil disturbance, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Political & Country | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0751 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that political instability, trade restriction or civil disturbance, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Political & Country | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0752 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that political instability, trade restriction or civil disturbance, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Political & Country | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0753 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that political instability, trade restriction or civil disturbance, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Political & Country | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0754 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that political instability, trade restriction or civil disturbance, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Political & Country | Grid Interconnection | Nuclear Power | North America | Procurement | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0755 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that political instability, trade restriction or civil disturbance, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Political & Country | R&D / Technology Development | District Energy | Oceania | Manufacturing | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0756 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that political instability, trade restriction or civil disturbance, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Political & Country | EPCM | LNG | Middle East | Detailed Engineering | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0757 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that political instability, trade restriction or civil disturbance, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Political & Country | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0758 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that political instability, trade restriction or civil disturbance, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Political & Country | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0759 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that political instability, trade restriction or civil disturbance, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Political & Country | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0760 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that political instability, trade restriction or civil disturbance, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Political & Country | Installation | Offshore Wind | Global / Multi-country | Installation | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0761 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that political instability, trade restriction or civil disturbance, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Political & Country | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0762 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that political instability, trade restriction or civil disturbance, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Political & Country | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0763 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that political instability, trade restriction or civil disturbance, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Political & Country | Owner’s Engineering | Transmission & Substations | North America | Installation | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0764 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that political instability, trade restriction or civil disturbance, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Political & Country | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0765 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that political instability, trade restriction or civil disturbance, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Political & Country | Commissioning & Start-up | Hydropower | Europe | Commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0766 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that political instability, trade restriction or civil disturbance, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Political & Country | Installation | Marine Energy | South Asia | Installation | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0767 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that political instability, trade restriction or civil disturbance, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Political & Country | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0768 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that political instability, trade restriction or civil disturbance, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Political & Country | Grid Interconnection | LNG | Latin America | Commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0769 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that political instability, trade restriction or civil disturbance, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Political & Country | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0770 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that political instability, trade restriction or civil disturbance, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Political & Country | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0771 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that political instability, trade restriction or civil disturbance, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Political & Country | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0772 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that political instability, trade restriction or civil disturbance, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Political & Country | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0773 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that political instability, trade restriction or civil disturbance, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Political & Country | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0774 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that political instability, trade restriction or civil disturbance, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Political & Country | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0775 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that political instability, trade restriction or civil disturbance, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Political & Country | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0776 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that political instability, trade restriction or civil disturbance, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Political & Country | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0777 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that political instability, trade restriction or civil disturbance, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Political & Country | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0778 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that political instability, trade restriction or civil disturbance, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Political & Country | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0779 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that political instability, trade restriction or civil disturbance, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Political & Country | Commissioning & Start-up | Geothermal | Middle East | Procurement | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0780 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that political instability, trade restriction or civil disturbance, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Political & Country | Decommissioning | LNG | South Asia | Manufacturing | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0781 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that political instability, trade restriction or civil disturbance, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Political & Country | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0782 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that political instability, trade restriction or civil disturbance, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Political & Country | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0783 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that political instability, trade restriction or civil disturbance, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Political & Country | R&D / Technology Development | Solar PV | Europe | Manufacturing | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0784 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that political instability, trade restriction or civil disturbance, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Political & Country | Brownfield Modification | Battery Energy Storage | Africa | Construction | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0785 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that political instability, trade restriction or civil disturbance, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Political & Country | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0786 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that political instability, trade restriction or civil disturbance, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Political & Country | Decommissioning | Nuclear Power | Latin America | Manufacturing | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0787 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that political instability, trade restriction or civil disturbance, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Political & Country | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0788 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that political instability, trade restriction or civil disturbance, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Political & Country | Installation | Pumped Storage | Middle East | Installation | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0789 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that political instability, trade restriction or civil disturbance, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Political & Country | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0790 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that political instability, trade restriction or civil disturbance, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Political & Country | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0791 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that political instability, trade restriction or civil disturbance, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Political & Country | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0792 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that political instability, trade restriction or civil disturbance, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Political & Country | EPCM | Offshore Wind | Europe | Pre-commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0793 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that political instability, trade restriction or civil disturbance, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Political & Country | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0794 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that political instability, trade restriction or civil disturbance, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Political & Country | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0795 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that political instability, trade restriction or civil disturbance, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Political & Country | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0796 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that political instability, trade restriction or civil disturbance, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Political & Country | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0797 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that political instability, trade restriction or civil disturbance, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Political & Country | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0798 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that political instability, trade restriction or civil disturbance, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Political & Country | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0799 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that political instability, trade restriction or civil disturbance, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Political & Country | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0800 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that political instability, trade restriction or civil disturbance, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Political & Country | EPCM | Pumped Storage | Latin America | Detailed Engineering | Employer | M | Cost / Time | Establish controls for political instability, trade restriction or civil disturbance; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0801 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that new law, code change or conflicting interpretation, combined with insufficient planning, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0802 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that new law, code change or conflicting interpretation, combined with insufficient planning, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0803 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that new law, code change or conflicting interpretation, combined with insufficient planning, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0804 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that new law, code change or conflicting interpretation, combined with insufficient planning, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Grid Interconnection | Offshore Wind | North America | Procurement | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0805 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that new law, code change or conflicting interpretation, combined with insufficient planning, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0806 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that new law, code change or conflicting interpretation, combined with incomplete information, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0807 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that new law, code change or conflicting interpretation, combined with incomplete information, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0808 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that new law, code change or conflicting interpretation, combined with incomplete information, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0809 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that new law, code change or conflicting interpretation, combined with incomplete information, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPC / Turnkey | Hydropower | Latin America | Construction | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0810 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that new law, code change or conflicting interpretation, combined with incomplete information, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Installation | Nuclear Power | Global / Multi-country | Installation | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0811 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that new law, code change or conflicting interpretation, combined with late decision-making, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | R&D / Technology Development | Geothermal | Africa | Manufacturing | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0812 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that new law, code change or conflicting interpretation, combined with late decision-making, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Brownfield Modification | LNG | East Asia | Construction | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0813 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that new law, code change or conflicting interpretation, combined with late decision-making, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Owner’s Engineering | Onshore Wind | North America | Installation | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0814 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that new law, code change or conflicting interpretation, combined with late decision-making, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0815 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that new law, code change or conflicting interpretation, combined with late decision-making, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0816 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that new law, code change or conflicting interpretation, combined with weak controls, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Installation | Battery Energy Storage | South Asia | Installation | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0817 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that new law, code change or conflicting interpretation, combined with weak controls, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0818 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that new law, code change or conflicting interpretation, combined with weak controls, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0819 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that new law, code change or conflicting interpretation, combined with weak controls, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0820 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that new law, code change or conflicting interpretation, combined with weak controls, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0821 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that new law, code change or conflicting interpretation, combined with resource constraints, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0822 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that new law, code change or conflicting interpretation, combined with resource constraints, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Decommissioning | Marine Energy | North America | Operations / Handover | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0823 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that new law, code change or conflicting interpretation, combined with resource constraints, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0824 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that new law, code change or conflicting interpretation, combined with resource constraints, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Installation | LNG | Europe | FEED / Basic Design | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0825 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that new law, code change or conflicting interpretation, combined with resource constraints, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0826 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that new law, code change or conflicting interpretation, combined with supplier dependency, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0827 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that new law, code change or conflicting interpretation, combined with supplier dependency, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0828 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that new law, code change or conflicting interpretation, combined with supplier dependency, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0829 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that new law, code change or conflicting interpretation, combined with supplier dependency, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0830 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that new law, code change or conflicting interpretation, combined with supplier dependency, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0831 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that new law, code change or conflicting interpretation, combined with interface complexity, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Operations & Maintenance | District Energy | North America | Detailed Engineering | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0832 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that new law, code change or conflicting interpretation, combined with interface complexity, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Grid Interconnection | Pumped Storage | Oceania | Procurement | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0833 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that new law, code change or conflicting interpretation, combined with interface complexity, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0834 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that new law, code change or conflicting interpretation, combined with interface complexity, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Brownfield Modification | Marine Energy | Africa | Construction | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0835 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that new law, code change or conflicting interpretation, combined with interface complexity, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Owner’s Engineering | Geothermal | East Asia | Installation | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0836 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that new law, code change or conflicting interpretation, combined with requirements volatility, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Decommissioning | Offshore Wind | Latin America | Manufacturing | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0837 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that new law, code change or conflicting interpretation, combined with requirements volatility, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0838 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that new law, code change or conflicting interpretation, combined with requirements volatility, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Installation | Refining & Petrochemicals | Middle East | Installation | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0839 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that new law, code change or conflicting interpretation, combined with requirements volatility, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0840 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that new law, code change or conflicting interpretation, combined with requirements volatility, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0841 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that new law, code change or conflicting interpretation, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Owner’s Engineering | Hydropower | Oceania | Installation | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0842 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that new law, code change or conflicting interpretation, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPCM | Nuclear Power | Europe | Pre-commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0843 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that new law, code change or conflicting interpretation, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Commissioning & Start-up | District Energy | Africa | Commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0844 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that new law, code change or conflicting interpretation, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0845 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that new law, code change or conflicting interpretation, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0846 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that new law, code change or conflicting interpretation, combined with inadequate verification, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0847 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that new law, code change or conflicting interpretation, combined with inadequate verification, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0848 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that new law, code change or conflicting interpretation, combined with inadequate verification, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0849 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that new law, code change or conflicting interpretation, combined with inadequate verification, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0850 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that new law, code change or conflicting interpretation, combined with inadequate verification, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0851 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that new law, code change or conflicting interpretation, combined with poor communication, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0852 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that new law, code change or conflicting interpretation, combined with poor communication, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0853 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that new law, code change or conflicting interpretation, combined with poor communication, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0854 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that new law, code change or conflicting interpretation, combined with poor communication, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Grid Interconnection | Nuclear Power | North America | Procurement | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0855 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that new law, code change or conflicting interpretation, combined with poor communication, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | R&D / Technology Development | District Energy | Oceania | Manufacturing | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0856 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that new law, code change or conflicting interpretation, combined with incorrect assumptions, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPCM | LNG | Middle East | Detailed Engineering | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0857 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that new law, code change or conflicting interpretation, combined with incorrect assumptions, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0858 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that new law, code change or conflicting interpretation, combined with incorrect assumptions, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0859 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that new law, code change or conflicting interpretation, combined with incorrect assumptions, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0860 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that new law, code change or conflicting interpretation, combined with incorrect assumptions, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Installation | Offshore Wind | Global / Multi-country | Installation | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0861 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that new law, code change or conflicting interpretation, combined with low technical maturity, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0862 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that new law, code change or conflicting interpretation, combined with low technical maturity, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0863 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that new law, code change or conflicting interpretation, combined with low technical maturity, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Owner’s Engineering | Transmission & Substations | North America | Installation | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0864 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that new law, code change or conflicting interpretation, combined with low technical maturity, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0865 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that new law, code change or conflicting interpretation, combined with low technical maturity, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Commissioning & Start-up | Hydropower | Europe | Commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0866 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that new law, code change or conflicting interpretation, combined with documentation gaps, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Installation | Marine Energy | South Asia | Installation | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0867 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that new law, code change or conflicting interpretation, combined with documentation gaps, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0868 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that new law, code change or conflicting interpretation, combined with documentation gaps, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Grid Interconnection | LNG | Latin America | Commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0869 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that new law, code change or conflicting interpretation, combined with documentation gaps, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0870 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that new law, code change or conflicting interpretation, combined with documentation gaps, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0871 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that new law, code change or conflicting interpretation, combined with external disruption, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0872 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that new law, code change or conflicting interpretation, combined with external disruption, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0873 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that new law, code change or conflicting interpretation, combined with external disruption, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0874 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that new law, code change or conflicting interpretation, combined with external disruption, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0875 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that new law, code change or conflicting interpretation, combined with external disruption, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0876 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that new law, code change or conflicting interpretation, combined with governance delay, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0877 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that new law, code change or conflicting interpretation, combined with governance delay, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0878 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that new law, code change or conflicting interpretation, combined with governance delay, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0879 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that new law, code change or conflicting interpretation, combined with governance delay, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Commissioning & Start-up | Geothermal | Middle East | Procurement | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0880 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that new law, code change or conflicting interpretation, combined with governance delay, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Decommissioning | LNG | South Asia | Manufacturing | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0881 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that new law, code change or conflicting interpretation, combined with commercial misalignment, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0882 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that new law, code change or conflicting interpretation, combined with commercial misalignment, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0883 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that new law, code change or conflicting interpretation, combined with commercial misalignment, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | R&D / Technology Development | Solar PV | Europe | Manufacturing | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0884 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that new law, code change or conflicting interpretation, combined with commercial misalignment, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Brownfield Modification | Battery Energy Storage | Africa | Construction | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0885 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that new law, code change or conflicting interpretation, combined with commercial misalignment, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0886 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that new law, code change or conflicting interpretation, combined with quality escape, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Decommissioning | Nuclear Power | Latin America | Manufacturing | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0887 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that new law, code change or conflicting interpretation, combined with quality escape, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0888 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that new law, code change or conflicting interpretation, combined with quality escape, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Installation | Pumped Storage | Middle East | Installation | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0889 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that new law, code change or conflicting interpretation, combined with quality escape, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0890 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that new law, code change or conflicting interpretation, combined with quality escape, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0891 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that new law, code change or conflicting interpretation, combined with access constraint, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0892 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that new law, code change or conflicting interpretation, combined with access constraint, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPCM | Offshore Wind | Europe | Pre-commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0893 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that new law, code change or conflicting interpretation, combined with access constraint, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0894 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that new law, code change or conflicting interpretation, combined with access constraint, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0895 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that new law, code change or conflicting interpretation, combined with access constraint, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0896 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that new law, code change or conflicting interpretation, combined with performance variability, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Legal Counsel | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0897 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that new law, code change or conflicting interpretation, combined with performance variability, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Legal Counsel | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0898 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that new law, code change or conflicting interpretation, combined with performance variability, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Legal Counsel | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0899 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that new law, code change or conflicting interpretation, combined with performance variability, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Legal Counsel | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0900 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that new law, code change or conflicting interpretation, combined with performance variability, may adversely affect project objectives through cost / time / quality consequences. | Regulatory & Change in Law | EPCM | Pumped Storage | Latin America | Detailed Engineering | Shared | M | Cost / Time / Quality | Establish controls for new law, code change or conflicting interpretation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Legal Counsel | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0901 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that late, incomplete or conditional approval, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0902 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that late, incomplete or conditional approval, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0903 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that late, incomplete or conditional approval, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0904 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that late, incomplete or conditional approval, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Grid Interconnection | Offshore Wind | North America | Procurement | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0905 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that late, incomplete or conditional approval, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0906 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that late, incomplete or conditional approval, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0907 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that late, incomplete or conditional approval, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0908 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that late, incomplete or conditional approval, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0909 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that late, incomplete or conditional approval, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPC / Turnkey | Hydropower | Latin America | Construction | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0910 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that late, incomplete or conditional approval, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Installation | Nuclear Power | Global / Multi-country | Installation | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0911 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that late, incomplete or conditional approval, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | R&D / Technology Development | Geothermal | Africa | Manufacturing | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0912 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that late, incomplete or conditional approval, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Brownfield Modification | LNG | East Asia | Construction | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0913 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that late, incomplete or conditional approval, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Owner’s Engineering | Onshore Wind | North America | Installation | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0914 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that late, incomplete or conditional approval, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0915 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that late, incomplete or conditional approval, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0916 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that late, incomplete or conditional approval, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Installation | Battery Energy Storage | South Asia | Installation | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0917 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that late, incomplete or conditional approval, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0918 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that late, incomplete or conditional approval, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0919 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that late, incomplete or conditional approval, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0920 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that late, incomplete or conditional approval, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0921 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that late, incomplete or conditional approval, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0922 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that late, incomplete or conditional approval, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Decommissioning | Marine Energy | North America | Operations / Handover | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0923 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that late, incomplete or conditional approval, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0924 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that late, incomplete or conditional approval, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Installation | LNG | Europe | FEED / Basic Design | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0925 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that late, incomplete or conditional approval, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0926 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that late, incomplete or conditional approval, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0927 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that late, incomplete or conditional approval, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0928 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that late, incomplete or conditional approval, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0929 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that late, incomplete or conditional approval, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0930 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that late, incomplete or conditional approval, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0931 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that late, incomplete or conditional approval, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Operations & Maintenance | District Energy | North America | Detailed Engineering | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0932 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that late, incomplete or conditional approval, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Grid Interconnection | Pumped Storage | Oceania | Procurement | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0933 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that late, incomplete or conditional approval, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0934 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that late, incomplete or conditional approval, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Brownfield Modification | Marine Energy | Africa | Construction | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0935 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that late, incomplete or conditional approval, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Owner’s Engineering | Geothermal | East Asia | Installation | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0936 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that late, incomplete or conditional approval, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Decommissioning | Offshore Wind | Latin America | Manufacturing | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0937 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that late, incomplete or conditional approval, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0938 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that late, incomplete or conditional approval, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Installation | Refining & Petrochemicals | Middle East | Installation | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0939 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that late, incomplete or conditional approval, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0940 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that late, incomplete or conditional approval, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0941 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that late, incomplete or conditional approval, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Owner’s Engineering | Hydropower | Oceania | Installation | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0942 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that late, incomplete or conditional approval, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPCM | Nuclear Power | Europe | Pre-commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0943 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that late, incomplete or conditional approval, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Commissioning & Start-up | District Energy | Africa | Commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0944 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that late, incomplete or conditional approval, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0945 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that late, incomplete or conditional approval, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0946 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that late, incomplete or conditional approval, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0947 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that late, incomplete or conditional approval, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0948 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that late, incomplete or conditional approval, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0949 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that late, incomplete or conditional approval, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0950 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that late, incomplete or conditional approval, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0951 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that late, incomplete or conditional approval, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0952 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that late, incomplete or conditional approval, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0953 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that late, incomplete or conditional approval, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0954 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that late, incomplete or conditional approval, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Grid Interconnection | Nuclear Power | North America | Procurement | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0955 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that late, incomplete or conditional approval, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | R&D / Technology Development | District Energy | Oceania | Manufacturing | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0956 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that late, incomplete or conditional approval, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPCM | LNG | Middle East | Detailed Engineering | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0957 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that late, incomplete or conditional approval, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0958 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that late, incomplete or conditional approval, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0959 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that late, incomplete or conditional approval, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0960 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that late, incomplete or conditional approval, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Installation | Offshore Wind | Global / Multi-country | Installation | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0961 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that late, incomplete or conditional approval, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0962 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that late, incomplete or conditional approval, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0963 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that late, incomplete or conditional approval, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Owner’s Engineering | Transmission & Substations | North America | Installation | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0964 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that late, incomplete or conditional approval, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0965 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that late, incomplete or conditional approval, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Commissioning & Start-up | Hydropower | Europe | Commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0966 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that late, incomplete or conditional approval, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Installation | Marine Energy | South Asia | Installation | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0967 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that late, incomplete or conditional approval, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0968 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that late, incomplete or conditional approval, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Grid Interconnection | LNG | Latin America | Commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0969 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that late, incomplete or conditional approval, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0970 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that late, incomplete or conditional approval, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0971 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that late, incomplete or conditional approval, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0972 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that late, incomplete or conditional approval, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0973 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that late, incomplete or conditional approval, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0974 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that late, incomplete or conditional approval, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0975 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that late, incomplete or conditional approval, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0976 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that late, incomplete or conditional approval, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0977 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that late, incomplete or conditional approval, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0978 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that late, incomplete or conditional approval, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0979 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that late, incomplete or conditional approval, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Commissioning & Start-up | Geothermal | Middle East | Procurement | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0980 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that late, incomplete or conditional approval, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Decommissioning | LNG | South Asia | Manufacturing | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0981 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that late, incomplete or conditional approval, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0982 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that late, incomplete or conditional approval, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0983 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that late, incomplete or conditional approval, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | R&D / Technology Development | Solar PV | Europe | Manufacturing | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0984 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that late, incomplete or conditional approval, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Brownfield Modification | Battery Energy Storage | Africa | Construction | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0985 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that late, incomplete or conditional approval, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0986 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that late, incomplete or conditional approval, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Decommissioning | Nuclear Power | Latin America | Manufacturing | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0987 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that late, incomplete or conditional approval, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0988 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that late, incomplete or conditional approval, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Installation | Pumped Storage | Middle East | Installation | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0989 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that late, incomplete or conditional approval, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0990 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that late, incomplete or conditional approval, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0991 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that late, incomplete or conditional approval, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0992 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that late, incomplete or conditional approval, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPCM | Offshore Wind | Europe | Pre-commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0993 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that late, incomplete or conditional approval, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0994 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that late, incomplete or conditional approval, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0995 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that late, incomplete or conditional approval, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0996 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that late, incomplete or conditional approval, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Permitting Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0997 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that late, incomplete or conditional approval, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Permitting Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0998 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that late, incomplete or conditional approval, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Permitting Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-0999 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that late, incomplete or conditional approval, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Permitting Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1000 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that late, incomplete or conditional approval, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Permits & Approvals | EPCM | Pumped Storage | Latin America | Detailed Engineering | Employer | H | Time / Cost | Establish controls for late, incomplete or conditional approval; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Permitting Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1001 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that unexpected geology, utilities or contamination, combined with insufficient planning, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1002 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that unexpected geology, utilities or contamination, combined with insufficient planning, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1003 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that unexpected geology, utilities or contamination, combined with insufficient planning, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1004 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that unexpected geology, utilities or contamination, combined with insufficient planning, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Grid Interconnection | Offshore Wind | North America | Procurement | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1005 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that unexpected geology, utilities or contamination, combined with insufficient planning, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1006 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that unexpected geology, utilities or contamination, combined with incomplete information, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1007 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that unexpected geology, utilities or contamination, combined with incomplete information, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1008 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that unexpected geology, utilities or contamination, combined with incomplete information, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1009 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that unexpected geology, utilities or contamination, combined with incomplete information, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPC / Turnkey | Hydropower | Latin America | Construction | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1010 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that unexpected geology, utilities or contamination, combined with incomplete information, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Installation | Nuclear Power | Global / Multi-country | Installation | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1011 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that unexpected geology, utilities or contamination, combined with late decision-making, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | R&D / Technology Development | Geothermal | Africa | Manufacturing | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1012 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that unexpected geology, utilities or contamination, combined with late decision-making, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Brownfield Modification | LNG | East Asia | Construction | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1013 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that unexpected geology, utilities or contamination, combined with late decision-making, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Owner’s Engineering | Onshore Wind | North America | Installation | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1014 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that unexpected geology, utilities or contamination, combined with late decision-making, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1015 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that unexpected geology, utilities or contamination, combined with late decision-making, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1016 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that unexpected geology, utilities or contamination, combined with weak controls, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Installation | Battery Energy Storage | South Asia | Installation | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1017 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that unexpected geology, utilities or contamination, combined with weak controls, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1018 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that unexpected geology, utilities or contamination, combined with weak controls, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1019 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that unexpected geology, utilities or contamination, combined with weak controls, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1020 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that unexpected geology, utilities or contamination, combined with weak controls, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1021 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that unexpected geology, utilities or contamination, combined with resource constraints, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1022 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that unexpected geology, utilities or contamination, combined with resource constraints, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Decommissioning | Marine Energy | North America | Operations / Handover | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1023 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that unexpected geology, utilities or contamination, combined with resource constraints, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1024 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that unexpected geology, utilities or contamination, combined with resource constraints, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Installation | LNG | Europe | FEED / Basic Design | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1025 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that unexpected geology, utilities or contamination, combined with resource constraints, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1026 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that unexpected geology, utilities or contamination, combined with supplier dependency, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1027 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that unexpected geology, utilities or contamination, combined with supplier dependency, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1028 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that unexpected geology, utilities or contamination, combined with supplier dependency, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1029 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that unexpected geology, utilities or contamination, combined with supplier dependency, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1030 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that unexpected geology, utilities or contamination, combined with supplier dependency, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1031 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that unexpected geology, utilities or contamination, combined with interface complexity, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Operations & Maintenance | District Energy | North America | Detailed Engineering | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1032 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that unexpected geology, utilities or contamination, combined with interface complexity, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Grid Interconnection | Pumped Storage | Oceania | Procurement | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1033 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that unexpected geology, utilities or contamination, combined with interface complexity, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1034 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that unexpected geology, utilities or contamination, combined with interface complexity, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Brownfield Modification | Marine Energy | Africa | Construction | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1035 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that unexpected geology, utilities or contamination, combined with interface complexity, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Owner’s Engineering | Geothermal | East Asia | Installation | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1036 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that unexpected geology, utilities or contamination, combined with requirements volatility, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Decommissioning | Offshore Wind | Latin America | Manufacturing | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1037 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that unexpected geology, utilities or contamination, combined with requirements volatility, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1038 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that unexpected geology, utilities or contamination, combined with requirements volatility, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Installation | Refining & Petrochemicals | Middle East | Installation | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1039 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that unexpected geology, utilities or contamination, combined with requirements volatility, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1040 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that unexpected geology, utilities or contamination, combined with requirements volatility, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1041 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that unexpected geology, utilities or contamination, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Owner’s Engineering | Hydropower | Oceania | Installation | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1042 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that unexpected geology, utilities or contamination, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPCM | Nuclear Power | Europe | Pre-commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1043 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that unexpected geology, utilities or contamination, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Commissioning & Start-up | District Energy | Africa | Commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1044 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that unexpected geology, utilities or contamination, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1045 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that unexpected geology, utilities or contamination, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1046 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that unexpected geology, utilities or contamination, combined with inadequate verification, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1047 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that unexpected geology, utilities or contamination, combined with inadequate verification, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1048 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that unexpected geology, utilities or contamination, combined with inadequate verification, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1049 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that unexpected geology, utilities or contamination, combined with inadequate verification, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1050 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that unexpected geology, utilities or contamination, combined with inadequate verification, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1051 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that unexpected geology, utilities or contamination, combined with poor communication, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1052 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that unexpected geology, utilities or contamination, combined with poor communication, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1053 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that unexpected geology, utilities or contamination, combined with poor communication, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1054 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that unexpected geology, utilities or contamination, combined with poor communication, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Grid Interconnection | Nuclear Power | North America | Procurement | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1055 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that unexpected geology, utilities or contamination, combined with poor communication, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | R&D / Technology Development | District Energy | Oceania | Manufacturing | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1056 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that unexpected geology, utilities or contamination, combined with incorrect assumptions, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPCM | LNG | Middle East | Detailed Engineering | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1057 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that unexpected geology, utilities or contamination, combined with incorrect assumptions, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1058 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that unexpected geology, utilities or contamination, combined with incorrect assumptions, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1059 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that unexpected geology, utilities or contamination, combined with incorrect assumptions, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1060 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that unexpected geology, utilities or contamination, combined with incorrect assumptions, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Installation | Offshore Wind | Global / Multi-country | Installation | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1061 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that unexpected geology, utilities or contamination, combined with low technical maturity, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1062 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that unexpected geology, utilities or contamination, combined with low technical maturity, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1063 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that unexpected geology, utilities or contamination, combined with low technical maturity, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Owner’s Engineering | Transmission & Substations | North America | Installation | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1064 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that unexpected geology, utilities or contamination, combined with low technical maturity, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1065 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that unexpected geology, utilities or contamination, combined with low technical maturity, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Commissioning & Start-up | Hydropower | Europe | Commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1066 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that unexpected geology, utilities or contamination, combined with documentation gaps, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Installation | Marine Energy | South Asia | Installation | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1067 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that unexpected geology, utilities or contamination, combined with documentation gaps, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1068 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that unexpected geology, utilities or contamination, combined with documentation gaps, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Grid Interconnection | LNG | Latin America | Commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1069 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that unexpected geology, utilities or contamination, combined with documentation gaps, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1070 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that unexpected geology, utilities or contamination, combined with documentation gaps, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1071 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that unexpected geology, utilities or contamination, combined with external disruption, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1072 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that unexpected geology, utilities or contamination, combined with external disruption, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1073 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that unexpected geology, utilities or contamination, combined with external disruption, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1074 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that unexpected geology, utilities or contamination, combined with external disruption, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1075 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that unexpected geology, utilities or contamination, combined with external disruption, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1076 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that unexpected geology, utilities or contamination, combined with governance delay, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1077 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that unexpected geology, utilities or contamination, combined with governance delay, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1078 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that unexpected geology, utilities or contamination, combined with governance delay, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1079 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that unexpected geology, utilities or contamination, combined with governance delay, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Commissioning & Start-up | Geothermal | Middle East | Procurement | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1080 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that unexpected geology, utilities or contamination, combined with governance delay, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Decommissioning | LNG | South Asia | Manufacturing | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1081 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that unexpected geology, utilities or contamination, combined with commercial misalignment, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1082 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that unexpected geology, utilities or contamination, combined with commercial misalignment, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1083 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that unexpected geology, utilities or contamination, combined with commercial misalignment, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | R&D / Technology Development | Solar PV | Europe | Manufacturing | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1084 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that unexpected geology, utilities or contamination, combined with commercial misalignment, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Brownfield Modification | Battery Energy Storage | Africa | Construction | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1085 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that unexpected geology, utilities or contamination, combined with commercial misalignment, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1086 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that unexpected geology, utilities or contamination, combined with quality escape, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Decommissioning | Nuclear Power | Latin America | Manufacturing | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1087 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that unexpected geology, utilities or contamination, combined with quality escape, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1088 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that unexpected geology, utilities or contamination, combined with quality escape, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Installation | Pumped Storage | Middle East | Installation | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1089 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that unexpected geology, utilities or contamination, combined with quality escape, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1090 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that unexpected geology, utilities or contamination, combined with quality escape, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1091 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that unexpected geology, utilities or contamination, combined with access constraint, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1092 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that unexpected geology, utilities or contamination, combined with access constraint, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPCM | Offshore Wind | Europe | Pre-commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1093 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that unexpected geology, utilities or contamination, combined with access constraint, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1094 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that unexpected geology, utilities or contamination, combined with access constraint, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1095 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that unexpected geology, utilities or contamination, combined with access constraint, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1096 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that unexpected geology, utilities or contamination, combined with performance variability, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1097 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that unexpected geology, utilities or contamination, combined with performance variability, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1098 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that unexpected geology, utilities or contamination, combined with performance variability, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1099 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that unexpected geology, utilities or contamination, combined with performance variability, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1100 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that unexpected geology, utilities or contamination, combined with performance variability, may adversely affect project objectives through cost / time / hse consequences. | Site & Ground Conditions | EPCM | Pumped Storage | Latin America | Detailed Engineering | Shared | M | Cost / Time / HSE | Establish controls for unexpected geology, utilities or contamination; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1101 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that extreme weather or natural hazard, combined with insufficient planning, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1102 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that extreme weather or natural hazard, combined with insufficient planning, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1103 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that extreme weather or natural hazard, combined with insufficient planning, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1104 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that extreme weather or natural hazard, combined with insufficient planning, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Grid Interconnection | Offshore Wind | North America | Procurement | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1105 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that extreme weather or natural hazard, combined with insufficient planning, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1106 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that extreme weather or natural hazard, combined with incomplete information, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1107 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that extreme weather or natural hazard, combined with incomplete information, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1108 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that extreme weather or natural hazard, combined with incomplete information, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1109 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that extreme weather or natural hazard, combined with incomplete information, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPC / Turnkey | Hydropower | Latin America | Construction | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1110 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that extreme weather or natural hazard, combined with incomplete information, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Installation | Nuclear Power | Global / Multi-country | Installation | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1111 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that extreme weather or natural hazard, combined with late decision-making, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | R&D / Technology Development | Geothermal | Africa | Manufacturing | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1112 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that extreme weather or natural hazard, combined with late decision-making, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Brownfield Modification | LNG | East Asia | Construction | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1113 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that extreme weather or natural hazard, combined with late decision-making, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Owner’s Engineering | Onshore Wind | North America | Installation | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1114 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that extreme weather or natural hazard, combined with late decision-making, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1115 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that extreme weather or natural hazard, combined with late decision-making, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1116 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that extreme weather or natural hazard, combined with weak controls, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Installation | Battery Energy Storage | South Asia | Installation | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1117 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that extreme weather or natural hazard, combined with weak controls, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1118 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that extreme weather or natural hazard, combined with weak controls, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1119 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that extreme weather or natural hazard, combined with weak controls, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1120 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that extreme weather or natural hazard, combined with weak controls, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1121 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that extreme weather or natural hazard, combined with resource constraints, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1122 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that extreme weather or natural hazard, combined with resource constraints, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Decommissioning | Marine Energy | North America | Operations / Handover | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1123 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that extreme weather or natural hazard, combined with resource constraints, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1124 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that extreme weather or natural hazard, combined with resource constraints, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Installation | LNG | Europe | FEED / Basic Design | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1125 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that extreme weather or natural hazard, combined with resource constraints, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1126 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that extreme weather or natural hazard, combined with supplier dependency, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1127 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that extreme weather or natural hazard, combined with supplier dependency, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1128 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that extreme weather or natural hazard, combined with supplier dependency, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1129 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that extreme weather or natural hazard, combined with supplier dependency, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1130 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that extreme weather or natural hazard, combined with supplier dependency, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1131 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that extreme weather or natural hazard, combined with interface complexity, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Operations & Maintenance | District Energy | North America | Detailed Engineering | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1132 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that extreme weather or natural hazard, combined with interface complexity, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Grid Interconnection | Pumped Storage | Oceania | Procurement | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1133 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that extreme weather or natural hazard, combined with interface complexity, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1134 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that extreme weather or natural hazard, combined with interface complexity, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Brownfield Modification | Marine Energy | Africa | Construction | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1135 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that extreme weather or natural hazard, combined with interface complexity, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Owner’s Engineering | Geothermal | East Asia | Installation | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1136 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that extreme weather or natural hazard, combined with requirements volatility, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Decommissioning | Offshore Wind | Latin America | Manufacturing | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1137 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that extreme weather or natural hazard, combined with requirements volatility, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1138 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that extreme weather or natural hazard, combined with requirements volatility, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Installation | Refining & Petrochemicals | Middle East | Installation | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1139 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that extreme weather or natural hazard, combined with requirements volatility, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1140 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that extreme weather or natural hazard, combined with requirements volatility, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1141 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that extreme weather or natural hazard, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Owner’s Engineering | Hydropower | Oceania | Installation | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1142 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that extreme weather or natural hazard, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPCM | Nuclear Power | Europe | Pre-commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1143 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that extreme weather or natural hazard, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Commissioning & Start-up | District Energy | Africa | Commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1144 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that extreme weather or natural hazard, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1145 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that extreme weather or natural hazard, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1146 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that extreme weather or natural hazard, combined with inadequate verification, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1147 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that extreme weather or natural hazard, combined with inadequate verification, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1148 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that extreme weather or natural hazard, combined with inadequate verification, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1149 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that extreme weather or natural hazard, combined with inadequate verification, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1150 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that extreme weather or natural hazard, combined with inadequate verification, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1151 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that extreme weather or natural hazard, combined with poor communication, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1152 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that extreme weather or natural hazard, combined with poor communication, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1153 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that extreme weather or natural hazard, combined with poor communication, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1154 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that extreme weather or natural hazard, combined with poor communication, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Grid Interconnection | Nuclear Power | North America | Procurement | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1155 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that extreme weather or natural hazard, combined with poor communication, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | R&D / Technology Development | District Energy | Oceania | Manufacturing | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1156 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that extreme weather or natural hazard, combined with incorrect assumptions, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPCM | LNG | Middle East | Detailed Engineering | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1157 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that extreme weather or natural hazard, combined with incorrect assumptions, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1158 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that extreme weather or natural hazard, combined with incorrect assumptions, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1159 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that extreme weather or natural hazard, combined with incorrect assumptions, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1160 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that extreme weather or natural hazard, combined with incorrect assumptions, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Installation | Offshore Wind | Global / Multi-country | Installation | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1161 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that extreme weather or natural hazard, combined with low technical maturity, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1162 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that extreme weather or natural hazard, combined with low technical maturity, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1163 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that extreme weather or natural hazard, combined with low technical maturity, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Owner’s Engineering | Transmission & Substations | North America | Installation | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1164 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that extreme weather or natural hazard, combined with low technical maturity, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1165 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that extreme weather or natural hazard, combined with low technical maturity, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Commissioning & Start-up | Hydropower | Europe | Commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1166 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that extreme weather or natural hazard, combined with documentation gaps, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Installation | Marine Energy | South Asia | Installation | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1167 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that extreme weather or natural hazard, combined with documentation gaps, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1168 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that extreme weather or natural hazard, combined with documentation gaps, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Grid Interconnection | LNG | Latin America | Commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1169 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that extreme weather or natural hazard, combined with documentation gaps, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1170 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that extreme weather or natural hazard, combined with documentation gaps, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1171 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that extreme weather or natural hazard, combined with external disruption, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1172 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that extreme weather or natural hazard, combined with external disruption, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1173 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that extreme weather or natural hazard, combined with external disruption, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1174 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that extreme weather or natural hazard, combined with external disruption, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1175 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that extreme weather or natural hazard, combined with external disruption, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1176 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that extreme weather or natural hazard, combined with governance delay, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1177 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that extreme weather or natural hazard, combined with governance delay, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1178 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that extreme weather or natural hazard, combined with governance delay, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1179 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that extreme weather or natural hazard, combined with governance delay, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Commissioning & Start-up | Geothermal | Middle East | Procurement | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1180 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that extreme weather or natural hazard, combined with governance delay, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Decommissioning | LNG | South Asia | Manufacturing | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1181 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that extreme weather or natural hazard, combined with commercial misalignment, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1182 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that extreme weather or natural hazard, combined with commercial misalignment, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1183 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that extreme weather or natural hazard, combined with commercial misalignment, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | R&D / Technology Development | Solar PV | Europe | Manufacturing | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1184 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that extreme weather or natural hazard, combined with commercial misalignment, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Brownfield Modification | Battery Energy Storage | Africa | Construction | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1185 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that extreme weather or natural hazard, combined with commercial misalignment, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1186 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that extreme weather or natural hazard, combined with quality escape, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Decommissioning | Nuclear Power | Latin America | Manufacturing | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1187 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that extreme weather or natural hazard, combined with quality escape, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1188 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that extreme weather or natural hazard, combined with quality escape, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Installation | Pumped Storage | Middle East | Installation | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1189 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that extreme weather or natural hazard, combined with quality escape, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1190 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that extreme weather or natural hazard, combined with quality escape, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1191 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that extreme weather or natural hazard, combined with access constraint, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1192 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that extreme weather or natural hazard, combined with access constraint, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPCM | Offshore Wind | Europe | Pre-commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1193 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that extreme weather or natural hazard, combined with access constraint, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1194 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that extreme weather or natural hazard, combined with access constraint, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1195 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that extreme weather or natural hazard, combined with access constraint, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1196 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that extreme weather or natural hazard, combined with performance variability, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1197 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that extreme weather or natural hazard, combined with performance variability, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1198 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that extreme weather or natural hazard, combined with performance variability, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1199 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that extreme weather or natural hazard, combined with performance variability, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1200 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that extreme weather or natural hazard, combined with performance variability, may adversely affect project objectives through time / cost / hse consequences. | Weather & Natural Hazards | EPCM | Pumped Storage | Latin America | Detailed Engineering | Shared | M | Time / Cost / HSE | Establish controls for extreme weather or natural hazard; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1201 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that war, pandemic, disaster or government shutdown, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1202 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that war, pandemic, disaster or government shutdown, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1203 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that war, pandemic, disaster or government shutdown, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1204 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that war, pandemic, disaster or government shutdown, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Grid Interconnection | Offshore Wind | North America | Procurement | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1205 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that war, pandemic, disaster or government shutdown, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1206 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that war, pandemic, disaster or government shutdown, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1207 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that war, pandemic, disaster or government shutdown, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1208 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that war, pandemic, disaster or government shutdown, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1209 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that war, pandemic, disaster or government shutdown, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPC / Turnkey | Hydropower | Latin America | Construction | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1210 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that war, pandemic, disaster or government shutdown, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Installation | Nuclear Power | Global / Multi-country | Installation | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1211 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that war, pandemic, disaster or government shutdown, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | R&D / Technology Development | Geothermal | Africa | Manufacturing | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1212 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that war, pandemic, disaster or government shutdown, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Brownfield Modification | LNG | East Asia | Construction | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1213 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that war, pandemic, disaster or government shutdown, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Owner’s Engineering | Onshore Wind | North America | Installation | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1214 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that war, pandemic, disaster or government shutdown, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1215 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that war, pandemic, disaster or government shutdown, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1216 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that war, pandemic, disaster or government shutdown, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Installation | Battery Energy Storage | South Asia | Installation | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1217 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that war, pandemic, disaster or government shutdown, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1218 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that war, pandemic, disaster or government shutdown, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1219 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that war, pandemic, disaster or government shutdown, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1220 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that war, pandemic, disaster or government shutdown, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1221 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that war, pandemic, disaster or government shutdown, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1222 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that war, pandemic, disaster or government shutdown, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Decommissioning | Marine Energy | North America | Operations / Handover | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1223 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that war, pandemic, disaster or government shutdown, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1224 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that war, pandemic, disaster or government shutdown, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Installation | LNG | Europe | FEED / Basic Design | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1225 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that war, pandemic, disaster or government shutdown, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1226 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that war, pandemic, disaster or government shutdown, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1227 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that war, pandemic, disaster or government shutdown, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1228 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that war, pandemic, disaster or government shutdown, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1229 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that war, pandemic, disaster or government shutdown, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1230 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that war, pandemic, disaster or government shutdown, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1231 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that war, pandemic, disaster or government shutdown, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Operations & Maintenance | District Energy | North America | Detailed Engineering | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1232 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that war, pandemic, disaster or government shutdown, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Grid Interconnection | Pumped Storage | Oceania | Procurement | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1233 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that war, pandemic, disaster or government shutdown, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1234 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that war, pandemic, disaster or government shutdown, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Brownfield Modification | Marine Energy | Africa | Construction | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1235 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that war, pandemic, disaster or government shutdown, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Owner’s Engineering | Geothermal | East Asia | Installation | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1236 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that war, pandemic, disaster or government shutdown, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Decommissioning | Offshore Wind | Latin America | Manufacturing | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1237 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that war, pandemic, disaster or government shutdown, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1238 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that war, pandemic, disaster or government shutdown, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Installation | Refining & Petrochemicals | Middle East | Installation | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1239 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that war, pandemic, disaster or government shutdown, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1240 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that war, pandemic, disaster or government shutdown, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1241 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that war, pandemic, disaster or government shutdown, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Owner’s Engineering | Hydropower | Oceania | Installation | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1242 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that war, pandemic, disaster or government shutdown, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPCM | Nuclear Power | Europe | Pre-commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1243 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that war, pandemic, disaster or government shutdown, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Commissioning & Start-up | District Energy | Africa | Commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1244 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that war, pandemic, disaster or government shutdown, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1245 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that war, pandemic, disaster or government shutdown, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1246 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that war, pandemic, disaster or government shutdown, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1247 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that war, pandemic, disaster or government shutdown, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1248 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that war, pandemic, disaster or government shutdown, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1249 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that war, pandemic, disaster or government shutdown, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1250 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that war, pandemic, disaster or government shutdown, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1251 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that war, pandemic, disaster or government shutdown, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1252 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that war, pandemic, disaster or government shutdown, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1253 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that war, pandemic, disaster or government shutdown, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1254 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that war, pandemic, disaster or government shutdown, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Grid Interconnection | Nuclear Power | North America | Procurement | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1255 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that war, pandemic, disaster or government shutdown, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | R&D / Technology Development | District Energy | Oceania | Manufacturing | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1256 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that war, pandemic, disaster or government shutdown, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPCM | LNG | Middle East | Detailed Engineering | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1257 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that war, pandemic, disaster or government shutdown, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1258 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that war, pandemic, disaster or government shutdown, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1259 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that war, pandemic, disaster or government shutdown, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1260 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that war, pandemic, disaster or government shutdown, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Installation | Offshore Wind | Global / Multi-country | Installation | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1261 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that war, pandemic, disaster or government shutdown, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1262 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that war, pandemic, disaster or government shutdown, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1263 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that war, pandemic, disaster or government shutdown, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Owner’s Engineering | Transmission & Substations | North America | Installation | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1264 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that war, pandemic, disaster or government shutdown, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1265 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that war, pandemic, disaster or government shutdown, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Commissioning & Start-up | Hydropower | Europe | Commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1266 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that war, pandemic, disaster or government shutdown, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Installation | Marine Energy | South Asia | Installation | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1267 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that war, pandemic, disaster or government shutdown, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1268 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that war, pandemic, disaster or government shutdown, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Grid Interconnection | LNG | Latin America | Commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1269 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that war, pandemic, disaster or government shutdown, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1270 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that war, pandemic, disaster or government shutdown, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1271 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that war, pandemic, disaster or government shutdown, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1272 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that war, pandemic, disaster or government shutdown, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1273 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that war, pandemic, disaster or government shutdown, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1274 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that war, pandemic, disaster or government shutdown, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1275 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that war, pandemic, disaster or government shutdown, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1276 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that war, pandemic, disaster or government shutdown, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1277 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that war, pandemic, disaster or government shutdown, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1278 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that war, pandemic, disaster or government shutdown, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1279 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that war, pandemic, disaster or government shutdown, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Commissioning & Start-up | Geothermal | Middle East | Procurement | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1280 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that war, pandemic, disaster or government shutdown, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Decommissioning | LNG | South Asia | Manufacturing | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1281 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that war, pandemic, disaster or government shutdown, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1282 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that war, pandemic, disaster or government shutdown, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1283 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that war, pandemic, disaster or government shutdown, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | R&D / Technology Development | Solar PV | Europe | Manufacturing | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1284 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that war, pandemic, disaster or government shutdown, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Brownfield Modification | Battery Energy Storage | Africa | Construction | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1285 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that war, pandemic, disaster or government shutdown, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1286 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that war, pandemic, disaster or government shutdown, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Decommissioning | Nuclear Power | Latin America | Manufacturing | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1287 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that war, pandemic, disaster or government shutdown, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1288 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that war, pandemic, disaster or government shutdown, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Installation | Pumped Storage | Middle East | Installation | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1289 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that war, pandemic, disaster or government shutdown, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1290 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that war, pandemic, disaster or government shutdown, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1291 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that war, pandemic, disaster or government shutdown, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1292 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that war, pandemic, disaster or government shutdown, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPCM | Offshore Wind | Europe | Pre-commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1293 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that war, pandemic, disaster or government shutdown, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1294 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that war, pandemic, disaster or government shutdown, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1295 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that war, pandemic, disaster or government shutdown, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1296 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that war, pandemic, disaster or government shutdown, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1297 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that war, pandemic, disaster or government shutdown, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1298 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that war, pandemic, disaster or government shutdown, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1299 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that war, pandemic, disaster or government shutdown, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1300 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that war, pandemic, disaster or government shutdown, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Force Majeure / Exceptional Events | EPCM | Pumped Storage | Latin America | Detailed Engineering | Shared | L | Time / Cost | Establish controls for war, pandemic, disaster or government shutdown; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1301 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that supplier failure, scarcity or long-lead delay, combined with insufficient planning, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1302 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that supplier failure, scarcity or long-lead delay, combined with insufficient planning, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1303 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that supplier failure, scarcity or long-lead delay, combined with insufficient planning, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1304 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that supplier failure, scarcity or long-lead delay, combined with insufficient planning, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Grid Interconnection | Offshore Wind | North America | Procurement | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1305 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that supplier failure, scarcity or long-lead delay, combined with insufficient planning, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1306 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that supplier failure, scarcity or long-lead delay, combined with incomplete information, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1307 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that supplier failure, scarcity or long-lead delay, combined with incomplete information, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1308 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that supplier failure, scarcity or long-lead delay, combined with incomplete information, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1309 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that supplier failure, scarcity or long-lead delay, combined with incomplete information, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPC / Turnkey | Hydropower | Latin America | Construction | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1310 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that supplier failure, scarcity or long-lead delay, combined with incomplete information, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Installation | Nuclear Power | Global / Multi-country | Installation | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1311 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that supplier failure, scarcity or long-lead delay, combined with late decision-making, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | R&D / Technology Development | Geothermal | Africa | Manufacturing | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1312 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that supplier failure, scarcity or long-lead delay, combined with late decision-making, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Brownfield Modification | LNG | East Asia | Construction | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1313 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that supplier failure, scarcity or long-lead delay, combined with late decision-making, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Owner’s Engineering | Onshore Wind | North America | Installation | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1314 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that supplier failure, scarcity or long-lead delay, combined with late decision-making, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1315 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that supplier failure, scarcity or long-lead delay, combined with late decision-making, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1316 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that supplier failure, scarcity or long-lead delay, combined with weak controls, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Installation | Battery Energy Storage | South Asia | Installation | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1317 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that supplier failure, scarcity or long-lead delay, combined with weak controls, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1318 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that supplier failure, scarcity or long-lead delay, combined with weak controls, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1319 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that supplier failure, scarcity or long-lead delay, combined with weak controls, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1320 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that supplier failure, scarcity or long-lead delay, combined with weak controls, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1321 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that supplier failure, scarcity or long-lead delay, combined with resource constraints, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1322 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that supplier failure, scarcity or long-lead delay, combined with resource constraints, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Decommissioning | Marine Energy | North America | Operations / Handover | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1323 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that supplier failure, scarcity or long-lead delay, combined with resource constraints, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1324 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that supplier failure, scarcity or long-lead delay, combined with resource constraints, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Installation | LNG | Europe | FEED / Basic Design | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1325 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that supplier failure, scarcity or long-lead delay, combined with resource constraints, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1326 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that supplier failure, scarcity or long-lead delay, combined with supplier dependency, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1327 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that supplier failure, scarcity or long-lead delay, combined with supplier dependency, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1328 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that supplier failure, scarcity or long-lead delay, combined with supplier dependency, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1329 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that supplier failure, scarcity or long-lead delay, combined with supplier dependency, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1330 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that supplier failure, scarcity or long-lead delay, combined with supplier dependency, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1331 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that supplier failure, scarcity or long-lead delay, combined with interface complexity, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Operations & Maintenance | District Energy | North America | Detailed Engineering | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1332 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that supplier failure, scarcity or long-lead delay, combined with interface complexity, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Grid Interconnection | Pumped Storage | Oceania | Procurement | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1333 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that supplier failure, scarcity or long-lead delay, combined with interface complexity, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1334 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that supplier failure, scarcity or long-lead delay, combined with interface complexity, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Brownfield Modification | Marine Energy | Africa | Construction | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1335 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that supplier failure, scarcity or long-lead delay, combined with interface complexity, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Owner’s Engineering | Geothermal | East Asia | Installation | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1336 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that supplier failure, scarcity or long-lead delay, combined with requirements volatility, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Decommissioning | Offshore Wind | Latin America | Manufacturing | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1337 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that supplier failure, scarcity or long-lead delay, combined with requirements volatility, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1338 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that supplier failure, scarcity or long-lead delay, combined with requirements volatility, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Installation | Refining & Petrochemicals | Middle East | Installation | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1339 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that supplier failure, scarcity or long-lead delay, combined with requirements volatility, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1340 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that supplier failure, scarcity or long-lead delay, combined with requirements volatility, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1341 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that supplier failure, scarcity or long-lead delay, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Owner’s Engineering | Hydropower | Oceania | Installation | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1342 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that supplier failure, scarcity or long-lead delay, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPCM | Nuclear Power | Europe | Pre-commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1343 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that supplier failure, scarcity or long-lead delay, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Commissioning & Start-up | District Energy | Africa | Commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1344 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that supplier failure, scarcity or long-lead delay, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1345 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that supplier failure, scarcity or long-lead delay, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1346 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that supplier failure, scarcity or long-lead delay, combined with inadequate verification, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1347 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that supplier failure, scarcity or long-lead delay, combined with inadequate verification, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1348 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that supplier failure, scarcity or long-lead delay, combined with inadequate verification, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1349 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that supplier failure, scarcity or long-lead delay, combined with inadequate verification, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1350 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that supplier failure, scarcity or long-lead delay, combined with inadequate verification, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1351 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that supplier failure, scarcity or long-lead delay, combined with poor communication, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1352 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that supplier failure, scarcity or long-lead delay, combined with poor communication, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1353 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that supplier failure, scarcity or long-lead delay, combined with poor communication, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1354 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that supplier failure, scarcity or long-lead delay, combined with poor communication, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Grid Interconnection | Nuclear Power | North America | Procurement | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1355 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that supplier failure, scarcity or long-lead delay, combined with poor communication, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | R&D / Technology Development | District Energy | Oceania | Manufacturing | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1356 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that supplier failure, scarcity or long-lead delay, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPCM | LNG | Middle East | Detailed Engineering | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1357 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that supplier failure, scarcity or long-lead delay, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1358 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that supplier failure, scarcity or long-lead delay, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1359 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that supplier failure, scarcity or long-lead delay, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1360 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that supplier failure, scarcity or long-lead delay, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Installation | Offshore Wind | Global / Multi-country | Installation | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1361 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that supplier failure, scarcity or long-lead delay, combined with low technical maturity, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1362 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that supplier failure, scarcity or long-lead delay, combined with low technical maturity, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1363 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that supplier failure, scarcity or long-lead delay, combined with low technical maturity, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Owner’s Engineering | Transmission & Substations | North America | Installation | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1364 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that supplier failure, scarcity or long-lead delay, combined with low technical maturity, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1365 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that supplier failure, scarcity or long-lead delay, combined with low technical maturity, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Commissioning & Start-up | Hydropower | Europe | Commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1366 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that supplier failure, scarcity or long-lead delay, combined with documentation gaps, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Installation | Marine Energy | South Asia | Installation | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1367 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that supplier failure, scarcity or long-lead delay, combined with documentation gaps, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1368 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that supplier failure, scarcity or long-lead delay, combined with documentation gaps, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Grid Interconnection | LNG | Latin America | Commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1369 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that supplier failure, scarcity or long-lead delay, combined with documentation gaps, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1370 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that supplier failure, scarcity or long-lead delay, combined with documentation gaps, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1371 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that supplier failure, scarcity or long-lead delay, combined with external disruption, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1372 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that supplier failure, scarcity or long-lead delay, combined with external disruption, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1373 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that supplier failure, scarcity or long-lead delay, combined with external disruption, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1374 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that supplier failure, scarcity or long-lead delay, combined with external disruption, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1375 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that supplier failure, scarcity or long-lead delay, combined with external disruption, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1376 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that supplier failure, scarcity or long-lead delay, combined with governance delay, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1377 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that supplier failure, scarcity or long-lead delay, combined with governance delay, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1378 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that supplier failure, scarcity or long-lead delay, combined with governance delay, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1379 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that supplier failure, scarcity or long-lead delay, combined with governance delay, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Commissioning & Start-up | Geothermal | Middle East | Procurement | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1380 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that supplier failure, scarcity or long-lead delay, combined with governance delay, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Decommissioning | LNG | South Asia | Manufacturing | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1381 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that supplier failure, scarcity or long-lead delay, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1382 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that supplier failure, scarcity or long-lead delay, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1383 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that supplier failure, scarcity or long-lead delay, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | R&D / Technology Development | Solar PV | Europe | Manufacturing | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1384 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that supplier failure, scarcity or long-lead delay, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Brownfield Modification | Battery Energy Storage | Africa | Construction | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1385 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that supplier failure, scarcity or long-lead delay, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1386 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that supplier failure, scarcity or long-lead delay, combined with quality escape, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Decommissioning | Nuclear Power | Latin America | Manufacturing | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1387 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that supplier failure, scarcity or long-lead delay, combined with quality escape, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1388 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that supplier failure, scarcity or long-lead delay, combined with quality escape, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Installation | Pumped Storage | Middle East | Installation | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1389 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that supplier failure, scarcity or long-lead delay, combined with quality escape, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1390 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that supplier failure, scarcity or long-lead delay, combined with quality escape, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1391 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that supplier failure, scarcity or long-lead delay, combined with access constraint, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1392 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that supplier failure, scarcity or long-lead delay, combined with access constraint, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPCM | Offshore Wind | Europe | Pre-commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1393 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that supplier failure, scarcity or long-lead delay, combined with access constraint, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1394 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that supplier failure, scarcity or long-lead delay, combined with access constraint, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1395 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that supplier failure, scarcity or long-lead delay, combined with access constraint, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1396 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that supplier failure, scarcity or long-lead delay, combined with performance variability, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Procurement Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1397 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that supplier failure, scarcity or long-lead delay, combined with performance variability, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Procurement Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1398 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that supplier failure, scarcity or long-lead delay, combined with performance variability, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Procurement Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1399 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that supplier failure, scarcity or long-lead delay, combined with performance variability, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Procurement Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1400 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that supplier failure, scarcity or long-lead delay, combined with performance variability, may adversely affect project objectives through time / cost / quality consequences. | Procurement & Supply Chain | EPCM | Pumped Storage | Latin America | Detailed Engineering | Contractor | H | Time / Cost / Quality | Establish controls for supplier failure, scarcity or long-lead delay; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Procurement Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1401 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that port, customs, route or transport disruption, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1402 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that port, customs, route or transport disruption, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1403 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that port, customs, route or transport disruption, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1404 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that port, customs, route or transport disruption, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Grid Interconnection | Offshore Wind | North America | Procurement | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1405 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that port, customs, route or transport disruption, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1406 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that port, customs, route or transport disruption, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1407 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that port, customs, route or transport disruption, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1408 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that port, customs, route or transport disruption, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1409 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that port, customs, route or transport disruption, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPC / Turnkey | Hydropower | Latin America | Construction | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1410 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that port, customs, route or transport disruption, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Installation | Nuclear Power | Global / Multi-country | Installation | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1411 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that port, customs, route or transport disruption, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | R&D / Technology Development | Geothermal | Africa | Manufacturing | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1412 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that port, customs, route or transport disruption, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Brownfield Modification | LNG | East Asia | Construction | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1413 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that port, customs, route or transport disruption, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Owner’s Engineering | Onshore Wind | North America | Installation | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1414 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that port, customs, route or transport disruption, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1415 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that port, customs, route or transport disruption, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1416 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that port, customs, route or transport disruption, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Installation | Battery Energy Storage | South Asia | Installation | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1417 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that port, customs, route or transport disruption, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1418 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that port, customs, route or transport disruption, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1419 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that port, customs, route or transport disruption, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1420 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that port, customs, route or transport disruption, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1421 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that port, customs, route or transport disruption, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1422 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that port, customs, route or transport disruption, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Decommissioning | Marine Energy | North America | Operations / Handover | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1423 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that port, customs, route or transport disruption, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1424 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that port, customs, route or transport disruption, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Installation | LNG | Europe | FEED / Basic Design | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1425 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that port, customs, route or transport disruption, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1426 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that port, customs, route or transport disruption, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1427 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that port, customs, route or transport disruption, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1428 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that port, customs, route or transport disruption, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1429 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that port, customs, route or transport disruption, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1430 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that port, customs, route or transport disruption, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1431 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that port, customs, route or transport disruption, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Operations & Maintenance | District Energy | North America | Detailed Engineering | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1432 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that port, customs, route or transport disruption, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Grid Interconnection | Pumped Storage | Oceania | Procurement | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1433 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that port, customs, route or transport disruption, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1434 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that port, customs, route or transport disruption, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Brownfield Modification | Marine Energy | Africa | Construction | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1435 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that port, customs, route or transport disruption, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Owner’s Engineering | Geothermal | East Asia | Installation | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1436 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that port, customs, route or transport disruption, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Decommissioning | Offshore Wind | Latin America | Manufacturing | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1437 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that port, customs, route or transport disruption, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1438 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that port, customs, route or transport disruption, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Installation | Refining & Petrochemicals | Middle East | Installation | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1439 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that port, customs, route or transport disruption, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1440 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that port, customs, route or transport disruption, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1441 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that port, customs, route or transport disruption, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Owner’s Engineering | Hydropower | Oceania | Installation | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1442 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that port, customs, route or transport disruption, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPCM | Nuclear Power | Europe | Pre-commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1443 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that port, customs, route or transport disruption, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Commissioning & Start-up | District Energy | Africa | Commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1444 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that port, customs, route or transport disruption, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1445 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that port, customs, route or transport disruption, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1446 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that port, customs, route or transport disruption, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1447 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that port, customs, route or transport disruption, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1448 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that port, customs, route or transport disruption, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1449 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that port, customs, route or transport disruption, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1450 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that port, customs, route or transport disruption, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1451 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that port, customs, route or transport disruption, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1452 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that port, customs, route or transport disruption, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1453 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that port, customs, route or transport disruption, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1454 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that port, customs, route or transport disruption, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Grid Interconnection | Nuclear Power | North America | Procurement | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1455 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that port, customs, route or transport disruption, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | R&D / Technology Development | District Energy | Oceania | Manufacturing | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1456 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that port, customs, route or transport disruption, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPCM | LNG | Middle East | Detailed Engineering | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1457 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that port, customs, route or transport disruption, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1458 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that port, customs, route or transport disruption, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1459 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that port, customs, route or transport disruption, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1460 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that port, customs, route or transport disruption, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Installation | Offshore Wind | Global / Multi-country | Installation | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1461 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that port, customs, route or transport disruption, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1462 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that port, customs, route or transport disruption, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1463 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that port, customs, route or transport disruption, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Owner’s Engineering | Transmission & Substations | North America | Installation | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1464 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that port, customs, route or transport disruption, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1465 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that port, customs, route or transport disruption, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Commissioning & Start-up | Hydropower | Europe | Commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1466 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that port, customs, route or transport disruption, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Installation | Marine Energy | South Asia | Installation | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1467 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that port, customs, route or transport disruption, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1468 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that port, customs, route or transport disruption, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Grid Interconnection | LNG | Latin America | Commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1469 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that port, customs, route or transport disruption, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1470 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that port, customs, route or transport disruption, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1471 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that port, customs, route or transport disruption, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1472 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that port, customs, route or transport disruption, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1473 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that port, customs, route or transport disruption, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1474 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that port, customs, route or transport disruption, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1475 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that port, customs, route or transport disruption, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1476 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that port, customs, route or transport disruption, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1477 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that port, customs, route or transport disruption, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1478 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that port, customs, route or transport disruption, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1479 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that port, customs, route or transport disruption, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Commissioning & Start-up | Geothermal | Middle East | Procurement | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1480 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that port, customs, route or transport disruption, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Decommissioning | LNG | South Asia | Manufacturing | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1481 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that port, customs, route or transport disruption, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1482 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that port, customs, route or transport disruption, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1483 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that port, customs, route or transport disruption, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | R&D / Technology Development | Solar PV | Europe | Manufacturing | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1484 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that port, customs, route or transport disruption, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Brownfield Modification | Battery Energy Storage | Africa | Construction | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1485 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that port, customs, route or transport disruption, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1486 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that port, customs, route or transport disruption, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Decommissioning | Nuclear Power | Latin America | Manufacturing | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1487 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that port, customs, route or transport disruption, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1488 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that port, customs, route or transport disruption, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Installation | Pumped Storage | Middle East | Installation | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1489 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that port, customs, route or transport disruption, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1490 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that port, customs, route or transport disruption, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1491 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that port, customs, route or transport disruption, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1492 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that port, customs, route or transport disruption, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPCM | Offshore Wind | Europe | Pre-commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1493 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that port, customs, route or transport disruption, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1494 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that port, customs, route or transport disruption, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1495 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that port, customs, route or transport disruption, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1496 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that port, customs, route or transport disruption, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Logistics Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1497 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that port, customs, route or transport disruption, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Logistics Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1498 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that port, customs, route or transport disruption, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Logistics Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1499 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that port, customs, route or transport disruption, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Logistics Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1500 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that port, customs, route or transport disruption, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Logistics & Customs | EPCM | Pumped Storage | Latin America | Detailed Engineering | Contractor | M | Time / Cost | Establish controls for port, customs, route or transport disruption; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Logistics Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1501 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that skill shortage, turnover or low productivity, combined with insufficient planning, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1502 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that skill shortage, turnover or low productivity, combined with insufficient planning, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1503 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that skill shortage, turnover or low productivity, combined with insufficient planning, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1504 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that skill shortage, turnover or low productivity, combined with insufficient planning, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Grid Interconnection | Offshore Wind | North America | Procurement | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1505 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that skill shortage, turnover or low productivity, combined with insufficient planning, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1506 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that skill shortage, turnover or low productivity, combined with incomplete information, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1507 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that skill shortage, turnover or low productivity, combined with incomplete information, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1508 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that skill shortage, turnover or low productivity, combined with incomplete information, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1509 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that skill shortage, turnover or low productivity, combined with incomplete information, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPC / Turnkey | Hydropower | Latin America | Construction | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1510 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that skill shortage, turnover or low productivity, combined with incomplete information, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Installation | Nuclear Power | Global / Multi-country | Installation | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1511 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that skill shortage, turnover or low productivity, combined with late decision-making, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | R&D / Technology Development | Geothermal | Africa | Manufacturing | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1512 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that skill shortage, turnover or low productivity, combined with late decision-making, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Brownfield Modification | LNG | East Asia | Construction | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1513 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that skill shortage, turnover or low productivity, combined with late decision-making, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Owner’s Engineering | Onshore Wind | North America | Installation | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1514 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that skill shortage, turnover or low productivity, combined with late decision-making, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1515 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that skill shortage, turnover or low productivity, combined with late decision-making, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1516 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that skill shortage, turnover or low productivity, combined with weak controls, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Installation | Battery Energy Storage | South Asia | Installation | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1517 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that skill shortage, turnover or low productivity, combined with weak controls, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1518 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that skill shortage, turnover or low productivity, combined with weak controls, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1519 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that skill shortage, turnover or low productivity, combined with weak controls, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1520 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that skill shortage, turnover or low productivity, combined with weak controls, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1521 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that skill shortage, turnover or low productivity, combined with resource constraints, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1522 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that skill shortage, turnover or low productivity, combined with resource constraints, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Decommissioning | Marine Energy | North America | Operations / Handover | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1523 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that skill shortage, turnover or low productivity, combined with resource constraints, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1524 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that skill shortage, turnover or low productivity, combined with resource constraints, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Installation | LNG | Europe | FEED / Basic Design | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1525 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that skill shortage, turnover or low productivity, combined with resource constraints, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1526 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that skill shortage, turnover or low productivity, combined with supplier dependency, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1527 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that skill shortage, turnover or low productivity, combined with supplier dependency, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1528 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that skill shortage, turnover or low productivity, combined with supplier dependency, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1529 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that skill shortage, turnover or low productivity, combined with supplier dependency, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1530 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that skill shortage, turnover or low productivity, combined with supplier dependency, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1531 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that skill shortage, turnover or low productivity, combined with interface complexity, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Operations & Maintenance | District Energy | North America | Detailed Engineering | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1532 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that skill shortage, turnover or low productivity, combined with interface complexity, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Grid Interconnection | Pumped Storage | Oceania | Procurement | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1533 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that skill shortage, turnover or low productivity, combined with interface complexity, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1534 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that skill shortage, turnover or low productivity, combined with interface complexity, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Brownfield Modification | Marine Energy | Africa | Construction | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1535 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that skill shortage, turnover or low productivity, combined with interface complexity, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Owner’s Engineering | Geothermal | East Asia | Installation | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1536 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that skill shortage, turnover or low productivity, combined with requirements volatility, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Decommissioning | Offshore Wind | Latin America | Manufacturing | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1537 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that skill shortage, turnover or low productivity, combined with requirements volatility, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1538 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that skill shortage, turnover or low productivity, combined with requirements volatility, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Installation | Refining & Petrochemicals | Middle East | Installation | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1539 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that skill shortage, turnover or low productivity, combined with requirements volatility, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1540 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that skill shortage, turnover or low productivity, combined with requirements volatility, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1541 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that skill shortage, turnover or low productivity, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Owner’s Engineering | Hydropower | Oceania | Installation | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1542 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that skill shortage, turnover or low productivity, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPCM | Nuclear Power | Europe | Pre-commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1543 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that skill shortage, turnover or low productivity, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Commissioning & Start-up | District Energy | Africa | Commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1544 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that skill shortage, turnover or low productivity, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1545 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that skill shortage, turnover or low productivity, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1546 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that skill shortage, turnover or low productivity, combined with inadequate verification, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1547 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that skill shortage, turnover or low productivity, combined with inadequate verification, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1548 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that skill shortage, turnover or low productivity, combined with inadequate verification, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1549 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that skill shortage, turnover or low productivity, combined with inadequate verification, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1550 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that skill shortage, turnover or low productivity, combined with inadequate verification, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1551 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that skill shortage, turnover or low productivity, combined with poor communication, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1552 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that skill shortage, turnover or low productivity, combined with poor communication, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1553 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that skill shortage, turnover or low productivity, combined with poor communication, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1554 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that skill shortage, turnover or low productivity, combined with poor communication, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Grid Interconnection | Nuclear Power | North America | Procurement | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1555 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that skill shortage, turnover or low productivity, combined with poor communication, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | R&D / Technology Development | District Energy | Oceania | Manufacturing | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1556 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that skill shortage, turnover or low productivity, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPCM | LNG | Middle East | Detailed Engineering | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1557 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that skill shortage, turnover or low productivity, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1558 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that skill shortage, turnover or low productivity, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1559 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that skill shortage, turnover or low productivity, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1560 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that skill shortage, turnover or low productivity, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Installation | Offshore Wind | Global / Multi-country | Installation | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1561 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that skill shortage, turnover or low productivity, combined with low technical maturity, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1562 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that skill shortage, turnover or low productivity, combined with low technical maturity, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1563 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that skill shortage, turnover or low productivity, combined with low technical maturity, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Owner’s Engineering | Transmission & Substations | North America | Installation | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1564 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that skill shortage, turnover or low productivity, combined with low technical maturity, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1565 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that skill shortage, turnover or low productivity, combined with low technical maturity, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Commissioning & Start-up | Hydropower | Europe | Commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1566 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that skill shortage, turnover or low productivity, combined with documentation gaps, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Installation | Marine Energy | South Asia | Installation | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1567 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that skill shortage, turnover or low productivity, combined with documentation gaps, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1568 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that skill shortage, turnover or low productivity, combined with documentation gaps, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Grid Interconnection | LNG | Latin America | Commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1569 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that skill shortage, turnover or low productivity, combined with documentation gaps, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1570 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that skill shortage, turnover or low productivity, combined with documentation gaps, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1571 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that skill shortage, turnover or low productivity, combined with external disruption, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1572 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that skill shortage, turnover or low productivity, combined with external disruption, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1573 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that skill shortage, turnover or low productivity, combined with external disruption, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1574 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that skill shortage, turnover or low productivity, combined with external disruption, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1575 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that skill shortage, turnover or low productivity, combined with external disruption, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1576 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that skill shortage, turnover or low productivity, combined with governance delay, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1577 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that skill shortage, turnover or low productivity, combined with governance delay, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1578 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that skill shortage, turnover or low productivity, combined with governance delay, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1579 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that skill shortage, turnover or low productivity, combined with governance delay, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Commissioning & Start-up | Geothermal | Middle East | Procurement | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1580 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that skill shortage, turnover or low productivity, combined with governance delay, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Decommissioning | LNG | South Asia | Manufacturing | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1581 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that skill shortage, turnover or low productivity, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1582 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that skill shortage, turnover or low productivity, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1583 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that skill shortage, turnover or low productivity, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | R&D / Technology Development | Solar PV | Europe | Manufacturing | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1584 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that skill shortage, turnover or low productivity, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Brownfield Modification | Battery Energy Storage | Africa | Construction | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1585 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that skill shortage, turnover or low productivity, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1586 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that skill shortage, turnover or low productivity, combined with quality escape, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Decommissioning | Nuclear Power | Latin America | Manufacturing | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1587 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that skill shortage, turnover or low productivity, combined with quality escape, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1588 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that skill shortage, turnover or low productivity, combined with quality escape, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Installation | Pumped Storage | Middle East | Installation | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1589 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that skill shortage, turnover or low productivity, combined with quality escape, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1590 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that skill shortage, turnover or low productivity, combined with quality escape, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1591 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that skill shortage, turnover or low productivity, combined with access constraint, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1592 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that skill shortage, turnover or low productivity, combined with access constraint, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPCM | Offshore Wind | Europe | Pre-commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1593 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that skill shortage, turnover or low productivity, combined with access constraint, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1594 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that skill shortage, turnover or low productivity, combined with access constraint, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1595 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that skill shortage, turnover or low productivity, combined with access constraint, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1596 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that skill shortage, turnover or low productivity, combined with performance variability, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Construction Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1597 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that skill shortage, turnover or low productivity, combined with performance variability, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Construction Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1598 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that skill shortage, turnover or low productivity, combined with performance variability, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Construction Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1599 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that skill shortage, turnover or low productivity, combined with performance variability, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Construction Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1600 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that skill shortage, turnover or low productivity, combined with performance variability, may adversely affect project objectives through time / cost / quality / hse consequences. | Labour & Skills | EPCM | Pumped Storage | Latin America | Detailed Engineering | Contractor | H | Time / Cost / Quality / HSE | Establish controls for skill shortage, turnover or low productivity; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Construction Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1601 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that equipment breakdown, capacity gap or certification lapse, combined with insufficient planning, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1602 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that equipment breakdown, capacity gap or certification lapse, combined with insufficient planning, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1603 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that equipment breakdown, capacity gap or certification lapse, combined with insufficient planning, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1604 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that equipment breakdown, capacity gap or certification lapse, combined with insufficient planning, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Grid Interconnection | Offshore Wind | North America | Procurement | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1605 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that equipment breakdown, capacity gap or certification lapse, combined with insufficient planning, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1606 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that equipment breakdown, capacity gap or certification lapse, combined with incomplete information, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1607 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that equipment breakdown, capacity gap or certification lapse, combined with incomplete information, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1608 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that equipment breakdown, capacity gap or certification lapse, combined with incomplete information, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1609 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that equipment breakdown, capacity gap or certification lapse, combined with incomplete information, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPC / Turnkey | Hydropower | Latin America | Construction | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1610 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that equipment breakdown, capacity gap or certification lapse, combined with incomplete information, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Installation | Nuclear Power | Global / Multi-country | Installation | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1611 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that equipment breakdown, capacity gap or certification lapse, combined with late decision-making, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | R&D / Technology Development | Geothermal | Africa | Manufacturing | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1612 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that equipment breakdown, capacity gap or certification lapse, combined with late decision-making, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Brownfield Modification | LNG | East Asia | Construction | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1613 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that equipment breakdown, capacity gap or certification lapse, combined with late decision-making, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Owner’s Engineering | Onshore Wind | North America | Installation | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1614 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that equipment breakdown, capacity gap or certification lapse, combined with late decision-making, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1615 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that equipment breakdown, capacity gap or certification lapse, combined with late decision-making, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1616 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that equipment breakdown, capacity gap or certification lapse, combined with weak controls, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Installation | Battery Energy Storage | South Asia | Installation | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1617 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that equipment breakdown, capacity gap or certification lapse, combined with weak controls, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1618 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that equipment breakdown, capacity gap or certification lapse, combined with weak controls, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1619 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that equipment breakdown, capacity gap or certification lapse, combined with weak controls, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1620 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that equipment breakdown, capacity gap or certification lapse, combined with weak controls, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1621 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that equipment breakdown, capacity gap or certification lapse, combined with resource constraints, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1622 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that equipment breakdown, capacity gap or certification lapse, combined with resource constraints, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Decommissioning | Marine Energy | North America | Operations / Handover | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1623 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that equipment breakdown, capacity gap or certification lapse, combined with resource constraints, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1624 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that equipment breakdown, capacity gap or certification lapse, combined with resource constraints, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Installation | LNG | Europe | FEED / Basic Design | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1625 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that equipment breakdown, capacity gap or certification lapse, combined with resource constraints, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1626 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that equipment breakdown, capacity gap or certification lapse, combined with supplier dependency, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1627 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that equipment breakdown, capacity gap or certification lapse, combined with supplier dependency, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1628 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that equipment breakdown, capacity gap or certification lapse, combined with supplier dependency, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1629 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that equipment breakdown, capacity gap or certification lapse, combined with supplier dependency, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1630 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that equipment breakdown, capacity gap or certification lapse, combined with supplier dependency, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1631 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that equipment breakdown, capacity gap or certification lapse, combined with interface complexity, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Operations & Maintenance | District Energy | North America | Detailed Engineering | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1632 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that equipment breakdown, capacity gap or certification lapse, combined with interface complexity, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Grid Interconnection | Pumped Storage | Oceania | Procurement | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1633 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that equipment breakdown, capacity gap or certification lapse, combined with interface complexity, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1634 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that equipment breakdown, capacity gap or certification lapse, combined with interface complexity, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Brownfield Modification | Marine Energy | Africa | Construction | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1635 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that equipment breakdown, capacity gap or certification lapse, combined with interface complexity, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Owner’s Engineering | Geothermal | East Asia | Installation | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1636 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that equipment breakdown, capacity gap or certification lapse, combined with requirements volatility, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Decommissioning | Offshore Wind | Latin America | Manufacturing | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1637 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that equipment breakdown, capacity gap or certification lapse, combined with requirements volatility, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1638 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that equipment breakdown, capacity gap or certification lapse, combined with requirements volatility, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Installation | Refining & Petrochemicals | Middle East | Installation | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1639 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that equipment breakdown, capacity gap or certification lapse, combined with requirements volatility, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1640 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that equipment breakdown, capacity gap or certification lapse, combined with requirements volatility, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1641 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that equipment breakdown, capacity gap or certification lapse, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Owner’s Engineering | Hydropower | Oceania | Installation | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1642 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that equipment breakdown, capacity gap or certification lapse, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPCM | Nuclear Power | Europe | Pre-commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1643 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that equipment breakdown, capacity gap or certification lapse, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Commissioning & Start-up | District Energy | Africa | Commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1644 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that equipment breakdown, capacity gap or certification lapse, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1645 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that equipment breakdown, capacity gap or certification lapse, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1646 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that equipment breakdown, capacity gap or certification lapse, combined with inadequate verification, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1647 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that equipment breakdown, capacity gap or certification lapse, combined with inadequate verification, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1648 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that equipment breakdown, capacity gap or certification lapse, combined with inadequate verification, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1649 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that equipment breakdown, capacity gap or certification lapse, combined with inadequate verification, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1650 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that equipment breakdown, capacity gap or certification lapse, combined with inadequate verification, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1651 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that equipment breakdown, capacity gap or certification lapse, combined with poor communication, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1652 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that equipment breakdown, capacity gap or certification lapse, combined with poor communication, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1653 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that equipment breakdown, capacity gap or certification lapse, combined with poor communication, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1654 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that equipment breakdown, capacity gap or certification lapse, combined with poor communication, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Grid Interconnection | Nuclear Power | North America | Procurement | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1655 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that equipment breakdown, capacity gap or certification lapse, combined with poor communication, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | R&D / Technology Development | District Energy | Oceania | Manufacturing | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1656 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that equipment breakdown, capacity gap or certification lapse, combined with incorrect assumptions, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPCM | LNG | Middle East | Detailed Engineering | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1657 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that equipment breakdown, capacity gap or certification lapse, combined with incorrect assumptions, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1658 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that equipment breakdown, capacity gap or certification lapse, combined with incorrect assumptions, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1659 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that equipment breakdown, capacity gap or certification lapse, combined with incorrect assumptions, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1660 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that equipment breakdown, capacity gap or certification lapse, combined with incorrect assumptions, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Installation | Offshore Wind | Global / Multi-country | Installation | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1661 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that equipment breakdown, capacity gap or certification lapse, combined with low technical maturity, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1662 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that equipment breakdown, capacity gap or certification lapse, combined with low technical maturity, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1663 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that equipment breakdown, capacity gap or certification lapse, combined with low technical maturity, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Owner’s Engineering | Transmission & Substations | North America | Installation | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1664 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that equipment breakdown, capacity gap or certification lapse, combined with low technical maturity, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1665 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that equipment breakdown, capacity gap or certification lapse, combined with low technical maturity, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Commissioning & Start-up | Hydropower | Europe | Commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1666 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that equipment breakdown, capacity gap or certification lapse, combined with documentation gaps, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Installation | Marine Energy | South Asia | Installation | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1667 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that equipment breakdown, capacity gap or certification lapse, combined with documentation gaps, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1668 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that equipment breakdown, capacity gap or certification lapse, combined with documentation gaps, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Grid Interconnection | LNG | Latin America | Commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1669 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that equipment breakdown, capacity gap or certification lapse, combined with documentation gaps, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1670 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that equipment breakdown, capacity gap or certification lapse, combined with documentation gaps, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1671 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that equipment breakdown, capacity gap or certification lapse, combined with external disruption, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1672 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that equipment breakdown, capacity gap or certification lapse, combined with external disruption, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1673 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that equipment breakdown, capacity gap or certification lapse, combined with external disruption, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1674 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that equipment breakdown, capacity gap or certification lapse, combined with external disruption, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1675 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that equipment breakdown, capacity gap or certification lapse, combined with external disruption, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1676 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that equipment breakdown, capacity gap or certification lapse, combined with governance delay, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1677 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that equipment breakdown, capacity gap or certification lapse, combined with governance delay, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1678 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that equipment breakdown, capacity gap or certification lapse, combined with governance delay, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1679 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that equipment breakdown, capacity gap or certification lapse, combined with governance delay, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Commissioning & Start-up | Geothermal | Middle East | Procurement | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1680 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that equipment breakdown, capacity gap or certification lapse, combined with governance delay, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Decommissioning | LNG | South Asia | Manufacturing | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1681 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that equipment breakdown, capacity gap or certification lapse, combined with commercial misalignment, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1682 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that equipment breakdown, capacity gap or certification lapse, combined with commercial misalignment, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1683 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that equipment breakdown, capacity gap or certification lapse, combined with commercial misalignment, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | R&D / Technology Development | Solar PV | Europe | Manufacturing | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1684 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that equipment breakdown, capacity gap or certification lapse, combined with commercial misalignment, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Brownfield Modification | Battery Energy Storage | Africa | Construction | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1685 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that equipment breakdown, capacity gap or certification lapse, combined with commercial misalignment, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1686 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that equipment breakdown, capacity gap or certification lapse, combined with quality escape, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Decommissioning | Nuclear Power | Latin America | Manufacturing | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1687 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that equipment breakdown, capacity gap or certification lapse, combined with quality escape, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1688 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that equipment breakdown, capacity gap or certification lapse, combined with quality escape, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Installation | Pumped Storage | Middle East | Installation | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1689 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that equipment breakdown, capacity gap or certification lapse, combined with quality escape, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1690 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that equipment breakdown, capacity gap or certification lapse, combined with quality escape, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1691 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that equipment breakdown, capacity gap or certification lapse, combined with access constraint, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1692 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that equipment breakdown, capacity gap or certification lapse, combined with access constraint, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPCM | Offshore Wind | Europe | Pre-commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1693 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that equipment breakdown, capacity gap or certification lapse, combined with access constraint, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1694 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that equipment breakdown, capacity gap or certification lapse, combined with access constraint, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1695 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that equipment breakdown, capacity gap or certification lapse, combined with access constraint, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1696 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that equipment breakdown, capacity gap or certification lapse, combined with performance variability, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Plant Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1697 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that equipment breakdown, capacity gap or certification lapse, combined with performance variability, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Plant Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1698 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that equipment breakdown, capacity gap or certification lapse, combined with performance variability, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Plant Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1699 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that equipment breakdown, capacity gap or certification lapse, combined with performance variability, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Plant Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1700 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that equipment breakdown, capacity gap or certification lapse, combined with performance variability, may adversely affect project objectives through time / cost / hse consequences. | Plant & Equipment | EPCM | Pumped Storage | Latin America | Detailed Engineering | Contractor | M | Time / Cost / HSE | Establish controls for equipment breakdown, capacity gap or certification lapse; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Plant Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1701 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that scope gap, boundary conflict or late interface data, combined with insufficient planning, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1702 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that scope gap, boundary conflict or late interface data, combined with insufficient planning, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1703 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that scope gap, boundary conflict or late interface data, combined with insufficient planning, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1704 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that scope gap, boundary conflict or late interface data, combined with insufficient planning, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Grid Interconnection | Offshore Wind | North America | Procurement | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1705 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that scope gap, boundary conflict or late interface data, combined with insufficient planning, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1706 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that scope gap, boundary conflict or late interface data, combined with incomplete information, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1707 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that scope gap, boundary conflict or late interface data, combined with incomplete information, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1708 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that scope gap, boundary conflict or late interface data, combined with incomplete information, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1709 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that scope gap, boundary conflict or late interface data, combined with incomplete information, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPC / Turnkey | Hydropower | Latin America | Construction | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1710 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that scope gap, boundary conflict or late interface data, combined with incomplete information, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Installation | Nuclear Power | Global / Multi-country | Installation | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1711 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that scope gap, boundary conflict or late interface data, combined with late decision-making, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | R&D / Technology Development | Geothermal | Africa | Manufacturing | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1712 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that scope gap, boundary conflict or late interface data, combined with late decision-making, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Brownfield Modification | LNG | East Asia | Construction | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1713 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that scope gap, boundary conflict or late interface data, combined with late decision-making, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Owner’s Engineering | Onshore Wind | North America | Installation | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1714 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that scope gap, boundary conflict or late interface data, combined with late decision-making, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1715 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that scope gap, boundary conflict or late interface data, combined with late decision-making, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1716 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that scope gap, boundary conflict or late interface data, combined with weak controls, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Installation | Battery Energy Storage | South Asia | Installation | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1717 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that scope gap, boundary conflict or late interface data, combined with weak controls, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1718 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that scope gap, boundary conflict or late interface data, combined with weak controls, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1719 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that scope gap, boundary conflict or late interface data, combined with weak controls, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1720 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that scope gap, boundary conflict or late interface data, combined with weak controls, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1721 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that scope gap, boundary conflict or late interface data, combined with resource constraints, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1722 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that scope gap, boundary conflict or late interface data, combined with resource constraints, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Decommissioning | Marine Energy | North America | Operations / Handover | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1723 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that scope gap, boundary conflict or late interface data, combined with resource constraints, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1724 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that scope gap, boundary conflict or late interface data, combined with resource constraints, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Installation | LNG | Europe | FEED / Basic Design | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1725 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that scope gap, boundary conflict or late interface data, combined with resource constraints, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1726 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that scope gap, boundary conflict or late interface data, combined with supplier dependency, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1727 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that scope gap, boundary conflict or late interface data, combined with supplier dependency, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1728 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that scope gap, boundary conflict or late interface data, combined with supplier dependency, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1729 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that scope gap, boundary conflict or late interface data, combined with supplier dependency, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1730 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that scope gap, boundary conflict or late interface data, combined with supplier dependency, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1731 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that scope gap, boundary conflict or late interface data, combined with interface complexity, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Operations & Maintenance | District Energy | North America | Detailed Engineering | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1732 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that scope gap, boundary conflict or late interface data, combined with interface complexity, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Grid Interconnection | Pumped Storage | Oceania | Procurement | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1733 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that scope gap, boundary conflict or late interface data, combined with interface complexity, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1734 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that scope gap, boundary conflict or late interface data, combined with interface complexity, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Brownfield Modification | Marine Energy | Africa | Construction | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1735 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that scope gap, boundary conflict or late interface data, combined with interface complexity, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Owner’s Engineering | Geothermal | East Asia | Installation | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1736 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that scope gap, boundary conflict or late interface data, combined with requirements volatility, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Decommissioning | Offshore Wind | Latin America | Manufacturing | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1737 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that scope gap, boundary conflict or late interface data, combined with requirements volatility, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1738 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that scope gap, boundary conflict or late interface data, combined with requirements volatility, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Installation | Refining & Petrochemicals | Middle East | Installation | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1739 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that scope gap, boundary conflict or late interface data, combined with requirements volatility, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1740 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that scope gap, boundary conflict or late interface data, combined with requirements volatility, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1741 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that scope gap, boundary conflict or late interface data, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Owner’s Engineering | Hydropower | Oceania | Installation | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1742 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that scope gap, boundary conflict or late interface data, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPCM | Nuclear Power | Europe | Pre-commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1743 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that scope gap, boundary conflict or late interface data, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Commissioning & Start-up | District Energy | Africa | Commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1744 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that scope gap, boundary conflict or late interface data, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1745 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that scope gap, boundary conflict or late interface data, combined with regulatory uncertainty, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1746 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that scope gap, boundary conflict or late interface data, combined with inadequate verification, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1747 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that scope gap, boundary conflict or late interface data, combined with inadequate verification, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1748 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that scope gap, boundary conflict or late interface data, combined with inadequate verification, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1749 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that scope gap, boundary conflict or late interface data, combined with inadequate verification, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1750 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that scope gap, boundary conflict or late interface data, combined with inadequate verification, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1751 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that scope gap, boundary conflict or late interface data, combined with poor communication, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1752 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that scope gap, boundary conflict or late interface data, combined with poor communication, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1753 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that scope gap, boundary conflict or late interface data, combined with poor communication, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1754 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that scope gap, boundary conflict or late interface data, combined with poor communication, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Grid Interconnection | Nuclear Power | North America | Procurement | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1755 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that scope gap, boundary conflict or late interface data, combined with poor communication, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | R&D / Technology Development | District Energy | Oceania | Manufacturing | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1756 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that scope gap, boundary conflict or late interface data, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPCM | LNG | Middle East | Detailed Engineering | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1757 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that scope gap, boundary conflict or late interface data, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1758 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that scope gap, boundary conflict or late interface data, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1759 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that scope gap, boundary conflict or late interface data, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1760 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that scope gap, boundary conflict or late interface data, combined with incorrect assumptions, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Installation | Offshore Wind | Global / Multi-country | Installation | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1761 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that scope gap, boundary conflict or late interface data, combined with low technical maturity, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1762 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that scope gap, boundary conflict or late interface data, combined with low technical maturity, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1763 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that scope gap, boundary conflict or late interface data, combined with low technical maturity, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Owner’s Engineering | Transmission & Substations | North America | Installation | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1764 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that scope gap, boundary conflict or late interface data, combined with low technical maturity, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1765 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that scope gap, boundary conflict or late interface data, combined with low technical maturity, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Commissioning & Start-up | Hydropower | Europe | Commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1766 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that scope gap, boundary conflict or late interface data, combined with documentation gaps, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Installation | Marine Energy | South Asia | Installation | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1767 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that scope gap, boundary conflict or late interface data, combined with documentation gaps, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1768 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that scope gap, boundary conflict or late interface data, combined with documentation gaps, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Grid Interconnection | LNG | Latin America | Commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1769 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that scope gap, boundary conflict or late interface data, combined with documentation gaps, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1770 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that scope gap, boundary conflict or late interface data, combined with documentation gaps, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1771 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that scope gap, boundary conflict or late interface data, combined with external disruption, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1772 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that scope gap, boundary conflict or late interface data, combined with external disruption, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1773 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that scope gap, boundary conflict or late interface data, combined with external disruption, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1774 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that scope gap, boundary conflict or late interface data, combined with external disruption, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1775 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that scope gap, boundary conflict or late interface data, combined with external disruption, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1776 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that scope gap, boundary conflict or late interface data, combined with governance delay, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1777 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that scope gap, boundary conflict or late interface data, combined with governance delay, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1778 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that scope gap, boundary conflict or late interface data, combined with governance delay, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1779 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that scope gap, boundary conflict or late interface data, combined with governance delay, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Commissioning & Start-up | Geothermal | Middle East | Procurement | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1780 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that scope gap, boundary conflict or late interface data, combined with governance delay, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Decommissioning | LNG | South Asia | Manufacturing | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1781 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that scope gap, boundary conflict or late interface data, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1782 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that scope gap, boundary conflict or late interface data, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1783 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that scope gap, boundary conflict or late interface data, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | R&D / Technology Development | Solar PV | Europe | Manufacturing | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1784 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that scope gap, boundary conflict or late interface data, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Brownfield Modification | Battery Energy Storage | Africa | Construction | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1785 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that scope gap, boundary conflict or late interface data, combined with commercial misalignment, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1786 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that scope gap, boundary conflict or late interface data, combined with quality escape, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Decommissioning | Nuclear Power | Latin America | Manufacturing | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1787 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that scope gap, boundary conflict or late interface data, combined with quality escape, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1788 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that scope gap, boundary conflict or late interface data, combined with quality escape, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Installation | Pumped Storage | Middle East | Installation | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1789 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that scope gap, boundary conflict or late interface data, combined with quality escape, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1790 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that scope gap, boundary conflict or late interface data, combined with quality escape, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1791 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that scope gap, boundary conflict or late interface data, combined with access constraint, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1792 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that scope gap, boundary conflict or late interface data, combined with access constraint, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPCM | Offshore Wind | Europe | Pre-commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1793 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that scope gap, boundary conflict or late interface data, combined with access constraint, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1794 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that scope gap, boundary conflict or late interface data, combined with access constraint, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1795 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that scope gap, boundary conflict or late interface data, combined with access constraint, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1796 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that scope gap, boundary conflict or late interface data, combined with performance variability, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Interface Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1797 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that scope gap, boundary conflict or late interface data, combined with performance variability, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Interface Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1798 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that scope gap, boundary conflict or late interface data, combined with performance variability, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Interface Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1799 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that scope gap, boundary conflict or late interface data, combined with performance variability, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Interface Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1800 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that scope gap, boundary conflict or late interface data, combined with performance variability, may adversely affect project objectives through time / cost / quality consequences. | Interfaces | EPCM | Pumped Storage | Latin America | Detailed Engineering | Shared | H | Time / Cost / Quality | Establish controls for scope gap, boundary conflict or late interface data; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Interface Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1801 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that opposition, grievance or expectation conflict, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1802 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that opposition, grievance or expectation conflict, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1803 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that opposition, grievance or expectation conflict, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1804 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that opposition, grievance or expectation conflict, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Grid Interconnection | Offshore Wind | North America | Procurement | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1805 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that opposition, grievance or expectation conflict, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1806 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that opposition, grievance or expectation conflict, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1807 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that opposition, grievance or expectation conflict, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1808 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that opposition, grievance or expectation conflict, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1809 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that opposition, grievance or expectation conflict, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPC / Turnkey | Hydropower | Latin America | Construction | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1810 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that opposition, grievance or expectation conflict, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Installation | Nuclear Power | Global / Multi-country | Installation | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1811 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that opposition, grievance or expectation conflict, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | R&D / Technology Development | Geothermal | Africa | Manufacturing | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1812 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that opposition, grievance or expectation conflict, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Brownfield Modification | LNG | East Asia | Construction | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1813 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that opposition, grievance or expectation conflict, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Owner’s Engineering | Onshore Wind | North America | Installation | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1814 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that opposition, grievance or expectation conflict, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1815 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that opposition, grievance or expectation conflict, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1816 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that opposition, grievance or expectation conflict, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Installation | Battery Energy Storage | South Asia | Installation | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1817 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that opposition, grievance or expectation conflict, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1818 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that opposition, grievance or expectation conflict, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1819 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that opposition, grievance or expectation conflict, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1820 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that opposition, grievance or expectation conflict, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1821 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that opposition, grievance or expectation conflict, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1822 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that opposition, grievance or expectation conflict, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Decommissioning | Marine Energy | North America | Operations / Handover | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1823 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that opposition, grievance or expectation conflict, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1824 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that opposition, grievance or expectation conflict, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Installation | LNG | Europe | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1825 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that opposition, grievance or expectation conflict, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1826 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that opposition, grievance or expectation conflict, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1827 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that opposition, grievance or expectation conflict, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1828 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that opposition, grievance or expectation conflict, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1829 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that opposition, grievance or expectation conflict, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1830 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that opposition, grievance or expectation conflict, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1831 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that opposition, grievance or expectation conflict, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Operations & Maintenance | District Energy | North America | Detailed Engineering | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1832 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that opposition, grievance or expectation conflict, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Grid Interconnection | Pumped Storage | Oceania | Procurement | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1833 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that opposition, grievance or expectation conflict, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1834 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that opposition, grievance or expectation conflict, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Brownfield Modification | Marine Energy | Africa | Construction | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1835 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that opposition, grievance or expectation conflict, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Owner’s Engineering | Geothermal | East Asia | Installation | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1836 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that opposition, grievance or expectation conflict, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Decommissioning | Offshore Wind | Latin America | Manufacturing | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1837 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that opposition, grievance or expectation conflict, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1838 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that opposition, grievance or expectation conflict, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Installation | Refining & Petrochemicals | Middle East | Installation | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1839 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that opposition, grievance or expectation conflict, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1840 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that opposition, grievance or expectation conflict, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1841 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that opposition, grievance or expectation conflict, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Owner’s Engineering | Hydropower | Oceania | Installation | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1842 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that opposition, grievance or expectation conflict, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPCM | Nuclear Power | Europe | Pre-commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1843 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that opposition, grievance or expectation conflict, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Commissioning & Start-up | District Energy | Africa | Commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1844 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that opposition, grievance or expectation conflict, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1845 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that opposition, grievance or expectation conflict, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1846 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that opposition, grievance or expectation conflict, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1847 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that opposition, grievance or expectation conflict, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1848 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that opposition, grievance or expectation conflict, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1849 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that opposition, grievance or expectation conflict, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1850 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that opposition, grievance or expectation conflict, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1851 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that opposition, grievance or expectation conflict, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1852 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that opposition, grievance or expectation conflict, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1853 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that opposition, grievance or expectation conflict, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1854 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that opposition, grievance or expectation conflict, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Grid Interconnection | Nuclear Power | North America | Procurement | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1855 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that opposition, grievance or expectation conflict, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | R&D / Technology Development | District Energy | Oceania | Manufacturing | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1856 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that opposition, grievance or expectation conflict, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPCM | LNG | Middle East | Detailed Engineering | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1857 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that opposition, grievance or expectation conflict, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1858 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that opposition, grievance or expectation conflict, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1859 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that opposition, grievance or expectation conflict, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1860 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that opposition, grievance or expectation conflict, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Installation | Offshore Wind | Global / Multi-country | Installation | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1861 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that opposition, grievance or expectation conflict, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1862 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that opposition, grievance or expectation conflict, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1863 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that opposition, grievance or expectation conflict, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Owner’s Engineering | Transmission & Substations | North America | Installation | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1864 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that opposition, grievance or expectation conflict, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1865 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that opposition, grievance or expectation conflict, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Commissioning & Start-up | Hydropower | Europe | Commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1866 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that opposition, grievance or expectation conflict, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Installation | Marine Energy | South Asia | Installation | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1867 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that opposition, grievance or expectation conflict, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1868 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that opposition, grievance or expectation conflict, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Grid Interconnection | LNG | Latin America | Commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1869 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that opposition, grievance or expectation conflict, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1870 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that opposition, grievance or expectation conflict, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1871 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that opposition, grievance or expectation conflict, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1872 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that opposition, grievance or expectation conflict, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1873 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that opposition, grievance or expectation conflict, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1874 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that opposition, grievance or expectation conflict, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1875 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that opposition, grievance or expectation conflict, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1876 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that opposition, grievance or expectation conflict, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1877 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that opposition, grievance or expectation conflict, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1878 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that opposition, grievance or expectation conflict, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1879 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that opposition, grievance or expectation conflict, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Commissioning & Start-up | Geothermal | Middle East | Procurement | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1880 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that opposition, grievance or expectation conflict, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Decommissioning | LNG | South Asia | Manufacturing | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1881 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that opposition, grievance or expectation conflict, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1882 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that opposition, grievance or expectation conflict, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1883 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that opposition, grievance or expectation conflict, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | R&D / Technology Development | Solar PV | Europe | Manufacturing | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1884 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that opposition, grievance or expectation conflict, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Brownfield Modification | Battery Energy Storage | Africa | Construction | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1885 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that opposition, grievance or expectation conflict, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1886 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that opposition, grievance or expectation conflict, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Decommissioning | Nuclear Power | Latin America | Manufacturing | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1887 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that opposition, grievance or expectation conflict, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1888 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that opposition, grievance or expectation conflict, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Installation | Pumped Storage | Middle East | Installation | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1889 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that opposition, grievance or expectation conflict, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1890 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that opposition, grievance or expectation conflict, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1891 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that opposition, grievance or expectation conflict, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1892 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that opposition, grievance or expectation conflict, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPCM | Offshore Wind | Europe | Pre-commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1893 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that opposition, grievance or expectation conflict, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1894 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that opposition, grievance or expectation conflict, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1895 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that opposition, grievance or expectation conflict, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1896 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that opposition, grievance or expectation conflict, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Stakeholder Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1897 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that opposition, grievance or expectation conflict, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Stakeholder Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1898 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that opposition, grievance or expectation conflict, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Stakeholder Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1899 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that opposition, grievance or expectation conflict, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Stakeholder Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1900 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that opposition, grievance or expectation conflict, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Stakeholder & Community | EPCM | Pumped Storage | Latin America | Detailed Engineering | Employer | M | Time / Cost | Establish controls for opposition, grievance or expectation conflict; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Stakeholder Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1901 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that late acquisition, easement dispute or access denial, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1902 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that late acquisition, easement dispute or access denial, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1903 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that late acquisition, easement dispute or access denial, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1904 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that late acquisition, easement dispute or access denial, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Grid Interconnection | Offshore Wind | North America | Procurement | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1905 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that late acquisition, easement dispute or access denial, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1906 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that late acquisition, easement dispute or access denial, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1907 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that late acquisition, easement dispute or access denial, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1908 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that late acquisition, easement dispute or access denial, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1909 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that late acquisition, easement dispute or access denial, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPC / Turnkey | Hydropower | Latin America | Construction | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1910 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that late acquisition, easement dispute or access denial, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Installation | Nuclear Power | Global / Multi-country | Installation | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1911 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that late acquisition, easement dispute or access denial, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | R&D / Technology Development | Geothermal | Africa | Manufacturing | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1912 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that late acquisition, easement dispute or access denial, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Brownfield Modification | LNG | East Asia | Construction | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1913 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that late acquisition, easement dispute or access denial, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Owner’s Engineering | Onshore Wind | North America | Installation | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1914 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that late acquisition, easement dispute or access denial, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1915 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that late acquisition, easement dispute or access denial, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1916 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that late acquisition, easement dispute or access denial, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Installation | Battery Energy Storage | South Asia | Installation | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1917 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that late acquisition, easement dispute or access denial, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1918 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that late acquisition, easement dispute or access denial, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1919 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that late acquisition, easement dispute or access denial, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1920 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that late acquisition, easement dispute or access denial, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1921 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that late acquisition, easement dispute or access denial, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1922 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that late acquisition, easement dispute or access denial, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Decommissioning | Marine Energy | North America | Operations / Handover | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1923 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that late acquisition, easement dispute or access denial, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1924 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that late acquisition, easement dispute or access denial, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Installation | LNG | Europe | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1925 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that late acquisition, easement dispute or access denial, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1926 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that late acquisition, easement dispute or access denial, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1927 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that late acquisition, easement dispute or access denial, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1928 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that late acquisition, easement dispute or access denial, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1929 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that late acquisition, easement dispute or access denial, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1930 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that late acquisition, easement dispute or access denial, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1931 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that late acquisition, easement dispute or access denial, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Operations & Maintenance | District Energy | North America | Detailed Engineering | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1932 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that late acquisition, easement dispute or access denial, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Grid Interconnection | Pumped Storage | Oceania | Procurement | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1933 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that late acquisition, easement dispute or access denial, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1934 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that late acquisition, easement dispute or access denial, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Brownfield Modification | Marine Energy | Africa | Construction | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1935 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that late acquisition, easement dispute or access denial, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Owner’s Engineering | Geothermal | East Asia | Installation | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1936 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that late acquisition, easement dispute or access denial, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Decommissioning | Offshore Wind | Latin America | Manufacturing | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1937 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that late acquisition, easement dispute or access denial, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1938 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that late acquisition, easement dispute or access denial, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Installation | Refining & Petrochemicals | Middle East | Installation | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1939 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that late acquisition, easement dispute or access denial, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1940 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that late acquisition, easement dispute or access denial, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1941 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that late acquisition, easement dispute or access denial, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Owner’s Engineering | Hydropower | Oceania | Installation | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1942 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that late acquisition, easement dispute or access denial, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPCM | Nuclear Power | Europe | Pre-commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1943 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that late acquisition, easement dispute or access denial, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Commissioning & Start-up | District Energy | Africa | Commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1944 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that late acquisition, easement dispute or access denial, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1945 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that late acquisition, easement dispute or access denial, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1946 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that late acquisition, easement dispute or access denial, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1947 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that late acquisition, easement dispute or access denial, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1948 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that late acquisition, easement dispute or access denial, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1949 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that late acquisition, easement dispute or access denial, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1950 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that late acquisition, easement dispute or access denial, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1951 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that late acquisition, easement dispute or access denial, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1952 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that late acquisition, easement dispute or access denial, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1953 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that late acquisition, easement dispute or access denial, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1954 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that late acquisition, easement dispute or access denial, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Grid Interconnection | Nuclear Power | North America | Procurement | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1955 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that late acquisition, easement dispute or access denial, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | R&D / Technology Development | District Energy | Oceania | Manufacturing | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1956 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that late acquisition, easement dispute or access denial, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPCM | LNG | Middle East | Detailed Engineering | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1957 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that late acquisition, easement dispute or access denial, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1958 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that late acquisition, easement dispute or access denial, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1959 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that late acquisition, easement dispute or access denial, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1960 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that late acquisition, easement dispute or access denial, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Installation | Offshore Wind | Global / Multi-country | Installation | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1961 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that late acquisition, easement dispute or access denial, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1962 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that late acquisition, easement dispute or access denial, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1963 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that late acquisition, easement dispute or access denial, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Owner’s Engineering | Transmission & Substations | North America | Installation | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1964 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that late acquisition, easement dispute or access denial, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1965 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that late acquisition, easement dispute or access denial, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Commissioning & Start-up | Hydropower | Europe | Commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1966 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that late acquisition, easement dispute or access denial, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Installation | Marine Energy | South Asia | Installation | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1967 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that late acquisition, easement dispute or access denial, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1968 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that late acquisition, easement dispute or access denial, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Grid Interconnection | LNG | Latin America | Commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1969 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that late acquisition, easement dispute or access denial, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1970 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that late acquisition, easement dispute or access denial, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1971 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that late acquisition, easement dispute or access denial, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1972 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that late acquisition, easement dispute or access denial, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1973 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that late acquisition, easement dispute or access denial, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1974 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that late acquisition, easement dispute or access denial, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1975 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that late acquisition, easement dispute or access denial, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1976 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that late acquisition, easement dispute or access denial, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1977 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that late acquisition, easement dispute or access denial, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1978 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that late acquisition, easement dispute or access denial, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1979 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that late acquisition, easement dispute or access denial, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Commissioning & Start-up | Geothermal | Middle East | Procurement | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1980 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that late acquisition, easement dispute or access denial, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Decommissioning | LNG | South Asia | Manufacturing | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1981 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that late acquisition, easement dispute or access denial, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1982 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that late acquisition, easement dispute or access denial, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1983 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that late acquisition, easement dispute or access denial, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | R&D / Technology Development | Solar PV | Europe | Manufacturing | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1984 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that late acquisition, easement dispute or access denial, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Brownfield Modification | Battery Energy Storage | Africa | Construction | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1985 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that late acquisition, easement dispute or access denial, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1986 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that late acquisition, easement dispute or access denial, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Decommissioning | Nuclear Power | Latin America | Manufacturing | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1987 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that late acquisition, easement dispute or access denial, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1988 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that late acquisition, easement dispute or access denial, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Installation | Pumped Storage | Middle East | Installation | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1989 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that late acquisition, easement dispute or access denial, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1990 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that late acquisition, easement dispute or access denial, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1991 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that late acquisition, easement dispute or access denial, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1992 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that late acquisition, easement dispute or access denial, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPCM | Offshore Wind | Europe | Pre-commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1993 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that late acquisition, easement dispute or access denial, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1994 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that late acquisition, easement dispute or access denial, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1995 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that late acquisition, easement dispute or access denial, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1996 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that late acquisition, easement dispute or access denial, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Land Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1997 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that late acquisition, easement dispute or access denial, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Land Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1998 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that late acquisition, easement dispute or access denial, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Land Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-1999 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that late acquisition, easement dispute or access denial, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Land Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2000 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that late acquisition, easement dispute or access denial, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Land & Right of Way | EPCM | Pumped Storage | Latin America | Detailed Engineering | Employer | M | Time / Cost | Establish controls for late acquisition, easement dispute or access denial; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Land Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2001 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that late certification, funding constraint or withholding, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2002 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that late certification, funding constraint or withholding, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2003 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that late certification, funding constraint or withholding, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2004 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that late certification, funding constraint or withholding, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Grid Interconnection | Offshore Wind | North America | Procurement | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2005 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that late certification, funding constraint or withholding, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2006 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that late certification, funding constraint or withholding, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2007 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that late certification, funding constraint or withholding, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2008 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that late certification, funding constraint or withholding, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2009 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that late certification, funding constraint or withholding, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPC / Turnkey | Hydropower | Latin America | Construction | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2010 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that late certification, funding constraint or withholding, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Installation | Nuclear Power | Global / Multi-country | Installation | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2011 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that late certification, funding constraint or withholding, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | R&D / Technology Development | Geothermal | Africa | Manufacturing | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2012 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that late certification, funding constraint or withholding, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Brownfield Modification | LNG | East Asia | Construction | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2013 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that late certification, funding constraint or withholding, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Owner’s Engineering | Onshore Wind | North America | Installation | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2014 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that late certification, funding constraint or withholding, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2015 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that late certification, funding constraint or withholding, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2016 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that late certification, funding constraint or withholding, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Installation | Battery Energy Storage | South Asia | Installation | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2017 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that late certification, funding constraint or withholding, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2018 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that late certification, funding constraint or withholding, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2019 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that late certification, funding constraint or withholding, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2020 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that late certification, funding constraint or withholding, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2021 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that late certification, funding constraint or withholding, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2022 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that late certification, funding constraint or withholding, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Decommissioning | Marine Energy | North America | Operations / Handover | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2023 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that late certification, funding constraint or withholding, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2024 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that late certification, funding constraint or withholding, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Installation | LNG | Europe | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2025 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that late certification, funding constraint or withholding, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2026 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that late certification, funding constraint or withholding, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2027 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that late certification, funding constraint or withholding, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2028 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that late certification, funding constraint or withholding, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2029 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that late certification, funding constraint or withholding, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2030 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that late certification, funding constraint or withholding, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2031 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that late certification, funding constraint or withholding, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Operations & Maintenance | District Energy | North America | Detailed Engineering | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2032 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that late certification, funding constraint or withholding, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Grid Interconnection | Pumped Storage | Oceania | Procurement | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2033 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that late certification, funding constraint or withholding, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2034 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that late certification, funding constraint or withholding, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Brownfield Modification | Marine Energy | Africa | Construction | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2035 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that late certification, funding constraint or withholding, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Owner’s Engineering | Geothermal | East Asia | Installation | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2036 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that late certification, funding constraint or withholding, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Decommissioning | Offshore Wind | Latin America | Manufacturing | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2037 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that late certification, funding constraint or withholding, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2038 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that late certification, funding constraint or withholding, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Installation | Refining & Petrochemicals | Middle East | Installation | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2039 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that late certification, funding constraint or withholding, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2040 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that late certification, funding constraint or withholding, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2041 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that late certification, funding constraint or withholding, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Owner’s Engineering | Hydropower | Oceania | Installation | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2042 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that late certification, funding constraint or withholding, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPCM | Nuclear Power | Europe | Pre-commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2043 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that late certification, funding constraint or withholding, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Commissioning & Start-up | District Energy | Africa | Commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2044 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that late certification, funding constraint or withholding, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2045 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that late certification, funding constraint or withholding, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2046 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that late certification, funding constraint or withholding, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2047 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that late certification, funding constraint or withholding, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2048 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that late certification, funding constraint or withholding, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2049 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that late certification, funding constraint or withholding, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2050 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that late certification, funding constraint or withholding, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2051 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that late certification, funding constraint or withholding, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2052 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that late certification, funding constraint or withholding, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2053 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that late certification, funding constraint or withholding, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2054 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that late certification, funding constraint or withholding, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Grid Interconnection | Nuclear Power | North America | Procurement | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2055 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that late certification, funding constraint or withholding, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | R&D / Technology Development | District Energy | Oceania | Manufacturing | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2056 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that late certification, funding constraint or withholding, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPCM | LNG | Middle East | Detailed Engineering | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2057 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that late certification, funding constraint or withholding, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2058 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that late certification, funding constraint or withholding, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2059 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that late certification, funding constraint or withholding, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2060 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that late certification, funding constraint or withholding, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Installation | Offshore Wind | Global / Multi-country | Installation | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2061 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that late certification, funding constraint or withholding, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2062 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that late certification, funding constraint or withholding, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2063 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that late certification, funding constraint or withholding, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Owner’s Engineering | Transmission & Substations | North America | Installation | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2064 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that late certification, funding constraint or withholding, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2065 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that late certification, funding constraint or withholding, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Commissioning & Start-up | Hydropower | Europe | Commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2066 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that late certification, funding constraint or withholding, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Installation | Marine Energy | South Asia | Installation | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2067 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that late certification, funding constraint or withholding, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2068 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that late certification, funding constraint or withholding, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Grid Interconnection | LNG | Latin America | Commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2069 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that late certification, funding constraint or withholding, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2070 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that late certification, funding constraint or withholding, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2071 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that late certification, funding constraint or withholding, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2072 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that late certification, funding constraint or withholding, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2073 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that late certification, funding constraint or withholding, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2074 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that late certification, funding constraint or withholding, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2075 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that late certification, funding constraint or withholding, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2076 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that late certification, funding constraint or withholding, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2077 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that late certification, funding constraint or withholding, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2078 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that late certification, funding constraint or withholding, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2079 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that late certification, funding constraint or withholding, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Commissioning & Start-up | Geothermal | Middle East | Procurement | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2080 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that late certification, funding constraint or withholding, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Decommissioning | LNG | South Asia | Manufacturing | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2081 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that late certification, funding constraint or withholding, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2082 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that late certification, funding constraint or withholding, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2083 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that late certification, funding constraint or withholding, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | R&D / Technology Development | Solar PV | Europe | Manufacturing | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2084 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that late certification, funding constraint or withholding, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Brownfield Modification | Battery Energy Storage | Africa | Construction | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2085 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that late certification, funding constraint or withholding, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2086 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that late certification, funding constraint or withholding, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Decommissioning | Nuclear Power | Latin America | Manufacturing | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2087 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that late certification, funding constraint or withholding, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2088 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that late certification, funding constraint or withholding, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Installation | Pumped Storage | Middle East | Installation | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2089 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that late certification, funding constraint or withholding, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2090 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that late certification, funding constraint or withholding, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2091 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that late certification, funding constraint or withholding, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2092 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that late certification, funding constraint or withholding, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPCM | Offshore Wind | Europe | Pre-commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2093 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that late certification, funding constraint or withholding, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2094 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that late certification, funding constraint or withholding, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2095 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that late certification, funding constraint or withholding, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2096 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that late certification, funding constraint or withholding, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commercial Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2097 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that late certification, funding constraint or withholding, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commercial Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2098 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that late certification, funding constraint or withholding, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commercial Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2099 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that late certification, funding constraint or withholding, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commercial Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2100 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that late certification, funding constraint or withholding, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Payment & Cash Flow | EPCM | Pumped Storage | Latin America | Detailed Engineering | Employer | M | Cost / Time | Establish controls for late certification, funding constraint or withholding; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commercial Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2101 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that late notice, poor records or valuation disagreement, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2102 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that late notice, poor records or valuation disagreement, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2103 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that late notice, poor records or valuation disagreement, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2104 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that late notice, poor records or valuation disagreement, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Grid Interconnection | Offshore Wind | North America | Procurement | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2105 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that late notice, poor records or valuation disagreement, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2106 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that late notice, poor records or valuation disagreement, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2107 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that late notice, poor records or valuation disagreement, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2108 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that late notice, poor records or valuation disagreement, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2109 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that late notice, poor records or valuation disagreement, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPC / Turnkey | Hydropower | Latin America | Construction | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2110 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that late notice, poor records or valuation disagreement, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Installation | Nuclear Power | Global / Multi-country | Installation | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2111 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that late notice, poor records or valuation disagreement, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | R&D / Technology Development | Geothermal | Africa | Manufacturing | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2112 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that late notice, poor records or valuation disagreement, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Brownfield Modification | LNG | East Asia | Construction | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2113 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that late notice, poor records or valuation disagreement, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Owner’s Engineering | Onshore Wind | North America | Installation | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2114 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that late notice, poor records or valuation disagreement, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2115 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that late notice, poor records or valuation disagreement, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2116 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that late notice, poor records or valuation disagreement, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Installation | Battery Energy Storage | South Asia | Installation | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2117 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that late notice, poor records or valuation disagreement, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2118 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that late notice, poor records or valuation disagreement, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2119 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that late notice, poor records or valuation disagreement, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2120 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that late notice, poor records or valuation disagreement, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2121 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that late notice, poor records or valuation disagreement, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2122 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that late notice, poor records or valuation disagreement, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Decommissioning | Marine Energy | North America | Operations / Handover | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2123 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that late notice, poor records or valuation disagreement, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2124 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that late notice, poor records or valuation disagreement, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Installation | LNG | Europe | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2125 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that late notice, poor records or valuation disagreement, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2126 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that late notice, poor records or valuation disagreement, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2127 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that late notice, poor records or valuation disagreement, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2128 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that late notice, poor records or valuation disagreement, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2129 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that late notice, poor records or valuation disagreement, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2130 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that late notice, poor records or valuation disagreement, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2131 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that late notice, poor records or valuation disagreement, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Operations & Maintenance | District Energy | North America | Detailed Engineering | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2132 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that late notice, poor records or valuation disagreement, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Grid Interconnection | Pumped Storage | Oceania | Procurement | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2133 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that late notice, poor records or valuation disagreement, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2134 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that late notice, poor records or valuation disagreement, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Brownfield Modification | Marine Energy | Africa | Construction | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2135 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that late notice, poor records or valuation disagreement, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Owner’s Engineering | Geothermal | East Asia | Installation | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2136 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that late notice, poor records or valuation disagreement, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Decommissioning | Offshore Wind | Latin America | Manufacturing | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2137 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that late notice, poor records or valuation disagreement, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2138 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that late notice, poor records or valuation disagreement, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Installation | Refining & Petrochemicals | Middle East | Installation | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2139 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that late notice, poor records or valuation disagreement, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2140 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that late notice, poor records or valuation disagreement, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2141 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that late notice, poor records or valuation disagreement, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Owner’s Engineering | Hydropower | Oceania | Installation | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2142 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that late notice, poor records or valuation disagreement, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPCM | Nuclear Power | Europe | Pre-commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2143 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that late notice, poor records or valuation disagreement, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Commissioning & Start-up | District Energy | Africa | Commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2144 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that late notice, poor records or valuation disagreement, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2145 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that late notice, poor records or valuation disagreement, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2146 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that late notice, poor records or valuation disagreement, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2147 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that late notice, poor records or valuation disagreement, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2148 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that late notice, poor records or valuation disagreement, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2149 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that late notice, poor records or valuation disagreement, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2150 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that late notice, poor records or valuation disagreement, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2151 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that late notice, poor records or valuation disagreement, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2152 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that late notice, poor records or valuation disagreement, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2153 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that late notice, poor records or valuation disagreement, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2154 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that late notice, poor records or valuation disagreement, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Grid Interconnection | Nuclear Power | North America | Procurement | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2155 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that late notice, poor records or valuation disagreement, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | R&D / Technology Development | District Energy | Oceania | Manufacturing | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2156 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that late notice, poor records or valuation disagreement, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPCM | LNG | Middle East | Detailed Engineering | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2157 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that late notice, poor records or valuation disagreement, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2158 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that late notice, poor records or valuation disagreement, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2159 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that late notice, poor records or valuation disagreement, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2160 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that late notice, poor records or valuation disagreement, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Installation | Offshore Wind | Global / Multi-country | Installation | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2161 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that late notice, poor records or valuation disagreement, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2162 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that late notice, poor records or valuation disagreement, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2163 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that late notice, poor records or valuation disagreement, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Owner’s Engineering | Transmission & Substations | North America | Installation | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2164 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that late notice, poor records or valuation disagreement, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2165 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that late notice, poor records or valuation disagreement, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Commissioning & Start-up | Hydropower | Europe | Commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2166 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that late notice, poor records or valuation disagreement, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Installation | Marine Energy | South Asia | Installation | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2167 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that late notice, poor records or valuation disagreement, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2168 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that late notice, poor records or valuation disagreement, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Grid Interconnection | LNG | Latin America | Commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2169 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that late notice, poor records or valuation disagreement, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2170 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that late notice, poor records or valuation disagreement, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2171 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that late notice, poor records or valuation disagreement, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2172 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that late notice, poor records or valuation disagreement, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2173 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that late notice, poor records or valuation disagreement, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2174 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that late notice, poor records or valuation disagreement, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2175 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that late notice, poor records or valuation disagreement, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2176 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that late notice, poor records or valuation disagreement, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2177 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that late notice, poor records or valuation disagreement, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2178 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that late notice, poor records or valuation disagreement, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2179 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that late notice, poor records or valuation disagreement, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Commissioning & Start-up | Geothermal | Middle East | Procurement | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2180 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that late notice, poor records or valuation disagreement, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Decommissioning | LNG | South Asia | Manufacturing | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2181 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that late notice, poor records or valuation disagreement, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2182 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that late notice, poor records or valuation disagreement, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2183 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that late notice, poor records or valuation disagreement, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | R&D / Technology Development | Solar PV | Europe | Manufacturing | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2184 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that late notice, poor records or valuation disagreement, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Brownfield Modification | Battery Energy Storage | Africa | Construction | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2185 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that late notice, poor records or valuation disagreement, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2186 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that late notice, poor records or valuation disagreement, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Decommissioning | Nuclear Power | Latin America | Manufacturing | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2187 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that late notice, poor records or valuation disagreement, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2188 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that late notice, poor records or valuation disagreement, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Installation | Pumped Storage | Middle East | Installation | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2189 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that late notice, poor records or valuation disagreement, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2190 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that late notice, poor records or valuation disagreement, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2191 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that late notice, poor records or valuation disagreement, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2192 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that late notice, poor records or valuation disagreement, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPCM | Offshore Wind | Europe | Pre-commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2193 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that late notice, poor records or valuation disagreement, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2194 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that late notice, poor records or valuation disagreement, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2195 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that late notice, poor records or valuation disagreement, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2196 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that late notice, poor records or valuation disagreement, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Claims Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2197 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that late notice, poor records or valuation disagreement, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Claims Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2198 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that late notice, poor records or valuation disagreement, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Claims Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2199 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that late notice, poor records or valuation disagreement, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Claims Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2200 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that late notice, poor records or valuation disagreement, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Claims & Disputes | EPCM | Pumped Storage | Latin America | Detailed Engineering | Shared | M | Cost / Time | Establish controls for late notice, poor records or valuation disagreement; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Claims Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2201 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that scope creep, late change or uncontrolled instruction, combined with insufficient planning, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2202 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that scope creep, late change or uncontrolled instruction, combined with insufficient planning, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2203 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that scope creep, late change or uncontrolled instruction, combined with insufficient planning, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2204 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that scope creep, late change or uncontrolled instruction, combined with insufficient planning, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Grid Interconnection | Offshore Wind | North America | Procurement | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2205 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that scope creep, late change or uncontrolled instruction, combined with insufficient planning, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2206 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that scope creep, late change or uncontrolled instruction, combined with incomplete information, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2207 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that scope creep, late change or uncontrolled instruction, combined with incomplete information, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2208 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that scope creep, late change or uncontrolled instruction, combined with incomplete information, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2209 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that scope creep, late change or uncontrolled instruction, combined with incomplete information, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPC / Turnkey | Hydropower | Latin America | Construction | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2210 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that scope creep, late change or uncontrolled instruction, combined with incomplete information, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Installation | Nuclear Power | Global / Multi-country | Installation | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2211 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that scope creep, late change or uncontrolled instruction, combined with late decision-making, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | R&D / Technology Development | Geothermal | Africa | Manufacturing | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2212 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that scope creep, late change or uncontrolled instruction, combined with late decision-making, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Brownfield Modification | LNG | East Asia | Construction | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2213 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that scope creep, late change or uncontrolled instruction, combined with late decision-making, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Owner’s Engineering | Onshore Wind | North America | Installation | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2214 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that scope creep, late change or uncontrolled instruction, combined with late decision-making, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2215 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that scope creep, late change or uncontrolled instruction, combined with late decision-making, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2216 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that scope creep, late change or uncontrolled instruction, combined with weak controls, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Installation | Battery Energy Storage | South Asia | Installation | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2217 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that scope creep, late change or uncontrolled instruction, combined with weak controls, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2218 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that scope creep, late change or uncontrolled instruction, combined with weak controls, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2219 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that scope creep, late change or uncontrolled instruction, combined with weak controls, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2220 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that scope creep, late change or uncontrolled instruction, combined with weak controls, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2221 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that scope creep, late change or uncontrolled instruction, combined with resource constraints, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2222 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that scope creep, late change or uncontrolled instruction, combined with resource constraints, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Decommissioning | Marine Energy | North America | Operations / Handover | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2223 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that scope creep, late change or uncontrolled instruction, combined with resource constraints, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2224 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that scope creep, late change or uncontrolled instruction, combined with resource constraints, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Installation | LNG | Europe | FEED / Basic Design | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2225 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that scope creep, late change or uncontrolled instruction, combined with resource constraints, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2226 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that scope creep, late change or uncontrolled instruction, combined with supplier dependency, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2227 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that scope creep, late change or uncontrolled instruction, combined with supplier dependency, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2228 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that scope creep, late change or uncontrolled instruction, combined with supplier dependency, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2229 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that scope creep, late change or uncontrolled instruction, combined with supplier dependency, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2230 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that scope creep, late change or uncontrolled instruction, combined with supplier dependency, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2231 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that scope creep, late change or uncontrolled instruction, combined with interface complexity, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Operations & Maintenance | District Energy | North America | Detailed Engineering | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2232 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that scope creep, late change or uncontrolled instruction, combined with interface complexity, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Grid Interconnection | Pumped Storage | Oceania | Procurement | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2233 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that scope creep, late change or uncontrolled instruction, combined with interface complexity, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2234 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that scope creep, late change or uncontrolled instruction, combined with interface complexity, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Brownfield Modification | Marine Energy | Africa | Construction | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2235 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that scope creep, late change or uncontrolled instruction, combined with interface complexity, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Owner’s Engineering | Geothermal | East Asia | Installation | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2236 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that scope creep, late change or uncontrolled instruction, combined with requirements volatility, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Decommissioning | Offshore Wind | Latin America | Manufacturing | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2237 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that scope creep, late change or uncontrolled instruction, combined with requirements volatility, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2238 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that scope creep, late change or uncontrolled instruction, combined with requirements volatility, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Installation | Refining & Petrochemicals | Middle East | Installation | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2239 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that scope creep, late change or uncontrolled instruction, combined with requirements volatility, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2240 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that scope creep, late change or uncontrolled instruction, combined with requirements volatility, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2241 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that scope creep, late change or uncontrolled instruction, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Owner’s Engineering | Hydropower | Oceania | Installation | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2242 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that scope creep, late change or uncontrolled instruction, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPCM | Nuclear Power | Europe | Pre-commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2243 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that scope creep, late change or uncontrolled instruction, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Commissioning & Start-up | District Energy | Africa | Commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2244 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that scope creep, late change or uncontrolled instruction, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2245 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that scope creep, late change or uncontrolled instruction, combined with regulatory uncertainty, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2246 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that scope creep, late change or uncontrolled instruction, combined with inadequate verification, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2247 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that scope creep, late change or uncontrolled instruction, combined with inadequate verification, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2248 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that scope creep, late change or uncontrolled instruction, combined with inadequate verification, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2249 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that scope creep, late change or uncontrolled instruction, combined with inadequate verification, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2250 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that scope creep, late change or uncontrolled instruction, combined with inadequate verification, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2251 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that scope creep, late change or uncontrolled instruction, combined with poor communication, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2252 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that scope creep, late change or uncontrolled instruction, combined with poor communication, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2253 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that scope creep, late change or uncontrolled instruction, combined with poor communication, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2254 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that scope creep, late change or uncontrolled instruction, combined with poor communication, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Grid Interconnection | Nuclear Power | North America | Procurement | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2255 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that scope creep, late change or uncontrolled instruction, combined with poor communication, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | R&D / Technology Development | District Energy | Oceania | Manufacturing | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2256 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that scope creep, late change or uncontrolled instruction, combined with incorrect assumptions, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPCM | LNG | Middle East | Detailed Engineering | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2257 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that scope creep, late change or uncontrolled instruction, combined with incorrect assumptions, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2258 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that scope creep, late change or uncontrolled instruction, combined with incorrect assumptions, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2259 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that scope creep, late change or uncontrolled instruction, combined with incorrect assumptions, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2260 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that scope creep, late change or uncontrolled instruction, combined with incorrect assumptions, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Installation | Offshore Wind | Global / Multi-country | Installation | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2261 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that scope creep, late change or uncontrolled instruction, combined with low technical maturity, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2262 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that scope creep, late change or uncontrolled instruction, combined with low technical maturity, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2263 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that scope creep, late change or uncontrolled instruction, combined with low technical maturity, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Owner’s Engineering | Transmission & Substations | North America | Installation | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2264 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that scope creep, late change or uncontrolled instruction, combined with low technical maturity, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2265 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that scope creep, late change or uncontrolled instruction, combined with low technical maturity, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Commissioning & Start-up | Hydropower | Europe | Commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2266 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that scope creep, late change or uncontrolled instruction, combined with documentation gaps, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Installation | Marine Energy | South Asia | Installation | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2267 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that scope creep, late change or uncontrolled instruction, combined with documentation gaps, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2268 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that scope creep, late change or uncontrolled instruction, combined with documentation gaps, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Grid Interconnection | LNG | Latin America | Commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2269 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that scope creep, late change or uncontrolled instruction, combined with documentation gaps, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2270 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that scope creep, late change or uncontrolled instruction, combined with documentation gaps, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2271 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that scope creep, late change or uncontrolled instruction, combined with external disruption, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2272 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that scope creep, late change or uncontrolled instruction, combined with external disruption, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2273 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that scope creep, late change or uncontrolled instruction, combined with external disruption, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2274 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that scope creep, late change or uncontrolled instruction, combined with external disruption, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2275 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that scope creep, late change or uncontrolled instruction, combined with external disruption, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2276 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that scope creep, late change or uncontrolled instruction, combined with governance delay, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2277 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that scope creep, late change or uncontrolled instruction, combined with governance delay, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2278 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that scope creep, late change or uncontrolled instruction, combined with governance delay, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2279 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that scope creep, late change or uncontrolled instruction, combined with governance delay, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Commissioning & Start-up | Geothermal | Middle East | Procurement | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2280 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that scope creep, late change or uncontrolled instruction, combined with governance delay, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Decommissioning | LNG | South Asia | Manufacturing | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2281 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that scope creep, late change or uncontrolled instruction, combined with commercial misalignment, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2282 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that scope creep, late change or uncontrolled instruction, combined with commercial misalignment, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2283 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that scope creep, late change or uncontrolled instruction, combined with commercial misalignment, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | R&D / Technology Development | Solar PV | Europe | Manufacturing | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2284 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that scope creep, late change or uncontrolled instruction, combined with commercial misalignment, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Brownfield Modification | Battery Energy Storage | Africa | Construction | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2285 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that scope creep, late change or uncontrolled instruction, combined with commercial misalignment, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2286 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that scope creep, late change or uncontrolled instruction, combined with quality escape, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Decommissioning | Nuclear Power | Latin America | Manufacturing | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2287 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that scope creep, late change or uncontrolled instruction, combined with quality escape, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2288 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that scope creep, late change or uncontrolled instruction, combined with quality escape, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Installation | Pumped Storage | Middle East | Installation | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2289 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that scope creep, late change or uncontrolled instruction, combined with quality escape, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2290 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that scope creep, late change or uncontrolled instruction, combined with quality escape, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2291 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that scope creep, late change or uncontrolled instruction, combined with access constraint, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2292 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that scope creep, late change or uncontrolled instruction, combined with access constraint, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPCM | Offshore Wind | Europe | Pre-commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2293 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that scope creep, late change or uncontrolled instruction, combined with access constraint, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2294 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that scope creep, late change or uncontrolled instruction, combined with access constraint, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2295 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that scope creep, late change or uncontrolled instruction, combined with access constraint, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2296 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that scope creep, late change or uncontrolled instruction, combined with performance variability, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Change Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2297 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that scope creep, late change or uncontrolled instruction, combined with performance variability, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Change Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2298 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that scope creep, late change or uncontrolled instruction, combined with performance variability, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Change Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2299 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that scope creep, late change or uncontrolled instruction, combined with performance variability, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Change Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2300 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that scope creep, late change or uncontrolled instruction, combined with performance variability, may adversely affect project objectives through cost / time / quality consequences. | Change & Scope | EPCM | Pumped Storage | Latin America | Detailed Engineering | Employer | H | Cost / Time / Quality | Establish controls for scope creep, late change or uncontrolled instruction; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Change Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2301 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that unproven technology, prototype failure or obsolescence, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2302 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that unproven technology, prototype failure or obsolescence, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2303 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that unproven technology, prototype failure or obsolescence, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2304 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that unproven technology, prototype failure or obsolescence, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Grid Interconnection | Offshore Wind | North America | Procurement | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2305 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that unproven technology, prototype failure or obsolescence, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2306 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that unproven technology, prototype failure or obsolescence, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2307 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that unproven technology, prototype failure or obsolescence, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2308 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that unproven technology, prototype failure or obsolescence, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2309 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that unproven technology, prototype failure or obsolescence, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPC / Turnkey | Hydropower | Latin America | Construction | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2310 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that unproven technology, prototype failure or obsolescence, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Installation | Nuclear Power | Global / Multi-country | Installation | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2311 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that unproven technology, prototype failure or obsolescence, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | R&D / Technology Development | Geothermal | Africa | Manufacturing | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2312 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that unproven technology, prototype failure or obsolescence, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Brownfield Modification | LNG | East Asia | Construction | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2313 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that unproven technology, prototype failure or obsolescence, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Owner’s Engineering | Onshore Wind | North America | Installation | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2314 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that unproven technology, prototype failure or obsolescence, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2315 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that unproven technology, prototype failure or obsolescence, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2316 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that unproven technology, prototype failure or obsolescence, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Installation | Battery Energy Storage | South Asia | Installation | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2317 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that unproven technology, prototype failure or obsolescence, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2318 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that unproven technology, prototype failure or obsolescence, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2319 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that unproven technology, prototype failure or obsolescence, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2320 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that unproven technology, prototype failure or obsolescence, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2321 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that unproven technology, prototype failure or obsolescence, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2322 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that unproven technology, prototype failure or obsolescence, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Decommissioning | Marine Energy | North America | Operations / Handover | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2323 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that unproven technology, prototype failure or obsolescence, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2324 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that unproven technology, prototype failure or obsolescence, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Installation | LNG | Europe | FEED / Basic Design | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2325 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that unproven technology, prototype failure or obsolescence, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2326 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that unproven technology, prototype failure or obsolescence, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2327 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that unproven technology, prototype failure or obsolescence, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2328 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that unproven technology, prototype failure or obsolescence, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2329 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that unproven technology, prototype failure or obsolescence, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2330 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that unproven technology, prototype failure or obsolescence, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2331 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that unproven technology, prototype failure or obsolescence, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Operations & Maintenance | District Energy | North America | Detailed Engineering | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2332 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that unproven technology, prototype failure or obsolescence, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Grid Interconnection | Pumped Storage | Oceania | Procurement | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2333 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that unproven technology, prototype failure or obsolescence, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2334 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that unproven technology, prototype failure or obsolescence, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Brownfield Modification | Marine Energy | Africa | Construction | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2335 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that unproven technology, prototype failure or obsolescence, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Owner’s Engineering | Geothermal | East Asia | Installation | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2336 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that unproven technology, prototype failure or obsolescence, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Decommissioning | Offshore Wind | Latin America | Manufacturing | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2337 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that unproven technology, prototype failure or obsolescence, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2338 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that unproven technology, prototype failure or obsolescence, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Installation | Refining & Petrochemicals | Middle East | Installation | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2339 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that unproven technology, prototype failure or obsolescence, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2340 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that unproven technology, prototype failure or obsolescence, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2341 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that unproven technology, prototype failure or obsolescence, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Owner’s Engineering | Hydropower | Oceania | Installation | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2342 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that unproven technology, prototype failure or obsolescence, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPCM | Nuclear Power | Europe | Pre-commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2343 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that unproven technology, prototype failure or obsolescence, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Commissioning & Start-up | District Energy | Africa | Commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2344 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that unproven technology, prototype failure or obsolescence, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2345 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that unproven technology, prototype failure or obsolescence, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2346 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that unproven technology, prototype failure or obsolescence, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2347 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that unproven technology, prototype failure or obsolescence, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2348 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that unproven technology, prototype failure or obsolescence, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2349 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that unproven technology, prototype failure or obsolescence, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2350 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that unproven technology, prototype failure or obsolescence, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2351 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that unproven technology, prototype failure or obsolescence, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2352 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that unproven technology, prototype failure or obsolescence, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2353 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that unproven technology, prototype failure or obsolescence, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2354 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that unproven technology, prototype failure or obsolescence, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Grid Interconnection | Nuclear Power | North America | Procurement | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2355 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that unproven technology, prototype failure or obsolescence, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | R&D / Technology Development | District Energy | Oceania | Manufacturing | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2356 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that unproven technology, prototype failure or obsolescence, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPCM | LNG | Middle East | Detailed Engineering | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2357 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that unproven technology, prototype failure or obsolescence, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2358 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that unproven technology, prototype failure or obsolescence, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2359 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that unproven technology, prototype failure or obsolescence, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2360 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that unproven technology, prototype failure or obsolescence, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Installation | Offshore Wind | Global / Multi-country | Installation | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2361 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that unproven technology, prototype failure or obsolescence, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2362 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that unproven technology, prototype failure or obsolescence, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2363 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that unproven technology, prototype failure or obsolescence, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Owner’s Engineering | Transmission & Substations | North America | Installation | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2364 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that unproven technology, prototype failure or obsolescence, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2365 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that unproven technology, prototype failure or obsolescence, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Commissioning & Start-up | Hydropower | Europe | Commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2366 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that unproven technology, prototype failure or obsolescence, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Installation | Marine Energy | South Asia | Installation | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2367 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that unproven technology, prototype failure or obsolescence, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2368 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that unproven technology, prototype failure or obsolescence, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Grid Interconnection | LNG | Latin America | Commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2369 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that unproven technology, prototype failure or obsolescence, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2370 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that unproven technology, prototype failure or obsolescence, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2371 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that unproven technology, prototype failure or obsolescence, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2372 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that unproven technology, prototype failure or obsolescence, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2373 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that unproven technology, prototype failure or obsolescence, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2374 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that unproven technology, prototype failure or obsolescence, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2375 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that unproven technology, prototype failure or obsolescence, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2376 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that unproven technology, prototype failure or obsolescence, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2377 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that unproven technology, prototype failure or obsolescence, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2378 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that unproven technology, prototype failure or obsolescence, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2379 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that unproven technology, prototype failure or obsolescence, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Commissioning & Start-up | Geothermal | Middle East | Procurement | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2380 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that unproven technology, prototype failure or obsolescence, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Decommissioning | LNG | South Asia | Manufacturing | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2381 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that unproven technology, prototype failure or obsolescence, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2382 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that unproven technology, prototype failure or obsolescence, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2383 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that unproven technology, prototype failure or obsolescence, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | R&D / Technology Development | Solar PV | Europe | Manufacturing | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2384 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that unproven technology, prototype failure or obsolescence, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Brownfield Modification | Battery Energy Storage | Africa | Construction | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2385 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that unproven technology, prototype failure or obsolescence, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2386 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that unproven technology, prototype failure or obsolescence, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Decommissioning | Nuclear Power | Latin America | Manufacturing | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2387 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that unproven technology, prototype failure or obsolescence, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2388 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that unproven technology, prototype failure or obsolescence, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Installation | Pumped Storage | Middle East | Installation | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2389 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that unproven technology, prototype failure or obsolescence, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2390 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that unproven technology, prototype failure or obsolescence, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2391 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that unproven technology, prototype failure or obsolescence, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2392 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that unproven technology, prototype failure or obsolescence, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPCM | Offshore Wind | Europe | Pre-commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2393 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that unproven technology, prototype failure or obsolescence, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2394 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that unproven technology, prototype failure or obsolescence, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2395 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that unproven technology, prototype failure or obsolescence, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2396 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that unproven technology, prototype failure or obsolescence, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Technical Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2397 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that unproven technology, prototype failure or obsolescence, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Technical Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2398 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that unproven technology, prototype failure or obsolescence, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Technical Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2399 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that unproven technology, prototype failure or obsolescence, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Technical Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2400 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that unproven technology, prototype failure or obsolescence, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Technology & Maturity | EPCM | Pumped Storage | Latin America | Detailed Engineering | Contractor | M | Quality / Time / Cost | Establish controls for unproven technology, prototype failure or obsolescence; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Technical Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2401 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that cyberattack, data corruption or integration failure, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2402 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that cyberattack, data corruption or integration failure, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2403 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that cyberattack, data corruption or integration failure, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2404 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that cyberattack, data corruption or integration failure, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Grid Interconnection | Offshore Wind | North America | Procurement | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2405 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that cyberattack, data corruption or integration failure, combined with insufficient planning, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2406 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that cyberattack, data corruption or integration failure, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2407 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that cyberattack, data corruption or integration failure, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2408 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that cyberattack, data corruption or integration failure, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2409 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that cyberattack, data corruption or integration failure, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPC / Turnkey | Hydropower | Latin America | Construction | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2410 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that cyberattack, data corruption or integration failure, combined with incomplete information, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Installation | Nuclear Power | Global / Multi-country | Installation | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2411 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that cyberattack, data corruption or integration failure, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | R&D / Technology Development | Geothermal | Africa | Manufacturing | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2412 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that cyberattack, data corruption or integration failure, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Brownfield Modification | LNG | East Asia | Construction | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2413 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that cyberattack, data corruption or integration failure, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Owner’s Engineering | Onshore Wind | North America | Installation | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2414 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that cyberattack, data corruption or integration failure, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2415 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that cyberattack, data corruption or integration failure, combined with late decision-making, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2416 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that cyberattack, data corruption or integration failure, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Installation | Battery Energy Storage | South Asia | Installation | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2417 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that cyberattack, data corruption or integration failure, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2418 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that cyberattack, data corruption or integration failure, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2419 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that cyberattack, data corruption or integration failure, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2420 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that cyberattack, data corruption or integration failure, combined with weak controls, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2421 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that cyberattack, data corruption or integration failure, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2422 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that cyberattack, data corruption or integration failure, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Decommissioning | Marine Energy | North America | Operations / Handover | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2423 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that cyberattack, data corruption or integration failure, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2424 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that cyberattack, data corruption or integration failure, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Installation | LNG | Europe | FEED / Basic Design | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2425 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that cyberattack, data corruption or integration failure, combined with resource constraints, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2426 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that cyberattack, data corruption or integration failure, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2427 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that cyberattack, data corruption or integration failure, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2428 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that cyberattack, data corruption or integration failure, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2429 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that cyberattack, data corruption or integration failure, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2430 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that cyberattack, data corruption or integration failure, combined with supplier dependency, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2431 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that cyberattack, data corruption or integration failure, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Operations & Maintenance | District Energy | North America | Detailed Engineering | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2432 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that cyberattack, data corruption or integration failure, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Grid Interconnection | Pumped Storage | Oceania | Procurement | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2433 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that cyberattack, data corruption or integration failure, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2434 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that cyberattack, data corruption or integration failure, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Brownfield Modification | Marine Energy | Africa | Construction | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2435 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that cyberattack, data corruption or integration failure, combined with interface complexity, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Owner’s Engineering | Geothermal | East Asia | Installation | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2436 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that cyberattack, data corruption or integration failure, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Decommissioning | Offshore Wind | Latin America | Manufacturing | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2437 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that cyberattack, data corruption or integration failure, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2438 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that cyberattack, data corruption or integration failure, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Installation | Refining & Petrochemicals | Middle East | Installation | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2439 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that cyberattack, data corruption or integration failure, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2440 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that cyberattack, data corruption or integration failure, combined with requirements volatility, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2441 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that cyberattack, data corruption or integration failure, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Owner’s Engineering | Hydropower | Oceania | Installation | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2442 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that cyberattack, data corruption or integration failure, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPCM | Nuclear Power | Europe | Pre-commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2443 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that cyberattack, data corruption or integration failure, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Commissioning & Start-up | District Energy | Africa | Commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2444 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that cyberattack, data corruption or integration failure, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2445 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that cyberattack, data corruption or integration failure, combined with regulatory uncertainty, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2446 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that cyberattack, data corruption or integration failure, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2447 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that cyberattack, data corruption or integration failure, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2448 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that cyberattack, data corruption or integration failure, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2449 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that cyberattack, data corruption or integration failure, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2450 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that cyberattack, data corruption or integration failure, combined with inadequate verification, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2451 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that cyberattack, data corruption or integration failure, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2452 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that cyberattack, data corruption or integration failure, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2453 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that cyberattack, data corruption or integration failure, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2454 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that cyberattack, data corruption or integration failure, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Grid Interconnection | Nuclear Power | North America | Procurement | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2455 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that cyberattack, data corruption or integration failure, combined with poor communication, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | R&D / Technology Development | District Energy | Oceania | Manufacturing | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2456 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that cyberattack, data corruption or integration failure, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPCM | LNG | Middle East | Detailed Engineering | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2457 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that cyberattack, data corruption or integration failure, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2458 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that cyberattack, data corruption or integration failure, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2459 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that cyberattack, data corruption or integration failure, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2460 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that cyberattack, data corruption or integration failure, combined with incorrect assumptions, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Installation | Offshore Wind | Global / Multi-country | Installation | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2461 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that cyberattack, data corruption or integration failure, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2462 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that cyberattack, data corruption or integration failure, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2463 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that cyberattack, data corruption or integration failure, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Owner’s Engineering | Transmission & Substations | North America | Installation | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2464 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that cyberattack, data corruption or integration failure, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2465 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that cyberattack, data corruption or integration failure, combined with low technical maturity, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Commissioning & Start-up | Hydropower | Europe | Commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2466 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that cyberattack, data corruption or integration failure, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Installation | Marine Energy | South Asia | Installation | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2467 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that cyberattack, data corruption or integration failure, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2468 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that cyberattack, data corruption or integration failure, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Grid Interconnection | LNG | Latin America | Commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2469 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that cyberattack, data corruption or integration failure, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2470 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that cyberattack, data corruption or integration failure, combined with documentation gaps, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2471 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that cyberattack, data corruption or integration failure, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2472 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that cyberattack, data corruption or integration failure, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2473 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that cyberattack, data corruption or integration failure, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2474 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that cyberattack, data corruption or integration failure, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2475 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that cyberattack, data corruption or integration failure, combined with external disruption, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2476 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that cyberattack, data corruption or integration failure, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2477 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that cyberattack, data corruption or integration failure, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2478 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that cyberattack, data corruption or integration failure, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2479 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that cyberattack, data corruption or integration failure, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Commissioning & Start-up | Geothermal | Middle East | Procurement | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2480 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that cyberattack, data corruption or integration failure, combined with governance delay, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Decommissioning | LNG | South Asia | Manufacturing | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2481 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that cyberattack, data corruption or integration failure, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2482 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that cyberattack, data corruption or integration failure, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2483 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that cyberattack, data corruption or integration failure, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | R&D / Technology Development | Solar PV | Europe | Manufacturing | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2484 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that cyberattack, data corruption or integration failure, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Brownfield Modification | Battery Energy Storage | Africa | Construction | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2485 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that cyberattack, data corruption or integration failure, combined with commercial misalignment, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2486 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that cyberattack, data corruption or integration failure, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Decommissioning | Nuclear Power | Latin America | Manufacturing | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2487 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that cyberattack, data corruption or integration failure, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2488 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that cyberattack, data corruption or integration failure, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Installation | Pumped Storage | Middle East | Installation | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2489 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that cyberattack, data corruption or integration failure, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2490 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that cyberattack, data corruption or integration failure, combined with quality escape, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2491 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that cyberattack, data corruption or integration failure, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2492 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that cyberattack, data corruption or integration failure, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPCM | Offshore Wind | Europe | Pre-commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2493 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that cyberattack, data corruption or integration failure, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2494 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that cyberattack, data corruption or integration failure, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2495 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that cyberattack, data corruption or integration failure, combined with access constraint, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2496 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that cyberattack, data corruption or integration failure, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Digital Project Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2497 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that cyberattack, data corruption or integration failure, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Digital Project Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2498 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that cyberattack, data corruption or integration failure, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Digital Project Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2499 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that cyberattack, data corruption or integration failure, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Digital Project Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2500 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that cyberattack, data corruption or integration failure, combined with performance variability, may adversely affect project objectives through quality / time / cost consequences. | Digital, Data & Cybersecurity | EPCM | Pumped Storage | Latin America | Detailed Engineering | Shared | M | Quality / Time / Cost | Establish controls for cyberattack, data corruption or integration failure; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Digital Project Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2501 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that failed test, incomplete turnover or unstable start-up, combined with insufficient planning, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2502 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that failed test, incomplete turnover or unstable start-up, combined with insufficient planning, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2503 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that failed test, incomplete turnover or unstable start-up, combined with insufficient planning, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2504 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that failed test, incomplete turnover or unstable start-up, combined with insufficient planning, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Grid Interconnection | Offshore Wind | North America | Procurement | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2505 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that failed test, incomplete turnover or unstable start-up, combined with insufficient planning, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2506 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that failed test, incomplete turnover or unstable start-up, combined with incomplete information, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2507 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that failed test, incomplete turnover or unstable start-up, combined with incomplete information, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2508 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that failed test, incomplete turnover or unstable start-up, combined with incomplete information, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2509 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that failed test, incomplete turnover or unstable start-up, combined with incomplete information, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPC / Turnkey | Hydropower | Latin America | Construction | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2510 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that failed test, incomplete turnover or unstable start-up, combined with incomplete information, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Installation | Nuclear Power | Global / Multi-country | Installation | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2511 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that failed test, incomplete turnover or unstable start-up, combined with late decision-making, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | R&D / Technology Development | Geothermal | Africa | Manufacturing | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2512 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that failed test, incomplete turnover or unstable start-up, combined with late decision-making, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Brownfield Modification | LNG | East Asia | Construction | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2513 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that failed test, incomplete turnover or unstable start-up, combined with late decision-making, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Owner’s Engineering | Onshore Wind | North America | Installation | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2514 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that failed test, incomplete turnover or unstable start-up, combined with late decision-making, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2515 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that failed test, incomplete turnover or unstable start-up, combined with late decision-making, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2516 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that failed test, incomplete turnover or unstable start-up, combined with weak controls, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Installation | Battery Energy Storage | South Asia | Installation | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2517 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that failed test, incomplete turnover or unstable start-up, combined with weak controls, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2518 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that failed test, incomplete turnover or unstable start-up, combined with weak controls, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2519 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that failed test, incomplete turnover or unstable start-up, combined with weak controls, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2520 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that failed test, incomplete turnover or unstable start-up, combined with weak controls, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2521 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that failed test, incomplete turnover or unstable start-up, combined with resource constraints, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2522 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that failed test, incomplete turnover or unstable start-up, combined with resource constraints, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Decommissioning | Marine Energy | North America | Operations / Handover | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2523 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that failed test, incomplete turnover or unstable start-up, combined with resource constraints, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2524 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that failed test, incomplete turnover or unstable start-up, combined with resource constraints, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Installation | LNG | Europe | FEED / Basic Design | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2525 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that failed test, incomplete turnover or unstable start-up, combined with resource constraints, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2526 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that failed test, incomplete turnover or unstable start-up, combined with supplier dependency, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2527 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that failed test, incomplete turnover or unstable start-up, combined with supplier dependency, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2528 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that failed test, incomplete turnover or unstable start-up, combined with supplier dependency, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2529 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that failed test, incomplete turnover or unstable start-up, combined with supplier dependency, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2530 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that failed test, incomplete turnover or unstable start-up, combined with supplier dependency, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2531 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that failed test, incomplete turnover or unstable start-up, combined with interface complexity, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Operations & Maintenance | District Energy | North America | Detailed Engineering | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2532 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that failed test, incomplete turnover or unstable start-up, combined with interface complexity, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Grid Interconnection | Pumped Storage | Oceania | Procurement | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2533 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that failed test, incomplete turnover or unstable start-up, combined with interface complexity, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2534 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that failed test, incomplete turnover or unstable start-up, combined with interface complexity, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Brownfield Modification | Marine Energy | Africa | Construction | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2535 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that failed test, incomplete turnover or unstable start-up, combined with interface complexity, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Owner’s Engineering | Geothermal | East Asia | Installation | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2536 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that failed test, incomplete turnover or unstable start-up, combined with requirements volatility, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Decommissioning | Offshore Wind | Latin America | Manufacturing | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2537 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that failed test, incomplete turnover or unstable start-up, combined with requirements volatility, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2538 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that failed test, incomplete turnover or unstable start-up, combined with requirements volatility, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Installation | Refining & Petrochemicals | Middle East | Installation | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2539 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that failed test, incomplete turnover or unstable start-up, combined with requirements volatility, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2540 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that failed test, incomplete turnover or unstable start-up, combined with requirements volatility, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2541 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that failed test, incomplete turnover or unstable start-up, combined with regulatory uncertainty, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Owner’s Engineering | Hydropower | Oceania | Installation | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2542 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that failed test, incomplete turnover or unstable start-up, combined with regulatory uncertainty, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPCM | Nuclear Power | Europe | Pre-commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2543 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that failed test, incomplete turnover or unstable start-up, combined with regulatory uncertainty, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Commissioning & Start-up | District Energy | Africa | Commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2544 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that failed test, incomplete turnover or unstable start-up, combined with regulatory uncertainty, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2545 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that failed test, incomplete turnover or unstable start-up, combined with regulatory uncertainty, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2546 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that failed test, incomplete turnover or unstable start-up, combined with inadequate verification, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2547 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that failed test, incomplete turnover or unstable start-up, combined with inadequate verification, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2548 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that failed test, incomplete turnover or unstable start-up, combined with inadequate verification, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2549 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that failed test, incomplete turnover or unstable start-up, combined with inadequate verification, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2550 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that failed test, incomplete turnover or unstable start-up, combined with inadequate verification, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2551 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that failed test, incomplete turnover or unstable start-up, combined with poor communication, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2552 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that failed test, incomplete turnover or unstable start-up, combined with poor communication, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2553 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that failed test, incomplete turnover or unstable start-up, combined with poor communication, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2554 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that failed test, incomplete turnover or unstable start-up, combined with poor communication, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Grid Interconnection | Nuclear Power | North America | Procurement | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2555 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that failed test, incomplete turnover or unstable start-up, combined with poor communication, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | R&D / Technology Development | District Energy | Oceania | Manufacturing | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2556 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that failed test, incomplete turnover or unstable start-up, combined with incorrect assumptions, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPCM | LNG | Middle East | Detailed Engineering | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2557 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that failed test, incomplete turnover or unstable start-up, combined with incorrect assumptions, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2558 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that failed test, incomplete turnover or unstable start-up, combined with incorrect assumptions, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2559 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that failed test, incomplete turnover or unstable start-up, combined with incorrect assumptions, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2560 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that failed test, incomplete turnover or unstable start-up, combined with incorrect assumptions, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Installation | Offshore Wind | Global / Multi-country | Installation | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2561 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that failed test, incomplete turnover or unstable start-up, combined with low technical maturity, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2562 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that failed test, incomplete turnover or unstable start-up, combined with low technical maturity, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2563 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that failed test, incomplete turnover or unstable start-up, combined with low technical maturity, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Owner’s Engineering | Transmission & Substations | North America | Installation | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2564 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that failed test, incomplete turnover or unstable start-up, combined with low technical maturity, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2565 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that failed test, incomplete turnover or unstable start-up, combined with low technical maturity, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Commissioning & Start-up | Hydropower | Europe | Commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2566 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that failed test, incomplete turnover or unstable start-up, combined with documentation gaps, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Installation | Marine Energy | South Asia | Installation | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2567 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that failed test, incomplete turnover or unstable start-up, combined with documentation gaps, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2568 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that failed test, incomplete turnover or unstable start-up, combined with documentation gaps, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Grid Interconnection | LNG | Latin America | Commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2569 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that failed test, incomplete turnover or unstable start-up, combined with documentation gaps, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2570 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that failed test, incomplete turnover or unstable start-up, combined with documentation gaps, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2571 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that failed test, incomplete turnover or unstable start-up, combined with external disruption, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2572 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that failed test, incomplete turnover or unstable start-up, combined with external disruption, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2573 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that failed test, incomplete turnover or unstable start-up, combined with external disruption, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2574 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that failed test, incomplete turnover or unstable start-up, combined with external disruption, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2575 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that failed test, incomplete turnover or unstable start-up, combined with external disruption, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2576 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that failed test, incomplete turnover or unstable start-up, combined with governance delay, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2577 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that failed test, incomplete turnover or unstable start-up, combined with governance delay, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2578 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that failed test, incomplete turnover or unstable start-up, combined with governance delay, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2579 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that failed test, incomplete turnover or unstable start-up, combined with governance delay, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Commissioning & Start-up | Geothermal | Middle East | Procurement | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2580 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that failed test, incomplete turnover or unstable start-up, combined with governance delay, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Decommissioning | LNG | South Asia | Manufacturing | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2581 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that failed test, incomplete turnover or unstable start-up, combined with commercial misalignment, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2582 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that failed test, incomplete turnover or unstable start-up, combined with commercial misalignment, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2583 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that failed test, incomplete turnover or unstable start-up, combined with commercial misalignment, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | R&D / Technology Development | Solar PV | Europe | Manufacturing | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2584 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that failed test, incomplete turnover or unstable start-up, combined with commercial misalignment, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Brownfield Modification | Battery Energy Storage | Africa | Construction | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2585 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that failed test, incomplete turnover or unstable start-up, combined with commercial misalignment, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2586 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that failed test, incomplete turnover or unstable start-up, combined with quality escape, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Decommissioning | Nuclear Power | Latin America | Manufacturing | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2587 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that failed test, incomplete turnover or unstable start-up, combined with quality escape, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2588 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that failed test, incomplete turnover or unstable start-up, combined with quality escape, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Installation | Pumped Storage | Middle East | Installation | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2589 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that failed test, incomplete turnover or unstable start-up, combined with quality escape, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2590 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that failed test, incomplete turnover or unstable start-up, combined with quality escape, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2591 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that failed test, incomplete turnover or unstable start-up, combined with access constraint, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2592 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that failed test, incomplete turnover or unstable start-up, combined with access constraint, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPCM | Offshore Wind | Europe | Pre-commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2593 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that failed test, incomplete turnover or unstable start-up, combined with access constraint, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2594 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that failed test, incomplete turnover or unstable start-up, combined with access constraint, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2595 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that failed test, incomplete turnover or unstable start-up, combined with access constraint, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2596 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that failed test, incomplete turnover or unstable start-up, combined with performance variability, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Commissioning Manager | 2% | 2000000 | 70% | 1400000 | 35% | 910000 | 0.91% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2597 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that failed test, incomplete turnover or unstable start-up, combined with performance variability, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Commissioning Manager | 2.25% | 2250000 | 70% | 1575000 | 35% | 1023750 | 1.024% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2598 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that failed test, incomplete turnover or unstable start-up, combined with performance variability, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Commissioning Manager | 2.5% | 2500000 | 70% | 1750000 | 35% | 1137500 | 1.137% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2599 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that failed test, incomplete turnover or unstable start-up, combined with performance variability, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Commissioning Manager | 2.75% | 2750000 | 70% | 1925000 | 35% | 1251250 | 1.251% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2600 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that failed test, incomplete turnover or unstable start-up, combined with performance variability, may adversely affect project objectives through time / quality / hse consequences. | Commissioning & Start-up | EPCM | Pumped Storage | Latin America | Detailed Engineering | Contractor | H | Time / Quality / HSE | Establish controls for failed test, incomplete turnover or unstable start-up; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Commissioning Manager | 3% | 3000000 | 70% | 2100000 | 35% | 1365000 | 1.365% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2601 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that poor maintainability, missing spares or training gap, combined with insufficient planning, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2602 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that poor maintainability, missing spares or training gap, combined with insufficient planning, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2603 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that poor maintainability, missing spares or training gap, combined with insufficient planning, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2604 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that poor maintainability, missing spares or training gap, combined with insufficient planning, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Grid Interconnection | Offshore Wind | North America | Procurement | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2605 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that poor maintainability, missing spares or training gap, combined with insufficient planning, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2606 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that poor maintainability, missing spares or training gap, combined with incomplete information, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2607 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that poor maintainability, missing spares or training gap, combined with incomplete information, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2608 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that poor maintainability, missing spares or training gap, combined with incomplete information, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2609 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that poor maintainability, missing spares or training gap, combined with incomplete information, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPC / Turnkey | Hydropower | Latin America | Construction | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2610 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that poor maintainability, missing spares or training gap, combined with incomplete information, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Installation | Nuclear Power | Global / Multi-country | Installation | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2611 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that poor maintainability, missing spares or training gap, combined with late decision-making, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | R&D / Technology Development | Geothermal | Africa | Manufacturing | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2612 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that poor maintainability, missing spares or training gap, combined with late decision-making, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Brownfield Modification | LNG | East Asia | Construction | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2613 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that poor maintainability, missing spares or training gap, combined with late decision-making, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Owner’s Engineering | Onshore Wind | North America | Installation | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2614 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that poor maintainability, missing spares or training gap, combined with late decision-making, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2615 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that poor maintainability, missing spares or training gap, combined with late decision-making, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2616 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that poor maintainability, missing spares or training gap, combined with weak controls, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Installation | Battery Energy Storage | South Asia | Installation | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2617 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that poor maintainability, missing spares or training gap, combined with weak controls, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2618 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that poor maintainability, missing spares or training gap, combined with weak controls, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2619 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that poor maintainability, missing spares or training gap, combined with weak controls, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2620 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that poor maintainability, missing spares or training gap, combined with weak controls, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2621 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that poor maintainability, missing spares or training gap, combined with resource constraints, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2622 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that poor maintainability, missing spares or training gap, combined with resource constraints, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Decommissioning | Marine Energy | North America | Operations / Handover | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2623 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that poor maintainability, missing spares or training gap, combined with resource constraints, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2624 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that poor maintainability, missing spares or training gap, combined with resource constraints, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Installation | LNG | Europe | FEED / Basic Design | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2625 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that poor maintainability, missing spares or training gap, combined with resource constraints, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2626 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that poor maintainability, missing spares or training gap, combined with supplier dependency, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2627 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that poor maintainability, missing spares or training gap, combined with supplier dependency, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2628 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that poor maintainability, missing spares or training gap, combined with supplier dependency, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2629 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that poor maintainability, missing spares or training gap, combined with supplier dependency, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2630 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that poor maintainability, missing spares or training gap, combined with supplier dependency, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2631 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that poor maintainability, missing spares or training gap, combined with interface complexity, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Operations & Maintenance | District Energy | North America | Detailed Engineering | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2632 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that poor maintainability, missing spares or training gap, combined with interface complexity, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Grid Interconnection | Pumped Storage | Oceania | Procurement | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2633 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that poor maintainability, missing spares or training gap, combined with interface complexity, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2634 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that poor maintainability, missing spares or training gap, combined with interface complexity, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Brownfield Modification | Marine Energy | Africa | Construction | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2635 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that poor maintainability, missing spares or training gap, combined with interface complexity, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Owner’s Engineering | Geothermal | East Asia | Installation | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2636 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that poor maintainability, missing spares or training gap, combined with requirements volatility, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Decommissioning | Offshore Wind | Latin America | Manufacturing | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2637 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that poor maintainability, missing spares or training gap, combined with requirements volatility, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2638 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that poor maintainability, missing spares or training gap, combined with requirements volatility, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Installation | Refining & Petrochemicals | Middle East | Installation | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2639 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that poor maintainability, missing spares or training gap, combined with requirements volatility, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2640 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that poor maintainability, missing spares or training gap, combined with requirements volatility, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2641 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that poor maintainability, missing spares or training gap, combined with regulatory uncertainty, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Owner’s Engineering | Hydropower | Oceania | Installation | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2642 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that poor maintainability, missing spares or training gap, combined with regulatory uncertainty, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPCM | Nuclear Power | Europe | Pre-commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2643 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that poor maintainability, missing spares or training gap, combined with regulatory uncertainty, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Commissioning & Start-up | District Energy | Africa | Commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2644 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that poor maintainability, missing spares or training gap, combined with regulatory uncertainty, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2645 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that poor maintainability, missing spares or training gap, combined with regulatory uncertainty, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2646 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that poor maintainability, missing spares or training gap, combined with inadequate verification, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2647 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that poor maintainability, missing spares or training gap, combined with inadequate verification, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2648 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that poor maintainability, missing spares or training gap, combined with inadequate verification, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2649 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that poor maintainability, missing spares or training gap, combined with inadequate verification, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2650 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that poor maintainability, missing spares or training gap, combined with inadequate verification, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2651 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that poor maintainability, missing spares or training gap, combined with poor communication, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2652 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that poor maintainability, missing spares or training gap, combined with poor communication, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2653 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that poor maintainability, missing spares or training gap, combined with poor communication, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2654 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that poor maintainability, missing spares or training gap, combined with poor communication, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Grid Interconnection | Nuclear Power | North America | Procurement | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2655 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that poor maintainability, missing spares or training gap, combined with poor communication, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | R&D / Technology Development | District Energy | Oceania | Manufacturing | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2656 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that poor maintainability, missing spares or training gap, combined with incorrect assumptions, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPCM | LNG | Middle East | Detailed Engineering | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2657 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that poor maintainability, missing spares or training gap, combined with incorrect assumptions, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2658 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that poor maintainability, missing spares or training gap, combined with incorrect assumptions, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2659 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that poor maintainability, missing spares or training gap, combined with incorrect assumptions, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2660 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that poor maintainability, missing spares or training gap, combined with incorrect assumptions, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Installation | Offshore Wind | Global / Multi-country | Installation | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2661 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that poor maintainability, missing spares or training gap, combined with low technical maturity, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2662 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that poor maintainability, missing spares or training gap, combined with low technical maturity, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2663 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that poor maintainability, missing spares or training gap, combined with low technical maturity, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Owner’s Engineering | Transmission & Substations | North America | Installation | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2664 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that poor maintainability, missing spares or training gap, combined with low technical maturity, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2665 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that poor maintainability, missing spares or training gap, combined with low technical maturity, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Commissioning & Start-up | Hydropower | Europe | Commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2666 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that poor maintainability, missing spares or training gap, combined with documentation gaps, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Installation | Marine Energy | South Asia | Installation | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2667 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that poor maintainability, missing spares or training gap, combined with documentation gaps, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2668 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that poor maintainability, missing spares or training gap, combined with documentation gaps, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Grid Interconnection | LNG | Latin America | Commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2669 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that poor maintainability, missing spares or training gap, combined with documentation gaps, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2670 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that poor maintainability, missing spares or training gap, combined with documentation gaps, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2671 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that poor maintainability, missing spares or training gap, combined with external disruption, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2672 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that poor maintainability, missing spares or training gap, combined with external disruption, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2673 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that poor maintainability, missing spares or training gap, combined with external disruption, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2674 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that poor maintainability, missing spares or training gap, combined with external disruption, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2675 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that poor maintainability, missing spares or training gap, combined with external disruption, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2676 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that poor maintainability, missing spares or training gap, combined with governance delay, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2677 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that poor maintainability, missing spares or training gap, combined with governance delay, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2678 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that poor maintainability, missing spares or training gap, combined with governance delay, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2679 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that poor maintainability, missing spares or training gap, combined with governance delay, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Commissioning & Start-up | Geothermal | Middle East | Procurement | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2680 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that poor maintainability, missing spares or training gap, combined with governance delay, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Decommissioning | LNG | South Asia | Manufacturing | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2681 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that poor maintainability, missing spares or training gap, combined with commercial misalignment, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2682 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that poor maintainability, missing spares or training gap, combined with commercial misalignment, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2683 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that poor maintainability, missing spares or training gap, combined with commercial misalignment, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | R&D / Technology Development | Solar PV | Europe | Manufacturing | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2684 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that poor maintainability, missing spares or training gap, combined with commercial misalignment, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Brownfield Modification | Battery Energy Storage | Africa | Construction | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2685 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that poor maintainability, missing spares or training gap, combined with commercial misalignment, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2686 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that poor maintainability, missing spares or training gap, combined with quality escape, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Decommissioning | Nuclear Power | Latin America | Manufacturing | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2687 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that poor maintainability, missing spares or training gap, combined with quality escape, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2688 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that poor maintainability, missing spares or training gap, combined with quality escape, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Installation | Pumped Storage | Middle East | Installation | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2689 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that poor maintainability, missing spares or training gap, combined with quality escape, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2690 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that poor maintainability, missing spares or training gap, combined with quality escape, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2691 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that poor maintainability, missing spares or training gap, combined with access constraint, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2692 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that poor maintainability, missing spares or training gap, combined with access constraint, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPCM | Offshore Wind | Europe | Pre-commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2693 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that poor maintainability, missing spares or training gap, combined with access constraint, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2694 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that poor maintainability, missing spares or training gap, combined with access constraint, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2695 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that poor maintainability, missing spares or training gap, combined with access constraint, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2696 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that poor maintainability, missing spares or training gap, combined with performance variability, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Operations Readiness Manager | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2697 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that poor maintainability, missing spares or training gap, combined with performance variability, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Operations Readiness Manager | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2698 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that poor maintainability, missing spares or training gap, combined with performance variability, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Operations Readiness Manager | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2699 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that poor maintainability, missing spares or training gap, combined with performance variability, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Operations Readiness Manager | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2700 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that poor maintainability, missing spares or training gap, combined with performance variability, may adversely affect project objectives through quality / cost / hse consequences. | Operations & Maintainability | EPCM | Pumped Storage | Latin America | Detailed Engineering | Contractor | M | Quality / Cost / HSE | Establish controls for poor maintainability, missing spares or training gap; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Operations Readiness Manager | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2701 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that slow decision, unclear authority or weak escalation, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2702 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that slow decision, unclear authority or weak escalation, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2703 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that slow decision, unclear authority or weak escalation, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2704 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that slow decision, unclear authority or weak escalation, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Grid Interconnection | Offshore Wind | North America | Procurement | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2705 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that slow decision, unclear authority or weak escalation, combined with insufficient planning, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2706 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that slow decision, unclear authority or weak escalation, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2707 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that slow decision, unclear authority or weak escalation, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2708 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that slow decision, unclear authority or weak escalation, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2709 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that slow decision, unclear authority or weak escalation, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPC / Turnkey | Hydropower | Latin America | Construction | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2710 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that slow decision, unclear authority or weak escalation, combined with incomplete information, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Installation | Nuclear Power | Global / Multi-country | Installation | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2711 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that slow decision, unclear authority or weak escalation, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | R&D / Technology Development | Geothermal | Africa | Manufacturing | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2712 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that slow decision, unclear authority or weak escalation, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Brownfield Modification | LNG | East Asia | Construction | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2713 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that slow decision, unclear authority or weak escalation, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Owner’s Engineering | Onshore Wind | North America | Installation | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2714 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that slow decision, unclear authority or weak escalation, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2715 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that slow decision, unclear authority or weak escalation, combined with late decision-making, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2716 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that slow decision, unclear authority or weak escalation, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Installation | Battery Energy Storage | South Asia | Installation | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2717 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that slow decision, unclear authority or weak escalation, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2718 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that slow decision, unclear authority or weak escalation, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2719 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that slow decision, unclear authority or weak escalation, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2720 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that slow decision, unclear authority or weak escalation, combined with weak controls, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2721 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that slow decision, unclear authority or weak escalation, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2722 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that slow decision, unclear authority or weak escalation, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Decommissioning | Marine Energy | North America | Operations / Handover | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2723 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that slow decision, unclear authority or weak escalation, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2724 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that slow decision, unclear authority or weak escalation, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Installation | LNG | Europe | FEED / Basic Design | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2725 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that slow decision, unclear authority or weak escalation, combined with resource constraints, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2726 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that slow decision, unclear authority or weak escalation, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2727 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that slow decision, unclear authority or weak escalation, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2728 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that slow decision, unclear authority or weak escalation, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2729 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that slow decision, unclear authority or weak escalation, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2730 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that slow decision, unclear authority or weak escalation, combined with supplier dependency, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2731 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that slow decision, unclear authority or weak escalation, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Operations & Maintenance | District Energy | North America | Detailed Engineering | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2732 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that slow decision, unclear authority or weak escalation, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Grid Interconnection | Pumped Storage | Oceania | Procurement | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2733 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that slow decision, unclear authority or weak escalation, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2734 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that slow decision, unclear authority or weak escalation, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Brownfield Modification | Marine Energy | Africa | Construction | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2735 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that slow decision, unclear authority or weak escalation, combined with interface complexity, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Owner’s Engineering | Geothermal | East Asia | Installation | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2736 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that slow decision, unclear authority or weak escalation, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Decommissioning | Offshore Wind | Latin America | Manufacturing | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2737 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that slow decision, unclear authority or weak escalation, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2738 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that slow decision, unclear authority or weak escalation, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Installation | Refining & Petrochemicals | Middle East | Installation | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2739 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that slow decision, unclear authority or weak escalation, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2740 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that slow decision, unclear authority or weak escalation, combined with requirements volatility, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2741 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that slow decision, unclear authority or weak escalation, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Owner’s Engineering | Hydropower | Oceania | Installation | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2742 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that slow decision, unclear authority or weak escalation, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPCM | Nuclear Power | Europe | Pre-commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2743 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that slow decision, unclear authority or weak escalation, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Commissioning & Start-up | District Energy | Africa | Commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2744 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that slow decision, unclear authority or weak escalation, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2745 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that slow decision, unclear authority or weak escalation, combined with regulatory uncertainty, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2746 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that slow decision, unclear authority or weak escalation, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2747 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that slow decision, unclear authority or weak escalation, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2748 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that slow decision, unclear authority or weak escalation, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2749 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that slow decision, unclear authority or weak escalation, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2750 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that slow decision, unclear authority or weak escalation, combined with inadequate verification, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2751 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that slow decision, unclear authority or weak escalation, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2752 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that slow decision, unclear authority or weak escalation, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2753 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that slow decision, unclear authority or weak escalation, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2754 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that slow decision, unclear authority or weak escalation, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Grid Interconnection | Nuclear Power | North America | Procurement | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2755 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that slow decision, unclear authority or weak escalation, combined with poor communication, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | R&D / Technology Development | District Energy | Oceania | Manufacturing | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2756 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that slow decision, unclear authority or weak escalation, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPCM | LNG | Middle East | Detailed Engineering | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2757 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that slow decision, unclear authority or weak escalation, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2758 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that slow decision, unclear authority or weak escalation, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2759 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that slow decision, unclear authority or weak escalation, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2760 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that slow decision, unclear authority or weak escalation, combined with incorrect assumptions, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Installation | Offshore Wind | Global / Multi-country | Installation | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2761 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that slow decision, unclear authority or weak escalation, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2762 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that slow decision, unclear authority or weak escalation, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2763 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that slow decision, unclear authority or weak escalation, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Owner’s Engineering | Transmission & Substations | North America | Installation | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2764 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that slow decision, unclear authority or weak escalation, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2765 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that slow decision, unclear authority or weak escalation, combined with low technical maturity, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Commissioning & Start-up | Hydropower | Europe | Commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2766 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that slow decision, unclear authority or weak escalation, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Installation | Marine Energy | South Asia | Installation | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2767 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that slow decision, unclear authority or weak escalation, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2768 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that slow decision, unclear authority or weak escalation, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Grid Interconnection | LNG | Latin America | Commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2769 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that slow decision, unclear authority or weak escalation, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2770 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that slow decision, unclear authority or weak escalation, combined with documentation gaps, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2771 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that slow decision, unclear authority or weak escalation, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2772 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that slow decision, unclear authority or weak escalation, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2773 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that slow decision, unclear authority or weak escalation, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2774 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that slow decision, unclear authority or weak escalation, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2775 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that slow decision, unclear authority or weak escalation, combined with external disruption, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2776 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that slow decision, unclear authority or weak escalation, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2777 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that slow decision, unclear authority or weak escalation, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2778 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that slow decision, unclear authority or weak escalation, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2779 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that slow decision, unclear authority or weak escalation, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Commissioning & Start-up | Geothermal | Middle East | Procurement | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2780 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that slow decision, unclear authority or weak escalation, combined with governance delay, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Decommissioning | LNG | South Asia | Manufacturing | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2781 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that slow decision, unclear authority or weak escalation, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2782 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that slow decision, unclear authority or weak escalation, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2783 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that slow decision, unclear authority or weak escalation, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | R&D / Technology Development | Solar PV | Europe | Manufacturing | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2784 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that slow decision, unclear authority or weak escalation, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Brownfield Modification | Battery Energy Storage | Africa | Construction | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2785 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that slow decision, unclear authority or weak escalation, combined with commercial misalignment, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2786 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that slow decision, unclear authority or weak escalation, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Decommissioning | Nuclear Power | Latin America | Manufacturing | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2787 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that slow decision, unclear authority or weak escalation, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2788 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that slow decision, unclear authority or weak escalation, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Installation | Pumped Storage | Middle East | Installation | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2789 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that slow decision, unclear authority or weak escalation, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2790 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that slow decision, unclear authority or weak escalation, combined with quality escape, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2791 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that slow decision, unclear authority or weak escalation, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2792 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that slow decision, unclear authority or weak escalation, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPCM | Offshore Wind | Europe | Pre-commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2793 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that slow decision, unclear authority or weak escalation, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2794 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that slow decision, unclear authority or weak escalation, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2795 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that slow decision, unclear authority or weak escalation, combined with access constraint, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2796 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that slow decision, unclear authority or weak escalation, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Project Director | 1.44% | 1440000 | 40% | 576000 | 35% | 374400 | 0.3744% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2797 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that slow decision, unclear authority or weak escalation, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Project Director | 1.62% | 1620000 | 40% | 648000 | 35% | 421200 | 0.4212% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2798 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that slow decision, unclear authority or weak escalation, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Project Director | 1.8% | 1800000 | 40% | 720000 | 35% | 468000 | 0.468% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2799 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that slow decision, unclear authority or weak escalation, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Project Director | 1.98% | 1980000 | 40% | 792000 | 35% | 514800 | 0.5148% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2800 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that slow decision, unclear authority or weak escalation, combined with performance variability, may adversely affect project objectives through time / cost consequences. | Governance & Decision Making | EPCM | Pumped Storage | Latin America | Detailed Engineering | Shared | M | Time / Cost | Establish controls for slow decision, unclear authority or weak escalation; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Project Director | 2.16% | 2160000 | 40% | 864000 | 35% | 561600 | 0.5616% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2801 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that bribery, fraud, sanctions or conflict of interest, combined with insufficient planning, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2802 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that bribery, fraud, sanctions or conflict of interest, combined with insufficient planning, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2803 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that bribery, fraud, sanctions or conflict of interest, combined with insufficient planning, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2804 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that bribery, fraud, sanctions or conflict of interest, combined with insufficient planning, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Grid Interconnection | Offshore Wind | North America | Procurement | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2805 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that bribery, fraud, sanctions or conflict of interest, combined with insufficient planning, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2806 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that bribery, fraud, sanctions or conflict of interest, combined with incomplete information, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2807 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that bribery, fraud, sanctions or conflict of interest, combined with incomplete information, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2808 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that bribery, fraud, sanctions or conflict of interest, combined with incomplete information, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2809 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that bribery, fraud, sanctions or conflict of interest, combined with incomplete information, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPC / Turnkey | Hydropower | Latin America | Construction | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2810 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that bribery, fraud, sanctions or conflict of interest, combined with incomplete information, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Installation | Nuclear Power | Global / Multi-country | Installation | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2811 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that bribery, fraud, sanctions or conflict of interest, combined with late decision-making, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | R&D / Technology Development | Geothermal | Africa | Manufacturing | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2812 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that bribery, fraud, sanctions or conflict of interest, combined with late decision-making, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Brownfield Modification | LNG | East Asia | Construction | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2813 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that bribery, fraud, sanctions or conflict of interest, combined with late decision-making, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Owner’s Engineering | Onshore Wind | North America | Installation | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2814 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that bribery, fraud, sanctions or conflict of interest, combined with late decision-making, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2815 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that bribery, fraud, sanctions or conflict of interest, combined with late decision-making, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2816 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that bribery, fraud, sanctions or conflict of interest, combined with weak controls, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Installation | Battery Energy Storage | South Asia | Installation | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2817 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that bribery, fraud, sanctions or conflict of interest, combined with weak controls, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2818 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that bribery, fraud, sanctions or conflict of interest, combined with weak controls, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2819 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that bribery, fraud, sanctions or conflict of interest, combined with weak controls, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2820 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that bribery, fraud, sanctions or conflict of interest, combined with weak controls, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2821 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that bribery, fraud, sanctions or conflict of interest, combined with resource constraints, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2822 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that bribery, fraud, sanctions or conflict of interest, combined with resource constraints, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Decommissioning | Marine Energy | North America | Operations / Handover | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2823 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that bribery, fraud, sanctions or conflict of interest, combined with resource constraints, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2824 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that bribery, fraud, sanctions or conflict of interest, combined with resource constraints, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Installation | LNG | Europe | FEED / Basic Design | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2825 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that bribery, fraud, sanctions or conflict of interest, combined with resource constraints, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2826 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that bribery, fraud, sanctions or conflict of interest, combined with supplier dependency, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2827 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that bribery, fraud, sanctions or conflict of interest, combined with supplier dependency, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2828 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that bribery, fraud, sanctions or conflict of interest, combined with supplier dependency, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2829 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that bribery, fraud, sanctions or conflict of interest, combined with supplier dependency, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2830 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that bribery, fraud, sanctions or conflict of interest, combined with supplier dependency, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2831 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that bribery, fraud, sanctions or conflict of interest, combined with interface complexity, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Operations & Maintenance | District Energy | North America | Detailed Engineering | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2832 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that bribery, fraud, sanctions or conflict of interest, combined with interface complexity, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Grid Interconnection | Pumped Storage | Oceania | Procurement | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2833 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that bribery, fraud, sanctions or conflict of interest, combined with interface complexity, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2834 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that bribery, fraud, sanctions or conflict of interest, combined with interface complexity, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Brownfield Modification | Marine Energy | Africa | Construction | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2835 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that bribery, fraud, sanctions or conflict of interest, combined with interface complexity, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Owner’s Engineering | Geothermal | East Asia | Installation | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2836 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that bribery, fraud, sanctions or conflict of interest, combined with requirements volatility, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Decommissioning | Offshore Wind | Latin America | Manufacturing | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2837 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that bribery, fraud, sanctions or conflict of interest, combined with requirements volatility, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2838 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that bribery, fraud, sanctions or conflict of interest, combined with requirements volatility, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Installation | Refining & Petrochemicals | Middle East | Installation | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2839 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that bribery, fraud, sanctions or conflict of interest, combined with requirements volatility, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2840 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that bribery, fraud, sanctions or conflict of interest, combined with requirements volatility, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2841 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that bribery, fraud, sanctions or conflict of interest, combined with regulatory uncertainty, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Owner’s Engineering | Hydropower | Oceania | Installation | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2842 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that bribery, fraud, sanctions or conflict of interest, combined with regulatory uncertainty, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPCM | Nuclear Power | Europe | Pre-commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2843 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that bribery, fraud, sanctions or conflict of interest, combined with regulatory uncertainty, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Commissioning & Start-up | District Energy | Africa | Commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2844 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that bribery, fraud, sanctions or conflict of interest, combined with regulatory uncertainty, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2845 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that bribery, fraud, sanctions or conflict of interest, combined with regulatory uncertainty, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2846 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that bribery, fraud, sanctions or conflict of interest, combined with inadequate verification, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2847 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that bribery, fraud, sanctions or conflict of interest, combined with inadequate verification, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2848 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that bribery, fraud, sanctions or conflict of interest, combined with inadequate verification, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2849 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that bribery, fraud, sanctions or conflict of interest, combined with inadequate verification, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2850 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that bribery, fraud, sanctions or conflict of interest, combined with inadequate verification, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2851 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that bribery, fraud, sanctions or conflict of interest, combined with poor communication, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2852 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that bribery, fraud, sanctions or conflict of interest, combined with poor communication, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2853 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that bribery, fraud, sanctions or conflict of interest, combined with poor communication, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2854 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that bribery, fraud, sanctions or conflict of interest, combined with poor communication, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Grid Interconnection | Nuclear Power | North America | Procurement | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2855 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that bribery, fraud, sanctions or conflict of interest, combined with poor communication, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | R&D / Technology Development | District Energy | Oceania | Manufacturing | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2856 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that bribery, fraud, sanctions or conflict of interest, combined with incorrect assumptions, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPCM | LNG | Middle East | Detailed Engineering | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2857 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that bribery, fraud, sanctions or conflict of interest, combined with incorrect assumptions, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2858 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that bribery, fraud, sanctions or conflict of interest, combined with incorrect assumptions, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2859 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that bribery, fraud, sanctions or conflict of interest, combined with incorrect assumptions, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2860 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that bribery, fraud, sanctions or conflict of interest, combined with incorrect assumptions, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Installation | Offshore Wind | Global / Multi-country | Installation | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2861 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that bribery, fraud, sanctions or conflict of interest, combined with low technical maturity, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2862 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that bribery, fraud, sanctions or conflict of interest, combined with low technical maturity, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2863 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that bribery, fraud, sanctions or conflict of interest, combined with low technical maturity, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Owner’s Engineering | Transmission & Substations | North America | Installation | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2864 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that bribery, fraud, sanctions or conflict of interest, combined with low technical maturity, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2865 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that bribery, fraud, sanctions or conflict of interest, combined with low technical maturity, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Commissioning & Start-up | Hydropower | Europe | Commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2866 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that bribery, fraud, sanctions or conflict of interest, combined with documentation gaps, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Installation | Marine Energy | South Asia | Installation | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2867 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that bribery, fraud, sanctions or conflict of interest, combined with documentation gaps, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2868 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that bribery, fraud, sanctions or conflict of interest, combined with documentation gaps, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Grid Interconnection | LNG | Latin America | Commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2869 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that bribery, fraud, sanctions or conflict of interest, combined with documentation gaps, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2870 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that bribery, fraud, sanctions or conflict of interest, combined with documentation gaps, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2871 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that bribery, fraud, sanctions or conflict of interest, combined with external disruption, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2872 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that bribery, fraud, sanctions or conflict of interest, combined with external disruption, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2873 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that bribery, fraud, sanctions or conflict of interest, combined with external disruption, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2874 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that bribery, fraud, sanctions or conflict of interest, combined with external disruption, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2875 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that bribery, fraud, sanctions or conflict of interest, combined with external disruption, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2876 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that bribery, fraud, sanctions or conflict of interest, combined with governance delay, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2877 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that bribery, fraud, sanctions or conflict of interest, combined with governance delay, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2878 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that bribery, fraud, sanctions or conflict of interest, combined with governance delay, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2879 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that bribery, fraud, sanctions or conflict of interest, combined with governance delay, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Commissioning & Start-up | Geothermal | Middle East | Procurement | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2880 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that bribery, fraud, sanctions or conflict of interest, combined with governance delay, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Decommissioning | LNG | South Asia | Manufacturing | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2881 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that bribery, fraud, sanctions or conflict of interest, combined with commercial misalignment, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2882 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that bribery, fraud, sanctions or conflict of interest, combined with commercial misalignment, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2883 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that bribery, fraud, sanctions or conflict of interest, combined with commercial misalignment, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | R&D / Technology Development | Solar PV | Europe | Manufacturing | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2884 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that bribery, fraud, sanctions or conflict of interest, combined with commercial misalignment, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Brownfield Modification | Battery Energy Storage | Africa | Construction | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2885 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that bribery, fraud, sanctions or conflict of interest, combined with commercial misalignment, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2886 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that bribery, fraud, sanctions or conflict of interest, combined with quality escape, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Decommissioning | Nuclear Power | Latin America | Manufacturing | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2887 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that bribery, fraud, sanctions or conflict of interest, combined with quality escape, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2888 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that bribery, fraud, sanctions or conflict of interest, combined with quality escape, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Installation | Pumped Storage | Middle East | Installation | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2889 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that bribery, fraud, sanctions or conflict of interest, combined with quality escape, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2890 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that bribery, fraud, sanctions or conflict of interest, combined with quality escape, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2891 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that bribery, fraud, sanctions or conflict of interest, combined with access constraint, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2892 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that bribery, fraud, sanctions or conflict of interest, combined with access constraint, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPCM | Offshore Wind | Europe | Pre-commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2893 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that bribery, fraud, sanctions or conflict of interest, combined with access constraint, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2894 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that bribery, fraud, sanctions or conflict of interest, combined with access constraint, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2895 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that bribery, fraud, sanctions or conflict of interest, combined with access constraint, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2896 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that bribery, fraud, sanctions or conflict of interest, combined with performance variability, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Compliance Officer | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2897 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that bribery, fraud, sanctions or conflict of interest, combined with performance variability, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Compliance Officer | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2898 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that bribery, fraud, sanctions or conflict of interest, combined with performance variability, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Compliance Officer | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2899 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that bribery, fraud, sanctions or conflict of interest, combined with performance variability, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Compliance Officer | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2900 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that bribery, fraud, sanctions or conflict of interest, combined with performance variability, may adversely affect project objectives through cost / quality consequences. | Fraud, Ethics & Compliance | EPCM | Pumped Storage | Latin America | Detailed Engineering | Shared | L | Cost / Quality | Establish controls for bribery, fraud, sanctions or conflict of interest; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Compliance Officer | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2901 | For a Onshore Wind EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that coverage gap, theft, vandalism or security incident, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPC / Turnkey | Onshore Wind | Europe | Feasibility & Concept | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2902 | For a Biomass / Waste-to-Energy Installation project in Africa, there is a risk during FEED / Basic Design that coverage gap, theft, vandalism or security incident, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Installation | Biomass / Waste-to-Energy | Africa | FEED / Basic Design | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2903 | For a Oil & Gas Upstream Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that coverage gap, theft, vandalism or security incident, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Operations & Maintenance | Oil & Gas Upstream | East Asia | Detailed Engineering | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2904 | For a Offshore Wind Grid Interconnection project in North America, there is a risk during Procurement that coverage gap, theft, vandalism or security incident, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Grid Interconnection | Offshore Wind | North America | Procurement | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2905 | For a Green Hydrogen R&D / Technology Development project in Oceania, there is a risk during Manufacturing that coverage gap, theft, vandalism or security incident, combined with insufficient planning, may adversely affect project objectives through cost / time consequences. | Insurance & Security | R&D / Technology Development | Green Hydrogen | Oceania | Manufacturing | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with insufficient planning. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2906 | For a Concentrated Solar Power EPCM project in Middle East, there is a risk during Detailed Engineering that coverage gap, theft, vandalism or security incident, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPCM | Concentrated Solar Power | Middle East | Detailed Engineering | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2907 | For a Transmission & Substations Commissioning & Start-up project in South Asia, there is a risk during Procurement that coverage gap, theft, vandalism or security incident, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Commissioning & Start-up | Transmission & Substations | South Asia | Procurement | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2908 | For a Carbon Capture, Utilization & Storage Decommissioning project in Southeast Asia, there is a risk during Manufacturing that coverage gap, theft, vandalism or security incident, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Decommissioning | Carbon Capture, Utilization & Storage | Southeast Asia | Manufacturing | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2909 | For a Hydropower EPC / Turnkey project in Latin America, there is a risk during Construction that coverage gap, theft, vandalism or security incident, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPC / Turnkey | Hydropower | Latin America | Construction | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2910 | For a Nuclear Power Installation project in Global / Multi-country, there is a risk during Installation that coverage gap, theft, vandalism or security incident, combined with incomplete information, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Installation | Nuclear Power | Global / Multi-country | Installation | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incomplete information. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2911 | For a Geothermal R&D / Technology Development project in Africa, there is a risk during Manufacturing that coverage gap, theft, vandalism or security incident, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Insurance & Security | R&D / Technology Development | Geothermal | Africa | Manufacturing | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2912 | For a LNG Brownfield Modification project in East Asia, there is a risk during Construction that coverage gap, theft, vandalism or security incident, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Brownfield Modification | LNG | East Asia | Construction | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2913 | For a Onshore Wind Owner’s Engineering project in North America, there is a risk during Installation that coverage gap, theft, vandalism or security incident, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Owner’s Engineering | Onshore Wind | North America | Installation | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2914 | For a Biomass / Waste-to-Energy EPCM project in Oceania, there is a risk during Pre-commissioning that coverage gap, theft, vandalism or security incident, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPCM | Biomass / Waste-to-Energy | Oceania | Pre-commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2915 | For a Oil & Gas Upstream Commissioning & Start-up project in Europe, there is a risk during Commissioning that coverage gap, theft, vandalism or security incident, combined with late decision-making, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Commissioning & Start-up | Oil & Gas Upstream | Europe | Commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with late decision-making. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2916 | For a Battery Energy Storage Installation project in South Asia, there is a risk during Installation that coverage gap, theft, vandalism or security incident, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Installation | Battery Energy Storage | South Asia | Installation | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2917 | For a Coal / Thermal Power Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that coverage gap, theft, vandalism or security incident, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Operations & Maintenance | Coal / Thermal Power | Southeast Asia | Pre-commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2918 | For a Concentrated Solar Power Grid Interconnection project in Latin America, there is a risk during Commissioning that coverage gap, theft, vandalism or security incident, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Grid Interconnection | Concentrated Solar Power | Latin America | Commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2919 | For a Transmission & Substations R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that coverage gap, theft, vandalism or security incident, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Insurance & Security | R&D / Technology Development | Transmission & Substations | Global / Multi-country | Operations / Handover | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2920 | For a Carbon Capture, Utilization & Storage Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that coverage gap, theft, vandalism or security incident, combined with weak controls, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Brownfield Modification | Carbon Capture, Utilization & Storage | Middle East | Feasibility & Concept | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with weak controls. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2921 | For a Natural Gas / CCGT Commissioning & Start-up project in East Asia, there is a risk during Commissioning that coverage gap, theft, vandalism or security incident, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Commissioning & Start-up | Natural Gas / CCGT | East Asia | Commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2922 | For a Marine Energy Decommissioning project in North America, there is a risk during Operations / Handover that coverage gap, theft, vandalism or security incident, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Decommissioning | Marine Energy | North America | Operations / Handover | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2923 | For a Geothermal EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that coverage gap, theft, vandalism or security incident, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPC / Turnkey | Geothermal | Oceania | Feasibility & Concept | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2924 | For a LNG Installation project in Europe, there is a risk during FEED / Basic Design that coverage gap, theft, vandalism or security incident, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Installation | LNG | Europe | FEED / Basic Design | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2925 | For a Onshore Wind Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that coverage gap, theft, vandalism or security incident, combined with resource constraints, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Operations & Maintenance | Onshore Wind | Africa | Detailed Engineering | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with resource constraints. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2926 | For a Refining & Petrochemicals Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that coverage gap, theft, vandalism or security incident, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Brownfield Modification | Refining & Petrochemicals | Southeast Asia | Feasibility & Concept | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2927 | For a Solar PV Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that coverage gap, theft, vandalism or security incident, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Owner’s Engineering | Solar PV | Latin America | FEED / Basic Design | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2928 | For a Battery Energy Storage EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that coverage gap, theft, vandalism or security incident, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPCM | Battery Energy Storage | Global / Multi-country | Detailed Engineering | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2929 | For a Coal / Thermal Power Commissioning & Start-up project in Middle East, there is a risk during Procurement that coverage gap, theft, vandalism or security incident, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Commissioning & Start-up | Coal / Thermal Power | Middle East | Procurement | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2930 | For a Concentrated Solar Power Decommissioning project in South Asia, there is a risk during Manufacturing that coverage gap, theft, vandalism or security incident, combined with supplier dependency, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Decommissioning | Concentrated Solar Power | South Asia | Manufacturing | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with supplier dependency. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2931 | For a District Energy Operations & Maintenance project in North America, there is a risk during Detailed Engineering that coverage gap, theft, vandalism or security incident, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Operations & Maintenance | District Energy | North America | Detailed Engineering | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2932 | For a Pumped Storage Grid Interconnection project in Oceania, there is a risk during Procurement that coverage gap, theft, vandalism or security incident, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Grid Interconnection | Pumped Storage | Oceania | Procurement | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2933 | For a Natural Gas / CCGT R&D / Technology Development project in Europe, there is a risk during Manufacturing that coverage gap, theft, vandalism or security incident, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Insurance & Security | R&D / Technology Development | Natural Gas / CCGT | Europe | Manufacturing | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2934 | For a Marine Energy Brownfield Modification project in Africa, there is a risk during Construction that coverage gap, theft, vandalism or security incident, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Brownfield Modification | Marine Energy | Africa | Construction | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2935 | For a Geothermal Owner’s Engineering project in East Asia, there is a risk during Installation that coverage gap, theft, vandalism or security incident, combined with interface complexity, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Owner’s Engineering | Geothermal | East Asia | Installation | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with interface complexity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2936 | For a Offshore Wind Decommissioning project in Latin America, there is a risk during Manufacturing that coverage gap, theft, vandalism or security incident, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Decommissioning | Offshore Wind | Latin America | Manufacturing | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2937 | For a Green Hydrogen EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that coverage gap, theft, vandalism or security incident, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPC / Turnkey | Green Hydrogen | Global / Multi-country | Construction | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2938 | For a Refining & Petrochemicals Installation project in Middle East, there is a risk during Installation that coverage gap, theft, vandalism or security incident, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Installation | Refining & Petrochemicals | Middle East | Installation | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2939 | For a Solar PV Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that coverage gap, theft, vandalism or security incident, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Operations & Maintenance | Solar PV | South Asia | Pre-commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2940 | For a Battery Energy Storage Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that coverage gap, theft, vandalism or security incident, combined with requirements volatility, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Grid Interconnection | Battery Energy Storage | Southeast Asia | Commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with requirements volatility. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2941 | For a Hydropower Owner’s Engineering project in Oceania, there is a risk during Installation that coverage gap, theft, vandalism or security incident, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Owner’s Engineering | Hydropower | Oceania | Installation | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2942 | For a Nuclear Power EPCM project in Europe, there is a risk during Pre-commissioning that coverage gap, theft, vandalism or security incident, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPCM | Nuclear Power | Europe | Pre-commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2943 | For a District Energy Commissioning & Start-up project in Africa, there is a risk during Commissioning that coverage gap, theft, vandalism or security incident, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Commissioning & Start-up | District Energy | Africa | Commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2944 | For a Pumped Storage Decommissioning project in East Asia, there is a risk during Operations / Handover that coverage gap, theft, vandalism or security incident, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Decommissioning | Pumped Storage | East Asia | Operations / Handover | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2945 | For a Natural Gas / CCGT EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that coverage gap, theft, vandalism or security incident, combined with regulatory uncertainty, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPC / Turnkey | Natural Gas / CCGT | North America | Feasibility & Concept | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with regulatory uncertainty. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2946 | For a Biomass / Waste-to-Energy Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that coverage gap, theft, vandalism or security incident, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Grid Interconnection | Biomass / Waste-to-Energy | Global / Multi-country | Commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2947 | For a Oil & Gas Upstream R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that coverage gap, theft, vandalism or security incident, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Insurance & Security | R&D / Technology Development | Oil & Gas Upstream | Middle East | Operations / Handover | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2948 | For a Offshore Wind Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that coverage gap, theft, vandalism or security incident, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Brownfield Modification | Offshore Wind | South Asia | Feasibility & Concept | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2949 | For a Green Hydrogen Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that coverage gap, theft, vandalism or security incident, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Owner’s Engineering | Green Hydrogen | Southeast Asia | FEED / Basic Design | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2950 | For a Refining & Petrochemicals EPCM project in Latin America, there is a risk during Detailed Engineering that coverage gap, theft, vandalism or security incident, combined with inadequate verification, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPCM | Refining & Petrochemicals | Latin America | Detailed Engineering | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with inadequate verification. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2951 | For a Transmission & Substations EPC / Turnkey project in Europe, there is a risk during Feasibility & Concept that coverage gap, theft, vandalism or security incident, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPC / Turnkey | Transmission & Substations | Europe | Feasibility & Concept | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2952 | For a Carbon Capture, Utilization & Storage Installation project in Africa, there is a risk during FEED / Basic Design that coverage gap, theft, vandalism or security incident, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Installation | Carbon Capture, Utilization & Storage | Africa | FEED / Basic Design | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2953 | For a Hydropower Operations & Maintenance project in East Asia, there is a risk during Detailed Engineering that coverage gap, theft, vandalism or security incident, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Operations & Maintenance | Hydropower | East Asia | Detailed Engineering | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2954 | For a Nuclear Power Grid Interconnection project in North America, there is a risk during Procurement that coverage gap, theft, vandalism or security incident, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Grid Interconnection | Nuclear Power | North America | Procurement | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2955 | For a District Energy R&D / Technology Development project in Oceania, there is a risk during Manufacturing that coverage gap, theft, vandalism or security incident, combined with poor communication, may adversely affect project objectives through cost / time consequences. | Insurance & Security | R&D / Technology Development | District Energy | Oceania | Manufacturing | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with poor communication. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2956 | For a LNG EPCM project in Middle East, there is a risk during Detailed Engineering that coverage gap, theft, vandalism or security incident, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPCM | LNG | Middle East | Detailed Engineering | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2957 | For a Onshore Wind Commissioning & Start-up project in South Asia, there is a risk during Procurement that coverage gap, theft, vandalism or security incident, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Commissioning & Start-up | Onshore Wind | South Asia | Procurement | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2958 | For a Biomass / Waste-to-Energy Decommissioning project in Southeast Asia, there is a risk during Manufacturing that coverage gap, theft, vandalism or security incident, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Decommissioning | Biomass / Waste-to-Energy | Southeast Asia | Manufacturing | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2959 | For a Oil & Gas Upstream EPC / Turnkey project in Latin America, there is a risk during Construction that coverage gap, theft, vandalism or security incident, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPC / Turnkey | Oil & Gas Upstream | Latin America | Construction | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2960 | For a Offshore Wind Installation project in Global / Multi-country, there is a risk during Installation that coverage gap, theft, vandalism or security incident, combined with incorrect assumptions, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Installation | Offshore Wind | Global / Multi-country | Installation | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with incorrect assumptions. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2961 | For a Coal / Thermal Power R&D / Technology Development project in Africa, there is a risk during Manufacturing that coverage gap, theft, vandalism or security incident, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Insurance & Security | R&D / Technology Development | Coal / Thermal Power | Africa | Manufacturing | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2962 | For a Concentrated Solar Power Brownfield Modification project in East Asia, there is a risk during Construction that coverage gap, theft, vandalism or security incident, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Brownfield Modification | Concentrated Solar Power | East Asia | Construction | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2963 | For a Transmission & Substations Owner’s Engineering project in North America, there is a risk during Installation that coverage gap, theft, vandalism or security incident, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Owner’s Engineering | Transmission & Substations | North America | Installation | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2964 | For a Carbon Capture, Utilization & Storage EPCM project in Oceania, there is a risk during Pre-commissioning that coverage gap, theft, vandalism or security incident, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPCM | Carbon Capture, Utilization & Storage | Oceania | Pre-commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2965 | For a Hydropower Commissioning & Start-up project in Europe, there is a risk during Commissioning that coverage gap, theft, vandalism or security incident, combined with low technical maturity, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Commissioning & Start-up | Hydropower | Europe | Commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with low technical maturity. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2966 | For a Marine Energy Installation project in South Asia, there is a risk during Installation that coverage gap, theft, vandalism or security incident, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Installation | Marine Energy | South Asia | Installation | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2967 | For a Geothermal Operations & Maintenance project in Southeast Asia, there is a risk during Pre-commissioning that coverage gap, theft, vandalism or security incident, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Operations & Maintenance | Geothermal | Southeast Asia | Pre-commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2968 | For a LNG Grid Interconnection project in Latin America, there is a risk during Commissioning that coverage gap, theft, vandalism or security incident, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Grid Interconnection | LNG | Latin America | Commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2969 | For a Onshore Wind R&D / Technology Development project in Global / Multi-country, there is a risk during Operations / Handover that coverage gap, theft, vandalism or security incident, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Insurance & Security | R&D / Technology Development | Onshore Wind | Global / Multi-country | Operations / Handover | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Onshore Wind, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2970 | For a Biomass / Waste-to-Energy Brownfield Modification project in Middle East, there is a risk during Feasibility & Concept that coverage gap, theft, vandalism or security incident, combined with documentation gaps, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Brownfield Modification | Biomass / Waste-to-Energy | Middle East | Feasibility & Concept | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Biomass / Waste-to-Energy, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with documentation gaps. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2971 | For a Solar PV Commissioning & Start-up project in East Asia, there is a risk during Commissioning that coverage gap, theft, vandalism or security incident, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Commissioning & Start-up | Solar PV | East Asia | Commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2972 | For a Battery Energy Storage Decommissioning project in North America, there is a risk during Operations / Handover that coverage gap, theft, vandalism or security incident, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Decommissioning | Battery Energy Storage | North America | Operations / Handover | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2973 | For a Coal / Thermal Power EPC / Turnkey project in Oceania, there is a risk during Feasibility & Concept that coverage gap, theft, vandalism or security incident, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPC / Turnkey | Coal / Thermal Power | Oceania | Feasibility & Concept | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2974 | For a Concentrated Solar Power Installation project in Europe, there is a risk during FEED / Basic Design that coverage gap, theft, vandalism or security incident, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Installation | Concentrated Solar Power | Europe | FEED / Basic Design | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Concentrated Solar Power, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2975 | For a Transmission & Substations Operations & Maintenance project in Africa, there is a risk during Detailed Engineering that coverage gap, theft, vandalism or security incident, combined with external disruption, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Operations & Maintenance | Transmission & Substations | Africa | Detailed Engineering | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Transmission & Substations, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with external disruption. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2976 | For a Pumped Storage Brownfield Modification project in Southeast Asia, there is a risk during Feasibility & Concept that coverage gap, theft, vandalism or security incident, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Brownfield Modification | Pumped Storage | Southeast Asia | Feasibility & Concept | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2977 | For a Natural Gas / CCGT Owner’s Engineering project in Latin America, there is a risk during FEED / Basic Design that coverage gap, theft, vandalism or security incident, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Owner’s Engineering | Natural Gas / CCGT | Latin America | FEED / Basic Design | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2978 | For a Marine Energy EPCM project in Global / Multi-country, there is a risk during Detailed Engineering that coverage gap, theft, vandalism or security incident, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPCM | Marine Energy | Global / Multi-country | Detailed Engineering | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2979 | For a Geothermal Commissioning & Start-up project in Middle East, there is a risk during Procurement that coverage gap, theft, vandalism or security incident, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Commissioning & Start-up | Geothermal | Middle East | Procurement | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Geothermal, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2980 | For a LNG Decommissioning project in South Asia, there is a risk during Manufacturing that coverage gap, theft, vandalism or security incident, combined with governance delay, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Decommissioning | LNG | South Asia | Manufacturing | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to LNG, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with governance delay. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2981 | For a Green Hydrogen Operations & Maintenance project in North America, there is a risk during Detailed Engineering that coverage gap, theft, vandalism or security incident, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Operations & Maintenance | Green Hydrogen | North America | Detailed Engineering | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2982 | For a Refining & Petrochemicals Grid Interconnection project in Oceania, there is a risk during Procurement that coverage gap, theft, vandalism or security incident, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Grid Interconnection | Refining & Petrochemicals | Oceania | Procurement | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Procurement gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2983 | For a Solar PV R&D / Technology Development project in Europe, there is a risk during Manufacturing that coverage gap, theft, vandalism or security incident, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Insurance & Security | R&D / Technology Development | Solar PV | Europe | Manufacturing | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2984 | For a Battery Energy Storage Brownfield Modification project in Africa, there is a risk during Construction that coverage gap, theft, vandalism or security incident, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Brownfield Modification | Battery Energy Storage | Africa | Construction | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Battery Energy Storage, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2985 | For a Coal / Thermal Power Owner’s Engineering project in East Asia, there is a risk during Installation that coverage gap, theft, vandalism or security incident, combined with commercial misalignment, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Owner’s Engineering | Coal / Thermal Power | East Asia | Installation | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Coal / Thermal Power, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with commercial misalignment. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2986 | For a Nuclear Power Decommissioning project in Latin America, there is a risk during Manufacturing that coverage gap, theft, vandalism or security incident, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Decommissioning | Nuclear Power | Latin America | Manufacturing | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Manufacturing gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2987 | For a District Energy EPC / Turnkey project in Global / Multi-country, there is a risk during Construction that coverage gap, theft, vandalism or security incident, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPC / Turnkey | District Energy | Global / Multi-country | Construction | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the Construction gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2988 | For a Pumped Storage Installation project in Middle East, there is a risk during Installation that coverage gap, theft, vandalism or security incident, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Installation | Pumped Storage | Middle East | Installation | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2989 | For a Natural Gas / CCGT Operations & Maintenance project in South Asia, there is a risk during Pre-commissioning that coverage gap, theft, vandalism or security incident, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Operations & Maintenance | Natural Gas / CCGT | South Asia | Pre-commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Natural Gas / CCGT, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2990 | For a Marine Energy Grid Interconnection project in Southeast Asia, there is a risk during Commissioning that coverage gap, theft, vandalism or security incident, combined with quality escape, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Grid Interconnection | Marine Energy | Southeast Asia | Commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Marine Energy, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with quality escape. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2991 | For a Oil & Gas Upstream Owner’s Engineering project in Oceania, there is a risk during Installation that coverage gap, theft, vandalism or security incident, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Owner’s Engineering | Oil & Gas Upstream | Oceania | Installation | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Oil & Gas Upstream, the Installation gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Oceania. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2992 | For a Offshore Wind EPCM project in Europe, there is a risk during Pre-commissioning that coverage gap, theft, vandalism or security incident, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPCM | Offshore Wind | Europe | Pre-commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Offshore Wind, the Pre-commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Europe. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2993 | For a Green Hydrogen Commissioning & Start-up project in Africa, there is a risk during Commissioning that coverage gap, theft, vandalism or security incident, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Commissioning & Start-up | Green Hydrogen | Africa | Commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Green Hydrogen, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Africa. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2994 | For a Refining & Petrochemicals Decommissioning project in East Asia, there is a risk during Operations / Handover that coverage gap, theft, vandalism or security incident, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Decommissioning | Refining & Petrochemicals | East Asia | Operations / Handover | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Refining & Petrochemicals, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in East Asia. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2995 | For a Solar PV EPC / Turnkey project in North America, there is a risk during Feasibility & Concept that coverage gap, theft, vandalism or security incident, combined with access constraint, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPC / Turnkey | Solar PV | North America | Feasibility & Concept | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Solar PV, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with access constraint. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in North America. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2996 | For a Carbon Capture, Utilization & Storage Grid Interconnection project in Global / Multi-country, there is a risk during Commissioning that coverage gap, theft, vandalism or security incident, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Grid Interconnection | Carbon Capture, Utilization & Storage | Global / Multi-country | Commissioning | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Carbon Capture, Utilization & Storage, the Commissioning gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Global / Multi-country. | Risk & Insurance Manager | 0.8% | 800000 | 15% | 120000 | 35% | 78000 | 0.078% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2997 | For a Hydropower R&D / Technology Development project in Middle East, there is a risk during Operations / Handover that coverage gap, theft, vandalism or security incident, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Insurance & Security | R&D / Technology Development | Hydropower | Middle East | Operations / Handover | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Hydropower, the Operations / Handover gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Middle East. | Risk & Insurance Manager | 0.9% | 900000 | 15% | 135000 | 35% | 87750 | 0.08775% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2998 | For a Nuclear Power Brownfield Modification project in South Asia, there is a risk during Feasibility & Concept that coverage gap, theft, vandalism or security incident, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Brownfield Modification | Nuclear Power | South Asia | Feasibility & Concept | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Nuclear Power, the Feasibility & Concept gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in South Asia. | Risk & Insurance Manager | 1% | 1000000 | 15% | 150000 | 35% | 97500 | 0.0975% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-2999 | For a District Energy Owner’s Engineering project in Southeast Asia, there is a risk during FEED / Basic Design that coverage gap, theft, vandalism or security incident, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Insurance & Security | Owner’s Engineering | District Energy | Southeast Asia | FEED / Basic Design | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to District Energy, the FEED / Basic Design gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Southeast Asia. | Risk & Insurance Manager | 1.1% | 1100000 | 15% | 165000 | 35% | 107250 | 0.1073% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.
GER-3000 | For a Pumped Storage EPCM project in Latin America, there is a risk during Detailed Engineering that coverage gap, theft, vandalism or security incident, combined with performance variability, may adversely affect project objectives through cost / time consequences. | Insurance & Security | EPCM | Pumped Storage | Latin America | Detailed Engineering | Shared | L | Cost / Time | Establish controls for coverage gap, theft, vandalism or security incident; assign actions, verify evidence, and review residual exposure at each gate. Tailor the response to Pumped Storage, the Detailed Engineering gate, local law, interfaces, and the selected delivery model. | Increasing unresolved actions, late milestones, repeated exceptions, or adverse trend associated with performance variability. Also monitor phase-gate slippage, unresolved interfaces, supplier status, and regulatory changes in Latin America. | Risk & Insurance Manager | 1.2% | 1200000 | 15% | 180000 | 35% | 117000 | 0.117% | Parametric screening: exposure % × TCV × probability; residual EMV after mitigation. | Research-informed synthesis: FIDIC risk themes and global construction/energy project literature; not verbatim source text.

## Category Summary
Global Energy Project Risk Library: 3,000-Risk Summary
Risk Category | Risk Count | Share of Library | High Probability | Contractor Allocated | Employer Allocated | Shared Allocation
Contractual | 100 | 3.333% | 0 | 0 | 0 | 100
Schedule | 100 | 3.333% | 100 | 100 | 0 | 0
Cost & Estimating | 100 | 3.333% | 100 | 100 | 0 | 0
Design & Engineering | 100 | 3.333% | 100 | 100 | 0 | 0
Quality & Defects | 100 | 3.333% | 0 | 100 | 0 | 0
HSE | 100 | 3.333% | 0 | 100 | 0 | 0
Environmental | 100 | 3.333% | 0 | 0 | 0 | 100
Political & Country | 100 | 3.333% | 0 | 0 | 100 | 0
Regulatory & Change in Law | 100 | 3.333% | 0 | 0 | 0 | 100
Permits & Approvals | 100 | 3.333% | 100 | 0 | 100 | 0
Site & Ground Conditions | 100 | 3.333% | 0 | 0 | 0 | 100
Weather & Natural Hazards | 100 | 3.333% | 0 | 0 | 0 | 100
Force Majeure / Exceptional Events | 100 | 3.333% | 0 | 0 | 0 | 100
Procurement & Supply Chain | 100 | 3.333% | 100 | 100 | 0 | 0
Logistics & Customs | 100 | 3.333% | 0 | 100 | 0 | 0
Labour & Skills | 100 | 3.333% | 100 | 100 | 0 | 0
Plant & Equipment | 100 | 3.333% | 0 | 100 | 0 | 0
Interfaces | 100 | 3.333% | 100 | 0 | 0 | 100
Stakeholder & Community | 100 | 3.333% | 0 | 0 | 100 | 0
Land & Right of Way | 100 | 3.333% | 0 | 0 | 100 | 0
Payment & Cash Flow | 100 | 3.333% | 0 | 0 | 100 | 0
Claims & Disputes | 100 | 3.333% | 0 | 0 | 0 | 100
Change & Scope | 100 | 3.333% | 100 | 0 | 100 | 0
Technology & Maturity | 100 | 3.333% | 0 | 100 | 0 | 0
Digital, Data & Cybersecurity | 100 | 3.333% | 0 | 0 | 0 | 100
Commissioning & Start-up | 100 | 3.333% | 100 | 100 | 0 | 0
Operations & Maintainability | 100 | 3.333% | 0 | 100 | 0 | 0
Governance & Decision Making | 100 | 3.333% | 0 | 0 | 0 | 100
Fraud, Ethics & Compliance | 100 | 3.333% | 0 | 0 | 0 | 100
Insurance & Security | 100 | 3.333% | 0 | 0 | 0 | 100
Total | 3000 | 100%

## Coverage Matrix
Coverage Dimensions
Dimension | Included Values | Number of Values | Application Note
Project types | EPC / Turnkey, EPCM, R&D / Technology Development, Installation, Commissioning & Start-up, Brownfield Modification, Operations & Maintenance, Decommissioning, Owner’s Engineering, Grid Interconnection | 10 | Use filters to isolate the relevant delivery model.
Energy segments | Onshore Wind, Offshore Wind, Solar PV, Concentrated Solar Power, Hydropower, Pumped Storage, Geothermal, Biomass / Waste-to-Energy, Green Hydrogen, Battery Energy Storage, Transmission & Substations, Nuclear Power, Natural Gas / CCGT, LNG, Oil & Gas Upstream, Refining & Petrochemicals, Coal / Thermal Power, Carbon Capture, Utilization & Storage, District Energy, Marine Energy | 20 | Covers renewable, low-carbon and conventional energy.
Geographic contexts | Europe, Middle East, Africa, South Asia, East Asia, Southeast Asia, North America, Latin America, Oceania, Global / Multi-country | 10 | Regional labels are screening contexts, not country-specific legal conclusions.
Lifecycle phases | Feasibility & Concept, FEED / Basic Design, Detailed Engineering, Procurement, Manufacturing, Construction, Installation, Pre-commissioning, Commissioning, Operations / Handover | 10 | Risks are contextualized from concept through handover and operations.
Risk categories | Contractual, Schedule, Cost & Estimating, Design & Engineering, Quality & Defects, HSE, Environmental, Political & Country, Regulatory & Change in Law, Permits & Approvals, Site & Ground Conditions, Weather & Natural Hazards, Force Majeure / Exceptional Events, Procurement & Supply Chain, Logistics & Customs, Labour & Skills, Plant & Equipment, Interfaces, Stakeholder & Community, Land & Right of Way, Payment & Cash Flow, Claims & Disputes, Change & Scope, Technology & Maturity, Digital, Data & Cybersecurity, Commissioning & Start-up, Operations & Maintainability, Governance & Decision Making, Fraud, Ethics & Compliance, Insurance & Security | 30 | Categories synthesize contractual and research-based risk themes.

## Method & Sources
Method, Limitations and Research Basis
Deliverable | 3,000 distinct contextualized risk statements created by extending 600 seed risks across project type, energy technology, geography and lifecycle dimensions.
Important limitation | This is a research-informed synthesis, not a claim to contain every risk from every publication worldwide. It does not reproduce copyrighted FIDIC clauses or journal text verbatim.
Use of probability | L/M/H values are initial screening defaults inherited from the category-level seed library. Reassess them using project evidence and an approved scoring matrix.
Use of allocation | Employer, Contractor and Shared allocations are screening assumptions. The signed contract, Particular Conditions, governing law and project facts control actual allocation.
Attached research article | Dikmen, Eken, Erol and Birgonul (2025), Computers in Industry 166, 104251. https://doi.org/10.1016/j.compind.2025.104251
Systematic review | Su and Khallaf (2022), Sustainability 14, 6412. https://doi.org/10.3390/su14116412
Taxonomic review | Sarvari (2026), Eng 7, 380. https://doi.org/10.3390/eng7080380
Energy investment context | International Energy Agency, World Energy Investment 2025. https://www.iea.org/reports/world-energy-investment-2025
EPC text-mining study | Choi et al. (2021), Energies 14, 4632. https://doi.org/10.3390/en14154632
Recommended workflow | Filter by energy segment, project type and lifecycle phase; workshop probability and impact; assign a named accountable owner; link each selected risk to project evidence and controls.
Monetary quantification | Gross exposure equals a category-based percentage of editable Total Contract Value. EMV equals gross exposure multiplied by the L/M/H probability factor. Residual exposure equals EMV multiplied by one minus mitigation effectiveness. These are parametric screening assumptions, not article-derived monetary estimates.